## Summary
Data-quality digest: Partner B
Synthetic data – not real findings
Item | Value
Partner | Partner B
States | Adamawa
Data as of | 2026-09-27
Submissions received | 1624
Interviews kept | 1519
Interviews removed | 105
Values corrected | 11
Interviews flagged for follow-up | 100
Households targeted | 1620
Households achieved | 1519
Progress against target | 93.8%

## Follow up
Interviews flagged: please check with the enumerator
Synthetic data – not real findings
date | enumerator_id | cluster_id | household_id | _uuid | check | issue | value
2026-08-17 | enum_B_22 | idp_NG002020_C11 | idp_NG002020_C11_H06 | 3c299c99-1361-4821-87dd-b632c280fdd6 | fcs_hhs_contradiction | Acceptable food consumption with severe hunger | FCS 93.5, HHS 6
2026-08-18 | enum_B_21 | non_idp_NG002020_C01 | non_idp_NG002020_C01_H03 | ac8c16a6-7559-4a90-99cc-e7db6fea6699 | fcs_flat | Every food group given the same number of days | 0
2026-08-19 | enum_B_15 | idp_NG002014_C05 | idp_NG002014_C05_H03 | ba941ed8-5707-4fcb-828b-65443889b465 | fcs_hhs_contradiction | Acceptable food consumption with severe hunger | FCS 37.0, HHS 4
2026-08-20 | enum_B_09 | non_idp_NG002005_C15 | non_idp_NG002005_C15_H01 | 59765fdd-d9d8-44a6-805b-7eddc0c94db2 | fcs_hhs_contradiction | Acceptable food consumption with severe hunger | FCS 93.5, HHS 6
2026-08-20 | enum_B_23 | idp_NG002021_C13 | idp_NG002021_C13_H06 | 6b318655-1822-4cb2-884a-ee84e1b94f63 | fcs_flat | Every food group given the same number of days | 7
2026-08-20 | enum_B_24 | idp_NG002021_C13 | idp_NG002021_C13_H01 | 63cd4d17-689f-4384-a935-1b7cb5a4d93b | children_exceed_hh | More children than household members | 1 + 8 children, household of 7
2026-08-21 | enum_B_01 | idp_NG002002_C04 | idp_NG002002_C04_H02 | f2453bd9-f1ea-489c-8ae7-d1d1bc1199ca | fcs_hhs_contradiction | Acceptable food consumption with severe hunger | FCS 93.5, HHS 6
2026-08-21 | enum_B_01 | idp_NG002002_C04 | idp_NG002002_C04_H05 | 83b53a4f-a8a7-40e7-8d03-05d61c64a5e7 | fcs_hhs_contradiction | Acceptable food consumption with severe hunger | FCS 52.5, HHS 4
2026-08-21 | enum_B_09 | non_idp_NG002005_C16 | non_idp_NG002005_C16_H01 | c381fe33-3dd3-405a-95ab-e9b015d0beca | gps_far | GPS point 1.0 km from the household | 988
2026-08-21 | enum_B_09 | non_idp_NG002005_C16 | non_idp_NG002005_C16_H04 | 4fd17bad-907a-4bc8-82fa-90272d337c8d | gps_far | GPS point 4.8 km from the household | 4799
2026-08-22 | enum_B_01 | idp_NG002002_C05 | idp_NG002002_C05_H02 | 9a156316-0b02-4d7a-8fc1-b15ae288c9dd | children_exceed_hh | More children than household members | 0 + 7 children, household of 6
2026-08-22 | enum_B_04 | non_idp_NG002002_C13 | non_idp_NG002002_C13_H04 | 8cfffb30-9a3c-429e-a85a-31eb1184006a | fcs_flat | Every food group given the same number of days | 0
2026-08-22 | enum_B_09 | non_idp_NG002005_C17 | non_idp_NG002005_C17_H03 | 5d0dad53-9fa0-4cce-9f0c-494dab5028fa | gps_far | GPS point 3.7 km from the household | 3708
2026-08-23 | enum_B_01 | idp_NG002002_C06 | idp_NG002002_C06_H05 | 80c8f78e-a6c2-40ce-b549-34aecbbab377 | gps_far | GPS point 1.0 km from the household | 996
2026-08-23 | enum_B_24 | idp_NG002021_C16 | idp_NG002021_C16_R01 | 57a8d737-83f6-4b02-90c4-a8819d54b139 | gps_far | GPS point 1.8 km from the household | 1848
2026-08-24 | enum_B_22 | non_idp_NG002020_C17 | non_idp_NG002020_C17_H06 | e50bc79a-541d-42b2-b056-7dd2111a5c35 | attending_exceed_school_age | More children attending school than of school age | 4
2026-08-24 | enum_B_24 | non_idp_NG002021_C01 | non_idp_NG002021_C01_H02 | 5e2ff38f-3a7b-4db1-8399-3393e8f39b90 | gps_far | GPS point 2.9 km from the household | 2870
2026-08-25 | enum_B_13 | idp_NG002008_C12 | idp_NG002008_C12_H03 | 8cb66491-da9f-47d0-bdac-e3ff1dcf6f51 | fcs_hhs_contradiction | Acceptable food consumption with severe hunger | FCS 56.5, HHS 4
2026-08-25 | enum_B_24 | non_idp_NG002021_C02 | non_idp_NG002021_C02_R01 | 19291c67-de29-4e78-8e7c-77adc659de9f | fcs_hhs_contradiction | Acceptable food consumption with severe hunger | FCS 36.0, HHS 4
2026-08-26 | enum_B_01 | idp_NG002002_C08 | idp_NG002002_C08_H06 | e2692dbe-72aa-4824-835f-1dd4501af05b | fcs_flat | Every food group given the same number of days | 7
2026-08-26 | enum_B_05 | idp_NG002004_C14 | idp_NG002004_C14_H02 | c277b706-10c7-4d3f-b7a9-0bb58ad1c25a | fcs_hhs_contradiction | Acceptable food consumption with severe hunger | FCS 93.5, HHS 6
2026-08-26 | enum_B_09 | idp_NG002007_C03 | idp_NG002007_C03_R01 | 42cf71c8-efe0-4595-9d39-3a317815ebc8 | fcs_hhs_contradiction | Acceptable food consumption with severe hunger | FCS 37.5, HHS 6
2026-08-26 | enum_B_22 | idp_NG002021_C02 | idp_NG002021_C02_R01 | 2199fda1-bbff-4291-b0b1-cb64f5f8b4c6 | fcs_flat | Every food group given the same number of days | 7
2026-08-27 | enum_B_02 | idp_NG002002_C09 | idp_NG002002_C09_H01 | e08cf752-bf59-47b0-83ab-73b5fb39d6c4 | gps_far | GPS point 4.2 km from the household | 4182
2026-08-27 | enum_B_02 | idp_NG002002_C09 | idp_NG002002_C09_H03 | a9454754-dacf-40c6-9eaa-a63fe03fa1d1 | fcs_hhs_contradiction | Acceptable food consumption with severe hunger | FCS 41.5, HHS 4
2026-08-27 | enum_B_02 | idp_NG002002_C09 | idp_NG002002_C09_H05 | d2329fbc-f97e-43b1-90f5-ee86eca5b374 | gps_far | GPS point 4.2 km from the household | 4159
2026-08-27 | enum_B_05 | idp_NG002004_C15 | idp_NG002004_C15_R01 | 39bd258e-3a97-45ee-9936-e6239513fe73 | gps_far | GPS point 3.9 km from the household | 3907
2026-08-27 | enum_B_06 | idp_NG002004_C15 | idp_NG002004_C15_R02 | 38d08d54-91ca-4f9f-baf2-0e8ea9c71644 | fcs_hhs_contradiction | Acceptable food consumption with severe hunger | FCS 93.5, HHS 6
2026-08-27 | enum_B_18 | non_idp_NG002014_C10 | non_idp_NG002014_C10_H02 | 256c17da-173f-40b9-bf33-269150504f1a | children_exceed_hh | More children than household members | 1 + 7 children, household of 6
2026-08-28 | enum_B_04 | idp_NG002004_C01 | idp_NG002004_C01_H01 | 513e23ce-f686-4dd7-9955-7b0d6aa341f5 | fcs_hhs_contradiction | Acceptable food consumption with severe hunger | FCS 44.0, HHS 4
2026-08-28 | enum_B_20 | non_idp_NG002018_C07 | non_idp_NG002018_C07_H01 | 7a22231f-c440-4d50-a0a1-bb9bad52c465 | gps_far | GPS point 1.4 km from the household | 1401
2026-08-28 | enum_B_22 | idp_NG002021_C04 | idp_NG002021_C04_H03 | 8454994d-d224-466a-b0fa-eff8ac19131d | fcs_hhs_contradiction | Acceptable food consumption with severe hunger | FCS 44.5, HHS 4
2026-08-29 | enum_B_05 | non_idp_NG002004_C02 | non_idp_NG002004_C02_R01 | fedd865e-d01b-41cf-b81a-3c65d7d95c67 | children_exceed_hh | More children than household members | 1 + 8 children, household of 6
2026-08-29 | enum_B_12 | non_idp_NG002007_C09 | non_idp_NG002007_C09_H04 | 00b99931-3642-4f06-b32f-c46103b10559 | fcs_flat | Every food group given the same number of days | 7
2026-08-29 | enum_B_21 | idp_NG002021_C06 | idp_NG002021_C06_H06 | abba0b1c-1ad3-4310-a9a8-8e1b9496fa10 | gps_far | GPS point 1.5 km from the household | 1485
2026-08-30 | enum_B_03 | idp_NG002004_C03 | idp_NG002004_C03_H04 | 73355356-4be0-48f9-bfd0-eff84a444148 | fcs_hhs_contradiction | Acceptable food consumption with severe hunger | FCS 93.5, HHS 6
2026-08-31 | enum_B_07 | idp_NG002005_C07 | idp_NG002005_C07_H03 | c81fb378-7b68-474c-88d7-0a1b6ae9bd21 | gps_far | GPS point 3.7 km from the household | 3742
2026-08-31 | enum_B_08 | idp_NG002005_C07 | idp_NG002005_C07_H06 | ad9c9a72-48f4-418f-be5f-6fc7618549fd | fcs_hhs_contradiction | Acceptable food consumption with severe hunger | FCS 93.5, HHS 6
2026-09-01 | enum_B_02 | idp_NG002002_C14 | idp_NG002002_C14_H06 | 565827d5-2a27-4538-80fb-70df2fd6b739 | children_exceed_hh | More children than household members | 1 + 7 children, household of 7
2026-09-01 | enum_B_08 | idp_NG002005_C08 | idp_NG002005_C08_H01 | 316ec145-3845-448a-8ed0-816a841b8596 | fcs_hhs_contradiction | Acceptable food consumption with severe hunger | FCS 35.5, HHS 5
2026-09-01 | enum_B_13 | non_idp_NG002008_C06 | non_idp_NG002008_C06_H05 | dacae3c2-ce53-431a-9252-37a32d19bb40 | gps_far | GPS point 4.2 km from the household | 4250
2026-09-02 | enum_B_10 | idp_NG002007_C05 | idp_NG002007_C05_H05 | 6bf4496a-a813-44eb-b94c-e92702e14804 | gps_far | GPS point 4.3 km from the household | 4262
2026-09-02 | enum_B_12 | non_idp_NG002007_C11 | non_idp_NG002007_C11_H06 | 87662d32-0bbf-4c44-82d3-4999b5a7a78d | fcs_hhs_contradiction | Acceptable food consumption with severe hunger | FCS 50.0, HHS 4
2026-09-02 | enum_B_17 | non_idp_NG002014_C16 | non_idp_NG002014_C16_R02 | 5f3d322d-bbdb-4d7e-9ba2-00dc24585cb3 | gps_far | GPS point 3.1 km from the household | 3098
2026-09-03 | enum_B_01 | non_idp_NG002002_C02 | non_idp_NG002002_C02_H06 | a3538caa-6a6a-4757-acb6-c33e95de3430 | children_exceed_hh | More children than household members | 0 + 9 children, household of 7
2026-09-03 | enum_B_22 | idp_NG002021_C07 | idp_NG002021_C07_H02 | 7e5bf250-c47e-4574-8196-bcd91d23dd27 | gps_far | GPS point 4.4 km from the household | 4423
2026-09-04 | enum_B_04 | idp_NG002004_C06 | idp_NG002004_C06_H03 | 03c83ef8-5266-4c36-bd0e-bddf257fb06a | fcs_flat | Every food group given the same number of days | 7
2026-09-04 | enum_B_15 | non_idp_NG002014_C04 | non_idp_NG002014_C04_H05 | 2810a9a3-1f13-4b70-b524-81ec10ba6b6d | fcs_hhs_contradiction | Acceptable food consumption with severe hunger | FCS 93.5, HHS 6
2026-09-04 | enum_B_24 | non_idp_NG002021_C09 | non_idp_NG002021_C09_H01 | 13b32648-269f-408a-85f1-23b54288a6a2 | gps_far | GPS point 2.3 km from the household | 2273
2026-09-05 | enum_B_11 | non_idp_NG002007_C13 | non_idp_NG002007_C13_H03 | 2fca8368-6789-4d16-9d55-50ac9c6ca4fc | fcs_hhs_contradiction | Acceptable food consumption with severe hunger | FCS 93.5, HHS 6
2026-09-05 | enum_B_12 | non_idp_NG002007_C13 | non_idp_NG002007_C13_H04 | a26d48a5-95fd-43e8-bcd6-5f72d515236d | fcs_flat | Every food group given the same number of days | 7
2026-09-05 | enum_B_13 | non_idp_NG002008_C08 | non_idp_NG002008_C08_H05 | c3f1f09f-e418-456e-b032-dab03305ac87 | gps_far | GPS point 4.3 km from the household | 4296
2026-09-05 | enum_B_14 | non_idp_NG002008_C08 | non_idp_NG002008_C08_H02 | 09a22333-82b3-4ca7-8b08-65ebb253173b | gps_far | GPS point 1.4 km from the household | 1387
2026-09-05 | enum_B_14 | non_idp_NG002008_C08 | non_idp_NG002008_C08_H06 | 3ae7bd55-7548-4065-807b-02b203c9fb39 | fcs_flat | Every food group given the same number of days | 0
2026-09-06 | enum_B_03 | idp_NG002004_C07 | idp_NG002004_C07_H02 | 26a984c7-c45c-42e4-ae66-f4c710cab07e | fcs_hhs_contradiction | Acceptable food consumption with severe hunger | FCS 39.0, HHS 4
2026-09-06 | enum_B_03 | idp_NG002004_C07 | idp_NG002004_C07_H04 | 1f312413-5c0c-418b-9d00-9c45ca7328b7 | children_exceed_hh | More children than household members | 1 + 8 children, household of 6
2026-09-06 | enum_B_05 | non_idp_NG002004_C10 | non_idp_NG002004_C10_H04 | 92b741ba-d067-4d93-9d88-62efedd334e6 | attending_exceed_school_age | More children attending school than of school age | 4
2026-09-06 | enum_B_05 | non_idp_NG002004_C10 | non_idp_NG002004_C10_H06 | d5da9cdd-d355-45fc-9e93-f174e95fa726 | children_exceed_hh | More children than household members | 2 + 8 children, household of 8
2026-09-06 | enum_B_07 | idp_NG002005_C13 | idp_NG002005_C13_H04 | 58341374-492a-463c-93ba-0953c5d968cd | fcs_hhs_contradiction | Acceptable food consumption with severe hunger | FCS 37.0, HHS 6
2026-09-06 | enum_B_15 | non_idp_NG002014_C07 | non_idp_NG002014_C07_H05 | 80c30717-b20a-4369-8f3d-2a838f2ed03d | gps_far | GPS point 1.2 km from the household | 1191
2026-09-07 | enum_B_09 | idp_NG002007_C10 | idp_NG002007_C10_H05 | 84a285e7-b326-4fba-9f17-8bbf61b1d643 | gps_far | GPS point 5.0 km from the household | 4956
2026-09-07 | enum_B_14 | non_idp_NG002008_C09 | non_idp_NG002008_C09_H05 | f1e64727-9607-4d2a-ad2b-7baf781bed56 | gps_far | GPS point 0.7 km from the household | 728
2026-09-08 | enum_B_04 | idp_NG002004_C08 | idp_NG002004_C08_H03 | 37ed0393-d76a-43dd-baca-9044ff2e3d1f | fcs_hhs_contradiction | Acceptable food consumption with severe hunger | FCS 93.5, HHS 6
2026-09-08 | enum_B_07 | non_idp_NG002005_C01 | non_idp_NG002005_C01_H02 | d2f6fd35-3c21-441a-bdb3-8776bfd26143 | fcs_hhs_contradiction | Acceptable food consumption with severe hunger | FCS 40.0, HHS 5
2026-09-08 | enum_B_09 | idp_NG002007_C11 | idp_NG002007_C11_H02 | 4428e0c1-fa5f-4871-b8ae-9d56385ead16 | attending_exceed_school_age | More children attending school than of school age | 3
2026-09-08 | enum_B_17 | idp_NG002018_C05 | idp_NG002018_C05_H02 | d0b151aa-c1ff-4036-81da-efc9b7682815 | fcs_flat | Every food group given the same number of days | 7
2026-09-09 | enum_B_19 | non_idp_NG002018_C17 | non_idp_NG002018_C17_H06 | de2514cb-52f5-4400-b0bd-0194626022ac | gps_far | GPS point 0.8 km from the household | 765
2026-09-09 | enum_B_20 | non_idp_NG002018_C17 | non_idp_NG002018_C17_H05 | a632de33-2ce2-4895-a0c9-fdc8f17fd316 | fcs_hhs_contradiction | Acceptable food consumption with severe hunger | FCS 93.5, HHS 6
2026-09-09 | enum_B_21 | non_idp_NG002020_R1_01 | non_idp_NG002020_R1_01_H02 | 0a009a43-f394-4901-9ceb-583d18559438 | fcs_hhs_contradiction | Acceptable food consumption with severe hunger | FCS 39.5, HHS 4
2026-09-09 | enum_B_22 | non_idp_NG002020_R1_01 | non_idp_NG002020_R1_01_H06 | f0851b94-125e-47ca-b368-331ee4dba990 | fcs_hhs_contradiction | Acceptable food consumption with severe hunger | FCS 93.5, HHS 6
2026-09-11 | enum_B_05 | non_idp_NG002004_C17 | non_idp_NG002004_C17_H05 | 8d66e239-25b1-47c2-9bcc-82ee78d4c0c8 | gps_far | GPS point 1.8 km from the household | 1827
2026-09-11 | enum_B_07 | non_idp_NG002005_C04 | non_idp_NG002005_C04_H06 | a2716ab8-d725-4965-bc2f-bf4a2f90a1c5 | gps_far | GPS point 1.8 km from the household | 1842
2026-09-11 | enum_B_09 | idp_NG002007_C13 | idp_NG002007_C13_H02 | ac6f0372-7144-42c7-b8a0-5e47b5a0690e | fcs_hhs_contradiction | Acceptable food consumption with severe hunger | FCS 38.0, HHS 5
2026-09-12 | enum_B_07 | non_idp_NG002005_C05 | non_idp_NG002005_C05_H01 | dbe6e2bb-c6b8-4f51-a4e9-68d027df394a | gps_far | GPS point 2.4 km from the household | 2360
2026-09-12 | enum_B_12 | non_idp_NG002007_C17 | non_idp_NG002007_C17_H02 | 5bda6973-8ddb-4849-a238-f3df14afd0ea | gps_far | GPS point 1.4 km from the household | 1417
2026-09-12 | enum_B_13 | non_idp_NG002008_C13 | non_idp_NG002008_C13_H04 | f1744c53-a151-407e-a5b2-8f765b773f76 | fcs_hhs_contradiction | Acceptable food consumption with severe hunger | FCS 58.0, HHS 6
2026-09-12 | enum_B_18 | idp_NG002018_C08 | idp_NG002018_C08_H04 | c087e7ae-8b46-4bc6-af0f-f0150f3c1e7f | gps_far | GPS point 3.6 km from the household | 3648
2026-09-13 | enum_B_06 | idp_NG002005_C02 | idp_NG002005_C02_H05 | 53b54032-38f7-4c0a-8d86-0095f85e49b1 | attending_exceed_school_age | More children attending school than of school age | 2
2026-09-13 | enum_B_10 | idp_NG002007_C14 | idp_NG002007_C14_H03 | f07c8ede-86b4-4599-891f-7233a8bd2f07 | fcs_hhs_contradiction | Acceptable food consumption with severe hunger | FCS 93.5, HHS 6
2026-09-13 | enum_B_19 | idp_NG002020_C03 | idp_NG002020_C03_H04 | c9143f67-8882-4abd-b590-4b2024951b70 | attending_exceed_school_age | More children attending school than of school age | 2
2026-09-14 | enum_B_09 | non_idp_NG002007_C01 | non_idp_NG002007_C01_H01 | da7224b1-110e-4b0e-ad3c-ac920a24d85b | fcs_flat | Every food group given the same number of days | 7
2026-09-14 | enum_B_18 | idp_NG002018_C10 | idp_NG002018_C10_H03 | 64b368ac-f775-46af-b0f5-2d35088cf465 | gps_far | GPS point 4.0 km from the household | 4018
2026-09-14 | enum_B_20 | idp_NG002020_C04 | idp_NG002020_C04_H05 | 2679cf85-4550-407a-aac3-eb65b675df6e | fcs_flat | Every food group given the same number of days | 7
2026-09-15 | enum_B_03 | idp_NG002004_C13 | idp_NG002004_C13_H05 | e33f7df1-be10-4acd-b4bb-b8857355b6fd | fcs_hhs_contradiction | Acceptable food consumption with severe hunger | FCS 46.5, HHS 4
2026-09-16 | enum_B_05 | non_idp_NG002004_R1_01 | non_idp_NG002004_R1_01_H04 | bf5df403-2a02-4af8-91ce-033b613804ff | fcs_flat | Every food group given the same number of days | 0
2026-09-16 | enum_B_11 | idp_NG002008_C02 | idp_NG002008_C02_R01 | fc3a7f80-2f16-4f18-ab13-7b8359dbf89d | children_exceed_hh | More children than household members | 1 + 7 children, household of 6
2026-09-16 | enum_B_17 | non_idp_NG002018_C02 | non_idp_NG002018_C02_H01 | 05cae4ef-4b51-40f4-a004-be2212306aae | fcs_hhs_contradiction | Acceptable food consumption with severe hunger | FCS 36.5, HHS 4
2026-09-17 | enum_B_04 | non_idp_NG002002_R2_01 | non_idp_NG002002_R2_01_H04 | 37a0127b-f043-4bc3-9316-df2551d1ea53 | fcs_hhs_contradiction | Acceptable food consumption with severe hunger | FCS 49.0, HHS 4
2026-09-17 | enum_B_09 | non_idp_NG002005_R2_01 | non_idp_NG002005_R2_01_H04 | b40a48c5-96e8-47ee-bb8b-8dd8385d201a | children_exceed_hh | More children than household members | 0 + 10 children, household of 7
2026-09-17 | enum_B_10 | non_idp_NG002005_R2_01 | non_idp_NG002005_R2_01_H02 | df91d546-dd57-403c-a4b3-7d1ccd59a87c | attending_exceed_school_age | More children attending school than of school age | 4
2026-09-17 | enum_B_14 | non_idp_NG002008_C15 | non_idp_NG002008_C15_R01 | 9dc3a35c-5aaa-4107-8a04-f60347eb99c6 | gps_far | GPS point 1.9 km from the household | 1853
2026-09-18 | enum_B_03 | non_idp_NG002002_R2_02 | non_idp_NG002002_R2_02_R02 | f057e314-77d3-41fb-b0da-d2f371199de3 | gps_far | GPS point 4.8 km from the household | 4775
2026-09-18 | enum_B_12 | idp_NG002008_C04 | idp_NG002008_C04_H06 | 292f0cc6-9968-4fb8-9d2a-3abf2f43c339 | fcs_hhs_contradiction | Acceptable food consumption with severe hunger | FCS 93.5, HHS 6
2026-09-18 | enum_B_14 | idp_NG002014_C01 | idp_NG002014_C01_H06 | 0e94d706-09f0-4fdd-ac43-6e6e7d7dab16 | fcs_hhs_contradiction | Acceptable food consumption with severe hunger | FCS 36.0, HHS 5
2026-09-18 | enum_B_18 | non_idp_NG002018_C04 | non_idp_NG002018_C04_H03 | 69a0d44c-ab17-4c26-bc45-0e50d62c154f | fcs_hhs_contradiction | Acceptable food consumption with severe hunger | FCS 36.5, HHS 5
2026-09-19 | enum_B_19 | idp_NG002020_C09 | idp_NG002020_C09_H01 | c7d17360-6112-44a7-beb4-59ac63fa61b9 | fcs_flat | Every food group given the same number of days | 0
2026-09-20 | enum_B_13 | non_idp_NG002008_R1_01 | non_idp_NG002008_R1_01_H05 | 7426f481-1560-4ef7-a0d9-6b2c375a770c | attending_exceed_school_age | More children attending school than of school age | 3
2026-09-21 | enum_B_13 | non_idp_NG002008_R1_02 | non_idp_NG002008_R1_02_H05 | aff7d9d7-e4ae-44c7-bb9c-b55a7c657d68 | gps_far | GPS point 2.4 km from the household | 2430
2026-09-21 | enum_B_13 | non_idp_NG002008_R1_02 | non_idp_NG002008_R1_02_H06 | 6162a9f8-8ab9-4127-b8c8-b530f4750da5 | fcs_hhs_contradiction | Acceptable food consumption with severe hunger | FCS 93.5, HHS 6
2026-09-23 | enum_B_11 | idp_NG002008_C07 | idp_NG002008_C07_H01 | 5e8a6423-a87a-48d9-b853-919d35589dc8 | gps_far | GPS point 1.4 km from the household | 1408

## Removed
Interviews removed from the dataset, and why
Synthetic data – not real findings
date | enumerator_id | cluster_id | household_id | _uuid | check_id | reason
2026-08-17 | enum_B_16 | idp_NG002014_C02 | idp_NG002014_C02_R01 | fdb27762-bc14-4be4-b939-85da1bd3b74a | C01 | Respondent did not consent
2026-08-17 | enum_B_22 | idp_NG002020_C91 | idp_NG002020_C11_H02 | 97a192b6-a89a-40ab-adf0-d3af0b9081e4 | C05 | Cluster code not in the sample
2026-08-18 | enum_B_11 | non_idp_NG002020_C08 | non_idp_NG002020_C08_H04 | eaf44512-c663-4f6a-9702-9f81776dedb0 | C06 | Cluster had been reported inaccessible
2026-08-18 | enum_B_22 | non_idp_NG002020_C01 | non_idp_NG002020_C01_H01 | fd11a031-0efa-4d85-a6b5-d2defcd08578 | C01 | Respondent did not consent
2026-08-19 | enum_B_01 | idp_NG002002_C02 | idp_NG002002_C02_H04 | 72dd121e-6c2d-4a12-9b47-99adb2933d02 | C01 | Respondent did not consent
2026-08-19 | enum_B_02 | idp_NG002002_C02 | idp_NG002002_C02_R04 | ce916862-2e02-4072-b0e4-7dbab93bea6d | C04 | Interview took 11 minutes
2026-08-19 | enum_B_16 | idp_NG002014_C05 | idp_NG002014_C05_R02 | 8929ee1a-7423-44fd-8fc7-37d2809087fe | C04 | Interview took 12 minutes
2026-08-20 | enum_B_03 | non_idp_NG002002_C12 | non_idp_NG002002_C12_H04 | 726d3b20-5d7d-46b8-8f32-cfda806c74ac | C03 | Household already interviewed in an earlier submission
2026-08-21 | enum_B_21 | non_idp_NG002020_C14 | non_idp_NG002020_C14_H01 | 3630032b-1b58-4004-ae96-3ff617ee5407 | C04 | Interview took 11 minutes
2026-08-21 | enum_B_21 | non_idp_NG002020_C14 | non_idp_NG002020_C14_H02 | 3209d952-20ec-4f10-a258-880b30d4296d | C04 | Interview took 9 minutes
2026-08-22 | enum_B_17 | non_idp_NG002020_C08 | non_idp_NG002020_C08_H05 | 0c1df41c-2cf4-4b4d-8a54-7206d14ee76a | C06 | Cluster had been reported inaccessible
2026-08-22 | enum_B_22 | non_idp_NG002020_C08 | non_idp_NG002020_C08_H01 | 4ae7a60a-a820-4b64-a82c-0eab9ab15f57 | C06 | Cluster had been reported inaccessible
2026-08-23 | enum_B_04 | non_idp_NG002002_C14 | non_idp_NG002002_C14_R01 | 4efd6d36-c9e4-47fb-855e-f7db47d924bd | C01 | Respondent did not consent
2026-08-23 | enum_B_24 | idp_NG002021_C16 | idp_NG002021_C16_H03 | 4307bb9f-5c66-4cf7-8c21-2811f949b144 | C04 | Interview took 6 minutes
2026-08-24 | enum_B_03 | non_idp_NG002002_C15 | non_idp_NG002002_C15_H02 | 127f7a45-fdd6-40cf-b102-208cb96cbd2c | C04 | Interview took 9 minutes
2026-08-24 | enum_B_04 | non_idp_NG002002_C15 | non_idp_NG002002_C15_H05 | 81b026a2-ad2e-49b1-9aa9-b32469145b9a | C03 | Household already interviewed in an earlier submission
2026-08-24 | enum_B_15 | idp_NG002014_C08 | idp_NG002014_C08_H06 | adb5b07e-7aee-4b57-aedc-0a94f70d1d41 | C01 | Respondent did not consent
2026-08-25 | enum_B_13 | idp_NG002008_C12 | idp_NG002008_C12_H03 | 8cb66491-da9f-47d0-bdac-e3ff1dcf6f51 | C04 | Interview took 6 minutes
2026-08-25 | enum_B_22 | idp_NG002021_C01 | idp_NG002021_C01_H03 | eb377fca-a479-4893-b674-420b7decc866 | C03 | Household already interviewed in an earlier submission
2026-08-25 | enum_B_23 | non_idp_NG002021_C02 | non_idp_NG002021_C02_H04 | 203707cf-0541-4020-a69b-823afdb687a1 | C03 | Household already interviewed in an earlier submission
2026-08-26 | enum_B_04 | non_idp_NG002002_C16 | non_idp_NG002002_C16_H06 | 7b7fa7e9-3764-4e4c-864d-106ec03c1ee7 | C04 | Interview took 8 minutes
2026-08-26 | enum_B_22 | idp_NG002021_C02 | idp_NG002021_C02_H05 | 7c64e984-f5b2-48cf-a5be-2b0cc09f2345 | C04 | Interview took 9 minutes
2026-08-27 | enum_B_05 | idp_NG002004_C15 | idp_NG002004_C15_H05 | 3bdc8781-58bc-46cc-8697-8498d3ada4db | C01 | Respondent did not consent
2026-08-27 | enum_B_06 | idp_NG002004_C15 | idp_NG002004_C15_H01 | 3303ff68-fbc2-48d6-a1d5-143b7a156a3a | C04 | Interview took 12 minutes
2026-08-27 | enum_B_19 | non_idp_NG002018_C06 | non_idp_NG002018_C06_H01 | f238e0b9-26f0-4ee6-88e8-b419a8f64be7 | C04 | Interview took 6 minutes
2026-08-27 | enum_B_22 | idp_NG002021_C03 | idp_NG002021_C03_H01 | c5222fd4-a046-41ea-ae41-8f3ef3ef00f8 | C03 | Household already interviewed in an earlier submission
2026-08-28 | enum_B_06 | non_idp_NG002004_C01 | non_idp_NG002004_C01_H05 | ef497baa-df6d-433e-8d3e-5440e946ce3a | C04 | Interview took 12 minutes
2026-08-28 | enum_B_07 | idp_NG002005_C04 | idp_NG002005_C04_H03 | 3611c7e8-62b9-4ce3-95e5-c18abfbf93fb | C04 | Interview took 11 minutes
2026-08-28 | enum_B_07 | idp_NG002005_C04 | idp_NG002005_C04_H06 | fd6603cc-5d9c-483d-8b73-fef10a88b21a | C04 | Interview took 8 minutes
2026-08-28 | enum_B_12 | non_idp_NG002007_C08 | non_idp_NG002007_C08_H02 | 5aa60a56-2f58-4fb9-8af0-ce785ca4552e | C02 | Same submission uploaded more than once
2026-08-28 | enum_B_19 | non_idp_NG002018_C07 | non_idp_NG002018_C07_H03 | cb55e0c9-1aa4-4964-80d8-febc73576989 | C01 | Respondent did not consent
2026-08-28 | enum_B_21 | idp_NG002021_C04 | idp_NG002021_C04_H05 | 3bab2f43-562a-4738-bfa7-9fb46a75d8f8 | C01 | Respondent did not consent
2026-08-29 | enum_B_01 | idp_NG002002_C11 | idp_NG002002_C11_H04 | 06252bbc-9ed3-4e20-b96b-b6553dc65e39 | C01 | Respondent did not consent
2026-08-29 | enum_B_01 | idp_NG002002_C11 | idp_NG002002_C11_R01 | f9167eed-6144-43b6-982b-ad3e17d9a38a | C01 | Respondent did not consent
2026-08-29 | enum_B_06 | non_idp_NG002004_C02 | non_idp_NG002004_C02_H02 | 4b6787ed-7a38-46d6-95de-23aa48ed6da1 | C04 | Interview took 10 minutes
2026-08-29 | enum_B_13 | non_idp_NG002008_C03 | non_idp_NG002008_C03_H01 | 2a90fadc-209e-48fd-88e3-38450f4dd167 | C01 | Respondent did not consent
2026-08-29 | enum_B_14 | non_idp_NG002008_C03 | non_idp_NG002008_C03_R03 | 3a4f7d8a-a221-4453-a3ae-0e15826f4ee4 | C01 | Respondent did not consent
2026-08-30 | enum_B_01 | idp_NG002002_C12 | idp_NG002002_C12_R01 | 0ce08754-baf1-4254-ae02-5b2192ab495b | C01 | Respondent did not consent
2026-08-30 | enum_B_06 | non_idp_NG002004_C03 | non_idp_NG002004_C03_H05 | a5ae991b-d526-4aeb-98ab-e19dc272aa08 | C01 | Respondent did not consent
2026-08-31 | enum_B_14 | non_idp_NG002008_C05 | non_idp_NG002008_C05_H06 | 876e5046-d6b5-487d-a046-13f3b3afdbe1 | C04 | Interview took 11 minutes
2026-08-31 | enum_B_24 | non_idp_NG002021_C06 | non_idp_NG002021_C06_H05 | b4f2c568-e4ef-40b4-9ff8-497106b6d868 | C02 | Same submission uploaded more than once
2026-09-01 | enum_B_01 | idp_NG002002_C14 | idp_NG002002_C14_R04 | 7069f201-bbe4-491d-8c4a-938c70d62ef4 | C01 | Respondent did not consent
2026-09-01 | enum_B_02 | idp_NG002002_C14 | idp_NG002002_C14_H03 | aeb12a01-8a5b-46c6-8173-81b268dd896a | C01 | Respondent did not consent
2026-09-01 | enum_B_16 | non_idp_NG002014_C01 | non_idp_NG002014_C01_H01 | 84683c73-c66e-461e-82cc-1d4bc9fa5783 | C03 | Household already interviewed in an earlier submission
2026-09-02 | enum_B_01 | non_idp_NG002002_C01 | non_idp_NG002002_C01_H06 | 553aa411-01a1-4cc8-a5e9-be3adea40ca7 | C01 | Respondent did not consent
2026-09-02 | enum_B_01 | non_idp_NG002002_C01 | non_idp_NG002002_C01_H05 | f2dcab87-6587-4a13-b7cd-5d54d73901d1 | C03 | Household already interviewed in an earlier submission
2026-09-02 | enum_B_04 | idp_NG002004_C05 | idp_NG002004_C05_H01 | fa0bb81c-56aa-4334-8ac9-b988ece209e5 | C01 | Respondent did not consent
2026-09-02 | enum_B_07 | idp_NG002005_C09 | idp_NG002005_C09_R01 | c4eafb54-c84b-41b2-b8eb-8b46a7ae6c24 | C04 | Interview took 9 minutes
2026-09-02 | enum_B_07 | idp_NG002005_C09 | idp_NG002005_C09_H06 | a61673e8-94ab-471b-917c-1916d56ae70f | C03 | Household already interviewed in an earlier submission
2026-09-02 | enum_B_13 | non_idp_NG002008_C07 | non_idp_NG002008_C07_R02 | 815dcba7-36e3-4a77-a6f2-27204e744ecd | C04 | Interview took 9 minutes
2026-09-02 | enum_B_15 | non_idp_NG002014_C02 | non_idp_NG002014_C02_R01 | 53ac9c55-2fd5-4396-b7ee-1141bd1827da | C01 | Respondent did not consent
2026-09-02 | enum_B_16 | non_idp_NG002014_C02 | non_idp_NG002014_C02_H03 | 5517e0ae-d7d1-4618-b00e-7dfc38dfbc6f | C03 | Household already interviewed in an earlier submission
2026-09-03 | enum_B_05 | non_idp_NG002004_C07 | non_idp_NG002004_C07_R01 | b23d1b8f-b3f6-457f-a1ab-7c1ff8a34d9e | C04 | Interview took 9 minutes
2026-09-03 | enum_B_07 | idp_NG002005_C10 | idp_NG002005_C10_H03 | 38908c32-49e9-4973-8cda-3e189b7086d2 | C04 | Interview took 10 minutes
2026-09-04 | enum_B_03 | idp_NG002004_C06 | idp_NG002004_C06_H05 | 9b0a7188-bd1d-4e82-87c4-fe1811c6a524 | C04 | Interview took 5 minutes
2026-09-04 | enum_B_04 | idp_NG002004_C06 | idp_NG002004_C06_H01 | 493a5d8a-c500-435f-8f27-1e912e22fa58 | C04 | Interview took 11 minutes
2026-09-04 | enum_B_06 | non_idp_NG002004_C93 | non_idp_NG002004_C08_R01 | 76a4f33c-1ad4-40ca-9320-a7e8c67084dd | C05 | Cluster code not in the sample
2026-09-05 | enum_B_21 | idp_NG002021_C08 | idp_NG002021_C08_H04 | d892ab56-9ea1-469a-bad5-94c2337b79e7 | C04 | Interview took 5 minutes
2026-09-05 | enum_B_24 | non_idp_NG002021_C10 | non_idp_NG002021_C10_H02 | dce5017c-6cd2-4460-b641-9dd3120a02a5 | C04 | Interview took 8 minutes
2026-09-06 | enum_B_02 | non_idp_NG002002_C06 | non_idp_NG002002_C06_H03 | cc8ce601-5ca1-4e99-a309-cd7eb06c34cd | C01 | Respondent did not consent
2026-09-06 | enum_B_23 | non_idp_NG002021_C12 | non_idp_NG002021_C12_H01 | 615884ef-e779-4ad6-b251-d2099173536e | C01 | Respondent did not consent
2026-09-06 | enum_B_24 | non_idp_NG002021_C12 | non_idp_NG002021_C12_H02 | b7fb8087-1fde-4a23-afc9-7394e67b2ec5 | C01 | Respondent did not consent
2026-09-07 | enum_B_01 | non_idp_NG002002_C08 | non_idp_NG002002_C08_H03 | b7e4db2b-01bb-438a-989c-698cffd5d212 | C04 | Interview took 6 minutes
2026-09-07 | enum_B_21 | idp_NG002021_C10 | idp_NG002021_C10_H01 | ee7f413b-dbb4-42a4-a8e4-f4c8b88e4386 | C02 | Same submission uploaded more than once
2026-09-07 | enum_B_22 | idp_NG002021_C10 | idp_NG002021_C10_H03 | ef9519da-162c-4264-8717-6c5be0bbcb72 | C04 | Interview took 10 minutes
2026-09-08 | enum_B_18 | idp_NG002018_C05 | idp_NG002018_C05_H06 | a1739dfd-79a9-4f7c-aa7b-1b47bcfd7c6b | C03 | Household already interviewed in an earlier submission
2026-09-08 | enum_B_19 | non_idp_NG002018_C16 | non_idp_NG002018_C16_H02 | 9bc8efdd-ee73-4345-b86e-37406716510a | C01 | Respondent did not consent
2026-09-08 | enum_B_19 | non_idp_NG002018_C16 | non_idp_NG002018_C16_H06 | 99471244-cff7-43a2-b094-558ba9beeaef | C04 | Interview took 4 minutes
2026-09-08 | enum_B_22 | idp_NG002021_C11 | idp_NG002021_C11_H01 | 23427564-eea5-426a-9dcd-abb2c44344d2 | C03 | Household already interviewed in an earlier submission
2026-09-09 | enum_B_12 | non_idp_NG002007_C16 | non_idp_NG002007_C16_H06 | 35d9163a-b37d-4be0-af3d-de2cdfa9f57b | C01 | Respondent did not consent
2026-09-09 | enum_B_16 | non_idp_NG002014_C08 | non_idp_NG002014_C08_H02 | adba9dae-8892-4325-99ff-7cd8c282feef | C04 | Interview took 10 minutes
2026-09-09 | enum_B_24 | non_idp_NG002021_C15 | non_idp_NG002021_C15_H04 | d6ded626-acaa-420c-b352-709a253b75c3 | C01 | Respondent did not consent
2026-09-10 | enum_B_07 | non_idp_NG002005_C03 | non_idp_NG002005_C03_H01 | b2f0bc7f-e44f-41bb-b5cc-2b4d7c03d64b | C02 | Same submission uploaded more than once
2026-09-10 | enum_B_10 | non_idp_NG002020_C08 | non_idp_NG002020_C08_H06 | de628b38-aa9d-43f7-8034-56d68823ff62 | C06 | Cluster had been reported inaccessible
2026-09-10 | enum_B_20 | idp_NG002020_C01 | idp_NG002020_C01_H04 | dacc06be-31ac-4ab9-86c9-3e724391a527 | C04 | Interview took 11 minutes
2026-09-11 | enum_B_03 | idp_NG002004_C10 | idp_NG002004_C10_H05 | 2f8603d3-0e77-4c5c-9411-9593b0a4c51f | C01 | Respondent did not consent
2026-09-11 | enum_B_09 | idp_NG002007_C13 | idp_NG002007_C13_H02 | 3d776333-9529-4ba9-9fed-6c84503b7f96 | C03 | Household already interviewed in an earlier submission
2026-09-11 | enum_B_10 | idp_NG002007_C13 | idp_NG002007_C13_H06 | 99aef1a2-ab53-4f84-8946-879e789df674 | C01 | Respondent did not consent
2026-09-11 | enum_B_19 | idp_NG002020_C02 | idp_NG002020_C02_H02 | ab93c232-a162-4273-b615-9bcbe1ddc571 | C04 | Interview took 8 minutes
2026-09-11 | enum_B_21 | non_idp_NG002020_R1_04 | non_idp_NG002020_R1_04_H05 | d40af8ca-9e35-461f-a127-3c0e13dfd520 | C04 | Interview took 10 minutes
2026-09-12 | enum_B_03 | idp_NG002004_C11 | idp_NG002004_C11_H06 | f37edb8e-ebbb-4745-a994-a2a1099f896c | C01 | Respondent did not consent
2026-09-12 | enum_B_04 | idp_NG002004_C11 | idp_NG002004_C11_H04 | 6551eff9-6959-4a7d-a7f0-5080accaeb23 | C01 | Respondent did not consent
2026-09-13 | enum_B_09 | idp_NG002007_C14 | idp_NG002007_C14_H05 | ee09c107-5dc3-465b-99a6-20bff939566b | C01 | Respondent did not consent
2026-09-13 | enum_B_19 | idp_NG002020_C03 | idp_NG002020_C03_H03 | 2533065f-ce79-4300-8d00-dd7e6183f576 | C01 | Respondent did not consent
2026-09-13 | enum_B_21 | non_idp_NG002020_R1_05 | non_idp_NG002020_R1_05_R01 | e436f846-9e28-4e47-a867-1e172898c01a | C04 | Interview took 7 minutes
2026-09-14 | enum_B_10 | non_idp_NG002020_C08 | non_idp_NG002020_C08_H03 | f16ab17d-7aa0-40ed-9df6-52d44f17db05 | C06 | Cluster had been reported inaccessible
2026-09-14 | enum_B_10 | non_idp_NG002020_C08 | non_idp_NG002020_C08_H02 | c8b90575-d3bd-4c69-b9b7-85c49b49c5e8 | C06 | Cluster had been reported inaccessible
2026-09-14 | enum_B_11 | idp_NG002008_C01 | idp_NG002008_C01_H05 | 974da115-1776-4d9d-b3ad-43f8c9cd7e3b | C01 | Respondent did not consent
2026-09-14 | enum_B_17 | idp_NG002018_C10 | idp_NG002018_C10_H02 | 36a3a241-71a9-4402-a354-b951d2c56d56 | C01 | Respondent did not consent
2026-09-15 | enum_B_03 | idp_NG002004_C13 | idp_NG002004_C13_H05 | e33f7df1-be10-4acd-b4bb-b8857355b6fd | C04 | Interview took 7 minutes
2026-09-15 | enum_B_07 | non_idp_NG002005_C12 | non_idp_NG002005_C12_R01 | 8a212c9d-f575-45e2-b2e3-4a347ce9e6de | C03 | Household already interviewed in an earlier submission
2026-09-15 | enum_B_20 | idp_NG002020_C05 | idp_NG002020_C05_H01 | bdb8eed0-8753-425b-80dc-4dfe100508c6 | C04 | Interview took 8 minutes
2026-09-16 | enum_B_09 | non_idp_NG002005_R1_01 | non_idp_NG002005_R1_01_H05 | 4373d9f5-2fb1-4b21-afd8-3647bd09ca61 | C04 | Interview took 11 minutes
2026-09-16 | enum_B_17 | non_idp_NG002018_C92 | non_idp_NG002018_C02_H03 | 22d2f682-714f-4b2c-8f59-f0aec42254aa | C05 | Cluster code not in the sample
2026-09-16 | enum_B_18 | non_idp_NG002018_C02 | non_idp_NG002018_C02_H02 | 942bd36c-da50-4754-bcc1-385702bd1bc3 | C04 | Interview took 8 minutes
2026-09-17 | enum_B_08 | non_idp_NG002005_C14 | non_idp_NG002005_C14_H04 | fed932e5-1446-4b32-872c-f83a61129ee3 | C04 | Interview took 11 minutes
2026-09-18 | enum_B_03 | non_idp_NG002002_R2_02 | non_idp_NG002002_R2_02_H04 | 9980f07c-3ff7-4715-9709-2f498642620c | C04 | Interview took 5 minutes
2026-09-18 | enum_B_04 | non_idp_NG002002_R2_02 | non_idp_NG002002_R2_02_H05 | b1abfa49-bde1-42d9-9fd1-95a3e35f5fb8 | C01 | Respondent did not consent
2026-09-18 | enum_B_13 | idp_NG002014_C01 | idp_NG002014_C01_H04 | 34f0957a-45e2-4129-a8cf-a7243736a724 | C01 | Respondent did not consent
2026-09-18 | enum_B_20 | idp_NG002020_C08 | idp_NG002020_C08_H03 | b14d6db3-098f-4ca8-8184-1998f7f68bef | C04 | Interview took 6 minutes
2026-09-18 | enum_B_20 | idp_NG002020_C08 | idp_NG002020_C08_R01 | 974814f2-7f8e-4635-be23-5be2d512d1d5 | C04 | Interview took 10 minutes
2026-09-19 | enum_B_06 | non_idp_NG002004_R1_03 | non_idp_NG002004_R1_03_H03 | 9c0599fe-aed7-4126-89bd-40545f0aec80 | C04 | Interview took 9 minutes
2026-09-19 | enum_B_11 | idp_NG002008_C05 | idp_NG002008_C05_H01 | e1eb1a1b-a986-4dc7-a393-7f7bca849e81 | C04 | Interview took 5 minutes
2026-09-19 | enum_B_12 | idp_NG002008_C05 | idp_NG002008_C05_H03 | 6933dac3-e3ee-4068-b2cc-ec772441ce99 | C02 | Same submission uploaded more than once
2026-09-20 | enum_B_13 | non_idp_NG002008_R1_01 | non_idp_NG002008_R1_01_H06 | 33686ab9-7dd1-4b20-81d4-2d7347f6e61e | C01 | Respondent did not consent

## Enumerators
Enumerators
Synthetic data – not real findings
enumerator_id | interviews | median minutes | % repeated answers | interviews removed | interviews flagged | pattern
enum_B_01 | 66 | 43.1 | 0 | 8 | 6
enum_B_02 | 67 | 42.5 | 0 | 3 | 4
enum_B_03 | 63 | 45.5 | 0 | 7 | 5
enum_B_04 | 71 | 44.2 | 0 | 7 | 5
enum_B_05 | 62 | 42 | 0 | 2 | 7
enum_B_06 | 70 | 41.7 | 0 | 6 | 2
enum_B_07 | 72 | 41.9 | 2.8 | 7 | 5
enum_B_08 | 57 | 42.5 | 0 | 1 | 2
enum_B_09 | 72 | 41 | 0 | 3 | 10
enum_B_10 | 64 | 40.2 | 0 | 4 | 3
enum_B_11 | 67 | 46.5 | 0 | 3 | 3
enum_B_12 | 68 | 43.9 | 5.9 | 3 | 5
enum_B_13 | 70 | 41.2 | 0 | 5 | 7
enum_B_14 | 62 | 44.5 | 0 | 2 | 5
enum_B_15 | 69 | 42.5 | 0 | 2 | 3
enum_B_16 | 58 | 44.8 | 0 | 5 | 0
enum_B_17 | 74 | 42.1 | 0 | 3 | 3
enum_B_18 | 59 | 43.8 | 0 | 2 | 4
enum_B_19 | 70 | 42.8 | 0 | 6 | 3
enum_B_20 | 62 | 44.6 | 0 | 4 | 3
enum_B_21 | 75 | 41.4 | 2.7 | 7 | 3
enum_B_22 | 62 | 39.1 | 0 | 8 | 6
enum_B_23 | 65 | 41 | 0 | 2 | 1
enum_B_24 | 63 | 40.2 | 3.2 | 5 | 5

## Progress
Progress against target by LGA
Synthetic data – not real findings
adm1_name | adm2_name | pop_type | target | achieved | percent
Adamawa | Fufore | idp | 84 | 83 | 98.8
Adamawa | Fufore | non_idp | 102 | 98 | 96.1
Adamawa | Girei | idp | 84 | 80 | 95.2
Adamawa | Girei | non_idp | 102 | 100 | 98
Adamawa | Gombi | idp | 90 | 86 | 95.6
Adamawa | Gombi | non_idp | 102 | 97 | 95.1
Adamawa | Hong | idp | 90 | 78 | 86.7
Adamawa | Hong | non_idp | 102 | 102 | 100
Adamawa | Jada | idp | 72 | 70 | 97.2
Adamawa | Jada | non_idp | 102 | 94 | 92.2
Adamawa | Mubi North | idp | 90 | 82 | 91.1
Adamawa | Mubi North | non_idp | 102 | 95 | 93.1
Adamawa | Song | idp | 60 | 59 | 98.3
Adamawa | Song | non_idp | 102 | 92 | 90.2
Adamawa | Yola North | idp | 66 | 60 | 90.9
Adamawa | Yola North | non_idp | 72 | 62 | 86.1
Adamawa | Yola South | idp | 96 | 86 | 89.6
Adamawa | Yola South | non_idp | 102 | 95 | 93.1