## Summary
Data-quality digest: Partner D
Synthetic data – not real findings
Item | Value
Partner | Partner D
States | Benue
Data as of | 2026-09-27
Submissions received | 2019
Interviews kept | 1860
Interviews removed | 159
Values corrected | 26
Interviews flagged for follow-up | 114
Households targeted | 1824
Households achieved | 1860
Progress against target | 102.0%

## Follow up
Interviews flagged: please check with the enumerator
Synthetic data – not real findings
date | enumerator_id | cluster_id | household_id | _uuid | check | issue | value
2026-08-21 | enum_D_27 | idp_NG007023_C12 | idp_NG007023_C12_H05 | d9c07a37-1a9a-4bb6-aa03-2b760d66d33d | fcs_hhs_contradiction | Acceptable food consumption with severe hunger | FCS 36.5, HHS 5
2026-08-23 | enum_D_05 | non_idp_NG007005_C04 | non_idp_NG007005_C04_H02 | 4f141179-015c-44ce-95e2-f570eefc47b2 | gps_far | GPS point 3.1 km from the household | 3057
2026-08-23 | enum_D_07 | idp_NG007007_C07 | idp_NG007007_C07_H06 | 06c93400-0435-4ce1-ae02-811692225425 | fcs_hhs_contradiction | Acceptable food consumption with severe hunger | FCS 93.5, HHS 6
2026-08-23 | enum_D_11 | non_idp_NG007009_C08 | non_idp_NG007009_C08_H04 | b1f23553-ea1f-4ebc-ada9-221a0f2c9a3b | fcs_hhs_contradiction | Acceptable food consumption with severe hunger | FCS 44.5, HHS 4
2026-08-24 | enum_D_04 | non_idp_NG007004_C16 | non_idp_NG007004_C16_R01 | 2e962125-552c-4371-8a4c-86e08cbb5a6e | attending_exceed_school_age | More children attending school than of school age | 3
2026-08-24 | enum_D_11 | non_idp_NG007009_C09 | non_idp_NG007009_C09_R01 | 63fd4098-89d9-4656-8e0e-be4ef207229f | gps_far | GPS point 4.8 km from the household | 4814
2026-08-24 | enum_D_23 | idp_NG007022_C02 | idp_NG007022_C02_H04 | 54a73c5f-d6e7-4a0c-b007-230e2448e704 | gps_far | GPS point 4.7 km from the household | 4698
2026-08-24 | enum_D_24 | idp_NG007022_C02 | idp_NG007022_C02_H01 | 974c35d5-6625-462b-b54e-56a4d7bbdf50 | gps_far | GPS point 2.8 km from the household | 2844
2026-08-24 | enum_D_27 | idp_NG007023_C15 | idp_NG007023_C15_H01 | f5e7a69a-bbe9-4868-ad79-6510d6a56217 | gps_far | GPS point 3.6 km from the household | 3582
2026-08-25 | enum_D_03 | non_idp_NG007004_C17 | non_idp_NG007004_C17_H01 | 3e59bc97-bc3a-49f1-826c-adef196da198 | gps_far | GPS point 3.1 km from the household | 3073
2026-08-25 | enum_D_05 | non_idp_NG007005_C07 | non_idp_NG007005_C07_H04 | bccd4e8e-67cf-4df8-90fd-1b29e3d58b70 | fcs_hhs_contradiction | Acceptable food consumption with severe hunger | FCS 93.5, HHS 6
2026-08-25 | enum_D_08 | idp_NG007007_C08 | idp_NG007007_C08_H06 | 552d19ba-e112-402e-a302-c046bfc94228 | fcs_flat | Every food group given the same number of days | 0
2026-08-25 | enum_D_14 | non_idp_NG007010_C17 | non_idp_NG007010_C17_H01 | 4c312d24-d71c-4c5a-a6f4-51869f35e31b | children_exceed_hh | More children than household members | 0 + 6 children, household of 3
2026-08-25 | enum_D_15 | non_idp_NG007011_C12 | non_idp_NG007011_C12_H01 | 39bd7822-fbb3-49e6-a71b-dca0516b0656 | attending_exceed_school_age | More children attending school than of school age | 3
2026-08-25 | enum_D_26 | non_idp_NG007022_C16 | non_idp_NG007022_C16_H05 | a193d979-eef4-46c2-9097-e8bd8a91a12c | gps_far | GPS point 2.7 km from the household | 2680
2026-08-25 | enum_D_28 | non_idp_NG007023_C01 | non_idp_NG007023_C01_H04 | 3547427b-6ad6-4130-af3f-5344af6a0167 | gps_far | GPS point 4.8 km from the household | 4809
2026-08-26 | enum_D_05 | non_idp_NG007005_C08 | non_idp_NG007005_C08_H01 | 096b7668-cd28-487b-8596-f23d3819a5c0 | gps_far | GPS point 3.8 km from the household | 3821
2026-08-27 | enum_D_05 | non_idp_NG007005_C10 | non_idp_NG007005_C10_H01 | 6f8a9ee9-89fb-4134-b766-f33b6f2a1f11 | gps_far | GPS point 5.0 km from the household | 5002
2026-08-27 | enum_D_14 | idp_NG007011_C02 | idp_NG007011_C02_H02 | fbe119fd-feb8-49b9-aa85-7e22ef0d1db0 | fcs_flat | Every food group given the same number of days | 0
2026-08-28 | enum_D_17 | non_idp_NG007012_C17 | non_idp_NG007012_C17_R01 | 43589858-968c-4c13-8bba-d54396fc1e44 | gps_far | GPS point 2.9 km from the household | 2889
2026-08-28 | enum_D_18 | idp_NG007020_C01 | idp_NG007020_C01_H03 | dacd21ac-983e-46d5-b237-9f063cdeb0b7 | fcs_hhs_contradiction | Acceptable food consumption with severe hunger | FCS 93.5, HHS 6
2026-08-28 | enum_D_22 | idp_NG007021_C11 | idp_NG007021_C11_H05 | 97d16fbc-9709-4233-b8c0-ab1be538ef49 | fcs_hhs_contradiction | Acceptable food consumption with severe hunger | FCS 44.0, HHS 4
2026-08-29 | enum_D_10 | non_idp_NG007009_C02 | non_idp_NG007009_C02_H02 | cb767cbc-3e8a-4aef-94bf-f0826b64fe58 | gps_far | GPS point 4.7 km from the household | 4715
2026-08-29 | enum_D_16 | non_idp_NG007011_C16 | non_idp_NG007011_C16_H01 | b5d1af77-d297-4ed8-912a-f605de4787ea | gps_far | GPS point 3.7 km from the household | 3728
2026-08-29 | enum_D_19 | non_idp_NG007020_C09 | non_idp_NG007020_C09_H05 | abc5c75c-d56c-431b-a58b-dbf497c608a5 | gps_far | GPS point 1.3 km from the household | 1332
2026-08-29 | enum_D_19 | non_idp_NG007020_C09 | non_idp_NG007020_C09_R01 | c5136bb8-0332-4603-8ba5-b250c6b16aa0 | fcs_flat | Every food group given the same number of days | 0
2026-08-29 | enum_D_27 | non_idp_NG007023_C05 | non_idp_NG007023_C05_R01 | b2cf4882-a042-4d36-aa67-dcc3b5d5ae88 | fcs_hhs_contradiction | Acceptable food consumption with severe hunger | FCS 43.0, HHS 4
2026-08-30 | enum_D_13 | idp_NG007011_C05 | idp_NG007011_C05_H03 | 8633431f-e1ba-43f1-a24c-5efd0bcd569b | fcs_flat | Every food group given the same number of days | 0
2026-08-31 | enum_D_01 | idp_NG007004_C10 | idp_NG007004_C10_H01 | 9c481825-a5a7-4c5f-b831-7b429922cb36 | gps_far | GPS point 3.6 km from the household | 3644
2026-08-31 | enum_D_04 | idp_NG007005_C04 | idp_NG007005_C04_H01 | 7a878c57-0f1e-4af6-9a17-b0160d80428e | fcs_hhs_contradiction | Acceptable food consumption with severe hunger | FCS 42.0, HHS 4
2026-09-01 | enum_D_06 | non_idp_NG007005_C16 | non_idp_NG007005_C16_H03 | acce7517-a5a8-4a73-bc86-e87f8c1575f5 | attending_exceed_school_age | More children attending school than of school age | 8
2026-09-01 | enum_D_08 | idp_NG007007_C12 | idp_NG007007_C12_H03 | 742a28b0-0f39-4540-9748-cdbb2d782a5a | gps_far | GPS point 2.8 km from the household | 2769
2026-09-01 | enum_D_12 | non_idp_NG007009_C17 | non_idp_NG007009_C17_H01 | d19cd1d9-d83e-4192-8d8e-677876efa1d2 | gps_far | GPS point 1.2 km from the household | 1231
2026-09-01 | enum_D_20 | non_idp_NG007020_C11 | non_idp_NG007020_C11_H05 | 59993b23-f836-4892-9db6-f309d7df9c98 | fcs_hhs_contradiction | Acceptable food consumption with severe hunger | FCS 38.0, HHS 4
2026-09-02 | enum_D_05 | idp_NG007007_C01 | idp_NG007007_C01_H04 | 6a71bed4-7846-414c-9043-c8f6d640b437 | gps_far | GPS point 3.2 km from the household | 3216
2026-09-02 | enum_D_10 | non_idp_NG007009_C06 | non_idp_NG007009_C06_H05 | 8fcb5157-b42b-4529-854e-326d00ed0e68 | gps_far | GPS point 4.3 km from the household | 4277
2026-09-02 | enum_D_13 | idp_NG007011_C06 | idp_NG007011_C06_H05 | 668b873b-f3b6-4c90-8a3f-51f1e38dc960 | fcs_hhs_contradiction | Acceptable food consumption with severe hunger | FCS 35.5, HHS 4
2026-09-02 | enum_D_21 | idp_NG007021_C14 | idp_NG007021_C14_H06 | be52c22d-6165-43e8-924c-6269081325cb | fcs_hhs_contradiction | Acceptable food consumption with severe hunger | FCS 66.0, HHS 4
2026-09-02 | enum_D_22 | idp_NG007021_C14 | idp_NG007021_C14_H02 | 6135bf8f-1a68-4875-8f67-12032c38dda2 | gps_far | GPS point 4.2 km from the household | 4248
2026-09-03 | enum_D_07 | non_idp_NG007007_C02 | non_idp_NG007007_C02_H04 | 2a034c8d-6bdb-4b83-94d1-250852f315c7 | gps_far | GPS point 1.3 km from the household | 1277
2026-09-03 | enum_D_08 | non_idp_NG007007_C02 | non_idp_NG007007_C02_R01 | 1e94fdf8-e560-4725-b4bf-3efab1b3d3e8 | fcs_hhs_contradiction | Acceptable food consumption with severe hunger | FCS 45.5, HHS 5
2026-09-03 | enum_D_09 | idp_NG007009_R1_01 | idp_NG007009_R1_01_R02 | 4c3ed7cc-43df-425d-a0e4-39cbe7055e73 | gps_far | GPS point 1.5 km from the household | 1528
2026-09-03 | enum_D_13 | non_idp_NG007011_C01 | non_idp_NG007011_C01_H06 | 8d494482-b0d3-4c81-8c1f-c2e1e64577eb | gps_far | GPS point 4.2 km from the household | 4202
2026-09-03 | enum_D_19 | non_idp_NG007020_C13 | non_idp_NG007020_C13_H05 | 9c9926da-cb25-408c-8dd9-9ad97859e98d | fcs_hhs_contradiction | Acceptable food consumption with severe hunger | FCS 93.5, HHS 6
2026-09-03 | enum_D_23 | idp_NG007022_C08 | idp_NG007022_C08_H05 | 46240ac9-acb8-4a68-91c7-7d18ee8afda0 | fcs_hhs_contradiction | Acceptable food consumption with severe hunger | FCS 41.0, HHS 4
2026-09-04 | enum_D_01 | idp_NG007004_C15 | idp_NG007004_C15_H03 | e42f9ead-357d-4ca7-96ed-b66cf10aeee6 | gps_far | GPS point 3.5 km from the household | 3479
2026-09-04 | enum_D_05 | idp_NG007007_C03 | idp_NG007007_C03_H06 | e7f32c99-9565-4c77-94be-15faa1ec649f | gps_far | GPS point 1.2 km from the household | 1233
2026-09-04 | enum_D_08 | non_idp_NG007007_C03 | non_idp_NG007007_C03_H05 | 293d7c09-5e5b-488f-affb-0436b7b95402 | fcs_flat | Every food group given the same number of days | 0
2026-09-04 | enum_D_15 | non_idp_NG007012_C05 | non_idp_NG007012_C05_H04 | 77c3655b-819c-48ae-893d-34ce1129f603 | fcs_hhs_contradiction | Acceptable food consumption with severe hunger | FCS 93.5, HHS 6
2026-09-04 | enum_D_25 | idp_NG007023_C08 | idp_NG007023_C08_H01 | 20d61ec5-c0aa-43e4-a0ca-8cece050c092 | gps_far | GPS point 2.0 km from the household | 1990
2026-09-05 | enum_D_01 | non_idp_NG007004_C01 | non_idp_NG007004_C01_H01 | 16d4441a-453c-43a8-9de5-ee1e7129f079 | gps_far | GPS point 1.1 km from the household | 1050
2026-09-05 | enum_D_12 | non_idp_NG007010_C09 | non_idp_NG007010_C09_H05 | ea609446-8139-4fd1-9225-b4a3342c5de4 | children_exceed_hh | More children than household members | 0 + 10 children, household of 8
2026-09-05 | enum_D_21 | non_idp_NG007021_C02 | non_idp_NG007021_C02_H01 | b8539270-f1d5-4550-9fee-7313d3314b2f | children_exceed_hh | More children than household members | 2 + 10 children, household of 10
2026-09-05 | enum_D_28 | non_idp_NG007023_C08 | non_idp_NG007023_C08_H01 | edc0028c-9254-4f58-bddf-e8b2e30246a6 | gps_far | GPS point 0.7 km from the household | 721
2026-09-06 | enum_D_02 | non_idp_NG007004_C04 | non_idp_NG007004_C04_H02 | 772c3c8d-5b99-430d-bf52-ee3610e3b7fa | gps_far | GPS point 3.2 km from the household | 3213
2026-09-06 | enum_D_11 | non_idp_NG007010_C10 | non_idp_NG007010_C10_H02 | 957faa0c-5de8-4046-b66b-b587c298804e | fcs_hhs_contradiction | Acceptable food consumption with severe hunger | FCS 93.5, HHS 6
2026-09-06 | enum_D_12 | non_idp_NG007010_C10 | non_idp_NG007010_C10_H06 | 085c984e-993f-4a86-9b77-08ce826e7cf9 | children_exceed_hh | More children than household members | 2 + 7 children, household of 7
2026-09-07 | enum_D_04 | idp_NG007005_C10 | idp_NG007005_C10_H04 | 98098b8c-346b-4ab9-92a2-08f7b431d9b9 | gps_far | GPS point 3.1 km from the household | 3070
2026-09-07 | enum_D_06 | idp_NG007007_C06 | idp_NG007007_C06_H03 | a9ff9467-c5e1-460e-9d3a-7db59da4fe0a | children_exceed_hh | More children than household members | 2 + 5 children, household of 4
2026-09-07 | enum_D_23 | idp_NG007022_C12 | idp_NG007022_C12_R01 | b62dd6d6-9189-4401-b693-0cd3e015e878 | fcs_hhs_contradiction | Acceptable food consumption with severe hunger | FCS 93.5, HHS 6
2026-09-08 | enum_D_05 | non_idp_NG007005_R1_01 | non_idp_NG007005_R1_01_H04 | 58b0933f-1dac-4e51-94d2-5cce5493ceda | gps_far | GPS point 1.3 km from the household | 1316
2026-09-08 | enum_D_07 | non_idp_NG007007_C08 | non_idp_NG007007_C08_H02 | f66e15fd-d820-443a-8411-8b7a7ce5c186 | fcs_flat | Every food group given the same number of days | 7
2026-09-08 | enum_D_08 | non_idp_NG007007_C08 | non_idp_NG007007_C08_H01 | d62244fb-2dc4-4e72-8165-1d30bf927539 | fcs_flat | Every food group given the same number of days | 0
2026-09-08 | enum_D_09 | idp_NG007009_R1_05 | idp_NG007009_R1_05_H05 | b6538e47-79be-4dca-a847-e644aeb11230 | fcs_flat | Every food group given the same number of days | 0
2026-09-09 | enum_D_02 | non_idp_NG007004_C08 | non_idp_NG007004_C08_H02 | 2e016cdd-301e-47c6-a74a-32407bb0b508 | fcs_hhs_contradiction | Acceptable food consumption with severe hunger | FCS 93.5, HHS 6
2026-09-09 | enum_D_05 | non_idp_NG007005_R1_02 | non_idp_NG007005_R1_02_H01 | 60f3ee9d-9026-4e60-8d22-191a67e11028 | children_exceed_hh | More children than household members | 0 + 9 children, household of 6
2026-09-09 | enum_D_15 | non_idp_NG007012_C09 | non_idp_NG007012_C09_H06 | f5dc5682-f48f-445b-9930-b449c81ebb34 | fcs_hhs_contradiction | Acceptable food consumption with severe hunger | FCS 40.5, HHS 5
2026-09-09 | enum_D_15 | non_idp_NG007012_C09 | non_idp_NG007012_C09_R01 | 324a4760-e787-4ba5-9b7a-72dd52bed470 | fcs_hhs_contradiction | Acceptable food consumption with severe hunger | FCS 93.5, HHS 6
2026-09-09 | enum_D_20 | non_idp_NG007020_C17 | non_idp_NG007020_C17_H05 | 085b88b2-123f-4b71-95b8-c5532673d95c | gps_far | GPS point 4.4 km from the household | 4421
2026-09-09 | enum_D_23 | idp_NG007022_C14 | idp_NG007022_C14_H03 | ee0542b3-c4cd-43ed-9264-dd6324120f96 | gps_far | GPS point 4.3 km from the household | 4342
2026-09-10 | enum_D_17 | idp_NG007020_C11 | idp_NG007020_C11_H01 | e4febfd0-f9b6-4e94-8ef5-a72ab9cbb049 | attending_exceed_school_age | More children attending school than of school age | 4
2026-09-10 | enum_D_17 | idp_NG007020_C11 | idp_NG007020_C11_H02 | 9bbd0073-dc3f-4a0b-8ead-7ef33fa2ca16 | fcs_hhs_contradiction | Acceptable food consumption with severe hunger | FCS 37.0, HHS 4
2026-09-10 | enum_D_17 | idp_NG007020_C11 | idp_NG007020_C11_R02 | 77146038-e7d8-4d4d-a170-9e029f78c262 | fcs_hhs_contradiction | Acceptable food consumption with severe hunger | FCS 93.5, HHS 6
2026-09-10 | enum_D_19 | idp_NG007021_C01 | idp_NG007021_C01_H05 | 2d633b07-2197-4f92-a068-8590073f878e | fcs_hhs_contradiction | Acceptable food consumption with severe hunger | FCS 48.0, HHS 5
2026-09-10 | enum_D_24 | idp_NG007022_C15 | idp_NG007022_C15_H03 | 3071fcac-dbdc-419e-9e9a-1ee304595cf7 | attending_exceed_school_age | More children attending school than of school age | 4
2026-09-11 | enum_D_11 | non_idp_NG007010_C15 | non_idp_NG007010_C15_H02 | 8ab7b8d3-b8fd-4c1d-9717-1e7bdefcc526 | gps_far | GPS point 3.3 km from the household | 3272
2026-09-11 | enum_D_19 | idp_NG007021_C02 | idp_NG007021_C02_H03 | 87e78671-cc7e-4158-a824-18ed5417881a | fcs_hhs_contradiction | Acceptable food consumption with severe hunger | FCS 93.5, HHS 6
2026-09-11 | enum_D_19 | idp_NG007021_C02 | idp_NG007021_C02_H05 | e9dfcd47-4ea4-4348-8f46-8098d739cefc | fcs_hhs_contradiction | Acceptable food consumption with severe hunger | FCS 42.5, HHS 4
2026-09-12 | enum_D_05 | non_idp_NG007005_R2_01 | non_idp_NG007005_R2_01_H03 | 6bf3351a-62f5-40fd-a71b-e5c55621cbc4 | gps_far | GPS point 4.0 km from the household | 4008
2026-09-12 | enum_D_08 | non_idp_NG007007_C10 | non_idp_NG007007_C10_H01 | 63fa5968-8456-44e4-92ef-9947bb461fa1 | gps_far | GPS point 2.4 km from the household | 2439
2026-09-12 | enum_D_10 | idp_NG007009_R1_07 | idp_NG007009_R1_07_H03 | b573561b-725d-4e3d-8ed5-c6d802f9fcf9 | gps_far | GPS point 3.7 km from the household | 3747
2026-09-12 | enum_D_13 | non_idp_NG007011_C07 | non_idp_NG007011_C07_H01 | 06e538f7-e461-44d2-a649-f5612856fad0 | fcs_flat | Every food group given the same number of days | 0
2026-09-13 | enum_D_20 | idp_NG007021_C03 | idp_NG007021_C03_H03 | 23101f2d-92ff-4ef6-a321-25031334ddc4 | fcs_hhs_contradiction | Acceptable food consumption with severe hunger | FCS 39.5, HHS 5
2026-09-13 | enum_D_22 | non_idp_NG007021_C09 | non_idp_NG007021_C09_H04 | c39cc5ed-1bd6-4bef-aa79-c5225565c365 | fcs_hhs_contradiction | Acceptable food consumption with severe hunger | FCS 93.5, HHS 6
2026-09-13 | enum_D_22 | non_idp_NG007021_C09 | non_idp_NG007021_C09_H06 | cf2a4e80-49c0-4acf-b47d-abf4329ecdf9 | fcs_hhs_contradiction | Acceptable food consumption with severe hunger | FCS 42.0, HHS 5
2026-09-14 | enum_D_09 | idp_NG007009_R1_08 | idp_NG007009_R1_08_H01 | d9f73803-274a-4efb-ad63-5622ceb72242 | fcs_hhs_contradiction | Acceptable food consumption with severe hunger | FCS 47.0, HHS 4
2026-09-14 | enum_D_23 | non_idp_NG007022_C01 | non_idp_NG007022_C01_H05 | 3728f5d1-ac6b-42fd-940b-ec4931c4ba6b | attending_exceed_school_age | More children attending school than of school age | 3
2026-09-14 | enum_D_28 | non_idp_NG007023_C11 | non_idp_NG007023_C11_H01 | 7b443ab1-01c9-450e-a0e3-f85c3cbfbe4d | gps_far | GPS point 0.7 km from the household | 679
2026-09-15 | enum_D_09 | idp_NG007009_R1_09 | idp_NG007009_R1_09_H04 | 053e9495-4e17-46ac-ad8d-0f99e0c5d649 | fcs_hhs_contradiction | Acceptable food consumption with severe hunger | FCS 43.5, HHS 4
2026-09-15 | enum_D_09 | idp_NG007009_R1_09 | idp_NG007009_R1_09_H06 | 3beb916f-dd0d-43fa-9543-2a6031d081d2 | fcs_hhs_contradiction | Acceptable food consumption with severe hunger | FCS 93.5, HHS 6
2026-09-15 | enum_D_20 | idp_NG007021_C05 | idp_NG007021_C05_H03 | de6a1219-2ca4-4aea-a059-1c84c041885b | fcs_flat | Every food group given the same number of days | 7
2026-09-16 | enum_D_03 | idp_NG007005_C15 | idp_NG007005_C15_H02 | 4b4160bb-61f9-4c72-9011-3ccd8d50c333 | fcs_hhs_contradiction | Acceptable food consumption with severe hunger | FCS 93.5, HHS 6
2026-09-16 | enum_D_13 | non_idp_NG007010_R1_02 | non_idp_NG007010_R1_02_H03 | 877a0fe8-b6b3-4934-815d-00969b69dc59 | fcs_hhs_contradiction | Acceptable food consumption with severe hunger | FCS 93.5, HHS 6
2026-09-16 | enum_D_18 | idp_NG007020_C14 | idp_NG007020_C14_H02 | b960e88b-823a-4031-8b85-5043c42e6d77 | fcs_hhs_contradiction | Acceptable food consumption with severe hunger | FCS 44.5, HHS 4
2026-09-16 | enum_D_27 | non_idp_NG007023_C13 | non_idp_NG007023_C13_H04 | 00964cf9-7bd3-4c78-aaf4-82d9ee83de55 | gps_far | GPS point 3.8 km from the household | 3843
2026-09-17 | enum_D_02 | non_idp_NG007004_C15 | non_idp_NG007004_C15_H02 | f34c1161-8eb9-4253-88bc-e7b7a6ba6249 | gps_far | GPS point 2.1 km from the household | 2117
2026-09-17 | enum_D_03 | idp_NG007005_C16 | idp_NG007005_C16_H06 | 0dc500da-ef95-423e-a480-90c385e0f77f | fcs_hhs_contradiction | Acceptable food consumption with severe hunger | FCS 93.5, HHS 6
2026-09-17 | enum_D_13 | non_idp_NG007010_R1_03 | non_idp_NG007010_R1_03_R01 | cb37537f-2a10-4b7b-82d3-011edf51cdde | gps_far | GPS point 3.8 km from the household | 3848
2026-09-18 | enum_D_09 | idp_NG007009_R1_11 | idp_NG007009_R1_11_H04 | d08dd596-3f3e-4f38-92d8-1b1da20d9a67 | fcs_flat | Every food group given the same number of days | 0
2026-09-18 | enum_D_14 | non_idp_NG007010_R1_04 | non_idp_NG007010_R1_04_H02 | 806531b8-3154-4e68-97ea-b3f9328afba0 | gps_far | GPS point 4.8 km from the household | 4758
2026-09-19 | enum_D_15 | non_idp_NG007012_C15 | non_idp_NG007012_C15_R01 | 3ba21307-881d-4431-9f9a-8db74204e210 | gps_far | GPS point 3.7 km from the household | 3707
2026-09-19 | enum_D_28 | non_idp_NG007023_C16 | non_idp_NG007023_C16_H02 | d2ddd04c-b4f7-4f25-b465-8c49f2f2312e | attending_exceed_school_age | More children attending school than of school age | 3
2026-09-19 | enum_D_28 | non_idp_NG007023_C16 | non_idp_NG007023_C16_H04 | 44f4159d-6fc0-4ce2-a642-ed5282a56d22 | children_exceed_hh | More children than household members | 2 + 11 children, household of 11
2026-09-20 | enum_D_03 | non_idp_NG007004_R1_02 | non_idp_NG007004_R1_02_H01 | 21f0048f-a44a-4791-8866-ae50ceb51a32 | gps_far | GPS point 4.9 km from the household | 4892
2026-09-20 | enum_D_03 | non_idp_NG007004_R1_02 | non_idp_NG007004_R1_02_H03 | 083910a0-517d-4ff4-bc5c-16a96a5d5410 | children_exceed_hh | More children than household members | 1 + 6 children, household of 5
2026-09-20 | enum_D_08 | non_idp_NG007007_R2_01 | non_idp_NG007007_R2_01_H03 | ce5e0280-f705-4f96-aeee-3fd205bb36c6 | fcs_hhs_contradiction | Acceptable food consumption with severe hunger | FCS 93.5, HHS 6
2026-09-21 | enum_D_08 | non_idp_NG007007_R2_02 | non_idp_NG007007_R2_02_H04 | 6373414b-898a-4845-95a6-e01414d8e23d | fcs_flat | Every food group given the same number of days | 7
2026-09-21 | enum_D_08 | non_idp_NG007007_R2_02 | non_idp_NG007007_R2_02_H04 | 6373414b-898a-4845-95a6-e01414d8e23d | fcs_hhs_contradiction | Acceptable food consumption with severe hunger | FCS 112.0, HHS 4
2026-09-22 | enum_D_04 | non_idp_NG007004_R1_03 | non_idp_NG007004_R1_03_H04 | bd373a71-1e63-443d-85f8-110b8417acbc | fcs_flat | Every food group given the same number of days | 7
2026-09-23 | enum_D_22 | non_idp_NG007021_C16 | non_idp_NG007021_C16_H02 | eaa65539-a978-446b-b771-7150c6bb0ca0 | gps_far | GPS point 3.0 km from the household | 2953
2026-09-24 | enum_D_15 | non_idp_NG007011_R1_01 | non_idp_NG007011_R1_01_H06 | 81f03ac2-308f-4a23-8887-3d9ca45328f8 | attending_exceed_school_age | More children attending school than of school age | 4
2026-09-24 | enum_D_21 | non_idp_NG007021_C17 | non_idp_NG007021_C17_H02 | f6ffbd66-ab5e-4267-b1ce-0625bd37077f | fcs_flat | Every food group given the same number of days | 7
2026-09-24 | enum_D_22 | non_idp_NG007021_C17 | non_idp_NG007021_C17_H06 | d70b8c36-3384-45c4-9774-b3f79118a039 | gps_far | GPS point 2.2 km from the household | 2245
2026-09-25 | enum_D_16 | non_idp_NG007011_R2_01 | non_idp_NG007011_R2_01_H06 | d9ffc04a-334c-45ff-ae93-4b26267f0069 | fcs_hhs_contradiction | Acceptable food consumption with severe hunger | FCS 93.5, HHS 6
2026-09-27 | enum_D_15 | non_idp_NG007011_R2_02 | non_idp_NG007011_R2_02_H02 | 74b832e5-ec9c-4ea4-b1d2-77d49b5851af | gps_far | GPS point 3.9 km from the household | 3930
2026-09-27 | enum_D_15 | non_idp_NG007011_R2_02 | non_idp_NG007011_R2_02_H02 | 74b832e5-ec9c-4ea4-b1d2-77d49b5851af | fcs_hhs_contradiction | Acceptable food consumption with severe hunger | FCS 35.5, HHS 4

## Removed
Interviews removed from the dataset, and why
Synthetic data – not real findings
date | enumerator_id | cluster_id | household_id | _uuid | check_id | reason
2026-08-17 | enum_D_14 | non_idp_NG007022_C06 | non_idp_NG007022_C06_H06 | e4161273-bffa-4de5-9406-7dba7b72b45f | C06 | Cluster had been reported inaccessible
2026-08-17 | enum_D_25 | non_idp_NG007022_C08 | non_idp_NG007022_C08_H01 | 345b45b5-e50d-43ca-8eaa-4c50567c0c30 | C02 | Same submission uploaded more than once
2026-08-17 | enum_D_25 | non_idp_NG007022_C08 | non_idp_NG007022_C08_H03 | 869f68aa-dfe1-45ab-912f-a79468e332c6 | C01 | Respondent did not consent
2026-08-17 | enum_D_28 | non_idp_NG007022_C06 | non_idp_NG007022_C06_H01 | b49dc926-8b02-4d40-985b-0c682fed581e | C06 | Cluster had been reported inaccessible
2026-08-18 | enum_D_26 | non_idp_NG007022_C09 | non_idp_NG007022_C09_H05 | 621ae298-c9f7-4cb8-8d2b-f7c7e28e8b79 | C04 | Interview took 10 minutes
2026-08-19 | enum_D_25 | non_idp_NG007022_C10 | non_idp_NG007022_C10_H01 | 9e168c0b-edf2-4dcf-82e1-4b92cf0f6d55 | C04 | Interview took 10 minutes
2026-08-20 | enum_D_12 | non_idp_NG007022_C06 | non_idp_NG007022_C06_H05 | c05a80aa-3c3c-4a2f-bf36-8377da04732c | C06 | Cluster had been reported inaccessible
2026-08-20 | enum_D_25 | non_idp_NG007022_C11 | non_idp_NG007022_C11_H04 | 18a6a66f-96bd-4636-a31c-2ac080005d7f | C04 | Interview took 5 minutes
2026-08-21 | enum_D_06 | non_idp_NG007022_C06 | non_idp_NG007022_C06_H04 | ab356051-48a0-4ab2-87c6-91b51295277b | C06 | Cluster had been reported inaccessible
2026-08-22 | enum_D_25 | non_idp_NG007022_C13 | non_idp_NG007022_C13_H02 | c4315d59-a96e-405f-94d5-2a19602bb926 | C01 | Respondent did not consent
2026-08-22 | enum_D_26 | non_idp_NG007022_C13 | non_idp_NG007022_C13_H04 | 758156d5-bdc4-40aa-97f0-ad02e962b04a | C01 | Respondent did not consent
2026-08-23 | enum_D_08 | idp_NG007007_C07 | idp_NG007007_C07_H02 | ed5e9664-7088-4599-b7f5-4a00b2e1a124 | C03 | Household already interviewed in an earlier submission
2026-08-23 | enum_D_25 | non_idp_NG007022_C14 | non_idp_NG007022_C14_H03 | a95cfd6d-2116-4510-b186-6a90dd9af2a0 | C03 | Household already interviewed in an earlier submission
2026-08-24 | enum_D_12 | non_idp_NG007009_C09 | non_idp_NG007009_C09_H06 | 3c1b6299-d147-4818-84f1-2da225fab030 | C04 | Interview took 7 minutes
2026-08-24 | enum_D_25 | non_idp_NG007022_C15 | non_idp_NG007022_C15_H05 | f39e67ee-9b7b-45eb-8afe-2bebd7613761 | C04 | Interview took 12 minutes
2026-08-24 | enum_D_26 | non_idp_NG007022_C15 | non_idp_NG007022_C15_H01 | 7b9754dc-3fb3-4d72-b699-4805d2f35f2a | C01 | Respondent did not consent
2026-08-24 | enum_D_26 | non_idp_NG007022_C06 | non_idp_NG007022_C06_H02 | 8a804867-7ff9-4ac6-839f-9d2b0f4205b1 | C06 | Cluster had been reported inaccessible
2026-08-25 | enum_D_03 | non_idp_NG007004_C17 | non_idp_NG007004_C17_H04 | 51d37932-1b27-4c6b-a434-a24d147a4efd | C02 | Same submission uploaded more than once
2026-08-25 | enum_D_05 | non_idp_NG007005_C07 | non_idp_NG007005_C07_H03 | 95f00cc6-1f76-4589-ad29-771ac4b78d13 | C01 | Respondent did not consent
2026-08-25 | enum_D_13 | non_idp_NG007010_C17 | non_idp_NG007010_C17_H02 | a32230b4-c2ad-4a1b-bee5-a76e1f901154 | C02 | Same submission uploaded more than once
2026-08-25 | enum_D_27 | non_idp_NG007023_C01 | non_idp_NG007023_C01_H01 | f0df2b7c-67d4-44b1-8062-760943fc539a | C02 | Same submission uploaded more than once
2026-08-25 | enum_D_27 | non_idp_NG007023_C01 | non_idp_NG007023_C01_H05 | daab7749-4ce5-4371-a1e3-52fac370162c | C04 | Interview took 7 minutes
2026-08-25 | enum_D_27 | non_idp_NG007023_C01 | non_idp_NG007023_C01_H06 | 526be11e-394e-4555-a316-58fd02483978 | C01 | Respondent did not consent
2026-08-26 | enum_D_06 | non_idp_NG007005_C08 | non_idp_NG007005_C08_R01 | 2fad1078-70c2-4c55-8523-e57fa3e62e74 | C04 | Interview took 9 minutes
2026-08-26 | enum_D_11 | non_idp_NG007022_C06 | non_idp_NG007022_C06_H03 | 13bad379-0575-493d-9ae5-a408e3bfb1ec | C06 | Cluster had been reported inaccessible
2026-08-26 | enum_D_13 | idp_NG007011_C01 | idp_NG007011_C01_H01 | b9ac0851-cead-4115-99af-b91c2d313639 | C04 | Interview took 12 minutes
2026-08-26 | enum_D_24 | idp_NG007022_C03 | idp_NG007022_C03_R01 | ac5fb6a5-5692-4102-8e2b-5db00626e767 | C04 | Interview took 5 minutes
2026-08-26 | enum_D_27 | non_idp_NG007023_C02 | non_idp_NG007023_C02_H03 | 325ff0c1-efb8-4ac1-a79f-89c65f35a27a | C04 | Interview took 11 minutes
2026-08-27 | enum_D_14 | idp_NG007011_C02 | idp_NG007011_C02_H06 | 1edf10ff-7c64-442b-a7cb-1229453c9af9 | C04 | Interview took 10 minutes
2026-08-27 | enum_D_16 | non_idp_NG007011_C14 | non_idp_NG007011_C14_H01 | bc59737a-9b6b-427b-ae36-b851b66e3097 | C01 | Respondent did not consent
2026-08-27 | enum_D_16 | non_idp_NG007011_C15 | non_idp_NG007011_C15_R01 | fc7604a7-cc71-46a8-bcc8-5169766c889e | C01 | Respondent did not consent
2026-08-27 | enum_D_28 | non_idp_NG007023_C03 | non_idp_NG007023_C03_H01 | d82c03cd-c044-4163-bcd0-b1894b2ddbcb | C01 | Respondent did not consent
2026-08-28 | enum_D_03 | idp_NG007005_C02 | idp_NG007005_C02_H02 | 647cb1c2-810e-4b73-94a4-e6f7f5b54e0e | C04 | Interview took 11 minutes
2026-08-28 | enum_D_06 | non_idp_NG007005_C11 | non_idp_NG007005_C11_H01 | da0f18cd-a448-41aa-9116-b6fe054b1519 | C01 | Respondent did not consent
2026-08-28 | enum_D_12 | non_idp_NG007009_C13 | non_idp_NG007009_C13_H04 | fec486f0-8843-4159-aeb2-35710906bcc0 | C04 | Interview took 9 minutes
2026-08-28 | enum_D_14 | idp_NG007011_C03 | idp_NG007011_C03_H02 | 3b91842c-20f7-4cc8-8c58-3020b56c2879 | C01 | Respondent did not consent
2026-08-28 | enum_D_21 | idp_NG007021_C11 | idp_NG007021_C11_R03 | 7b51da5d-0202-4493-94d7-9a2d942e2a2c | C01 | Respondent did not consent
2026-08-28 | enum_D_22 | idp_NG007021_C11 | idp_NG007021_C11_R02 | 6922f039-134d-4720-b649-00ed0ba0bb09 | C01 | Respondent did not consent
2026-08-28 | enum_D_23 | idp_NG007022_C04 | idp_NG007022_C04_H03 | 561d99b1-c848-44eb-83d4-b9d4b0e8bc7e | C01 | Respondent did not consent
2026-08-28 | enum_D_24 | idp_NG007022_C98 | idp_NG007022_C04_H05 | f2a55b76-b468-48d9-b874-a93b27e164fb | C05 | Cluster code not in the sample
2026-08-28 | enum_D_25 | idp_NG007023_C02 | idp_NG007023_C02_H02 | 918de108-e986-46dd-a58f-329158fd8e8d | C01 | Respondent did not consent
2026-08-29 | enum_D_09 | non_idp_NG007009_C03 | non_idp_NG007009_C03_R02 | d8337334-d3d6-4a8a-8b75-1a4ca129c5e3 | C01 | Respondent did not consent
2026-08-29 | enum_D_15 | non_idp_NG007011_C16 | non_idp_NG007011_C16_H05 | 7bde01a1-640f-4628-bc53-25dc8b4811c6 | C01 | Respondent did not consent
2026-08-30 | enum_D_05 | non_idp_NG007005_C13 | non_idp_NG007005_C13_H04 | 6c87b0ab-ee9a-4b27-a9c8-3db4110473e8 | C04 | Interview took 6 minutes
2026-08-30 | enum_D_06 | non_idp_NG007005_C13 | non_idp_NG007005_C13_H05 | 6600e559-c356-496e-9573-723b85ea8ab8 | C01 | Respondent did not consent
2026-08-30 | enum_D_12 | non_idp_NG007009_C15 | non_idp_NG007009_C15_H05 | 484773b8-9050-4b69-bb73-27c21a3e552b | C01 | Respondent did not consent
2026-08-30 | enum_D_17 | idp_NG007020_C03 | idp_NG007020_C03_H02 | a88c64a9-502c-4d91-88f8-9b360bff0df8 | C01 | Respondent did not consent
2026-08-30 | enum_D_26 | idp_NG007023_C04 | idp_NG007023_C04_H05 | b402f2c7-c496-42fc-9454-d926eb904273 | C01 | Respondent did not consent
2026-08-31 | enum_D_04 | idp_NG007005_C04 | idp_NG007005_C04_R01 | 89b26b5a-dc78-43b8-a38b-2a5c3a5afda3 | C01 | Respondent did not consent
2026-08-31 | enum_D_05 | non_idp_NG007005_C14 | non_idp_NG007005_C14_H03 | fb0ce716-c50e-4059-bc23-6f8d01cbd99b | C01 | Respondent did not consent
2026-08-31 | enum_D_11 | non_idp_NG007009_C16 | non_idp_NG007009_C16_R02 | 21338347-d107-43da-bc76-8a426ec1ebee | C04 | Interview took 8 minutes
2026-08-31 | enum_D_21 | idp_NG007021_C13 | idp_NG007021_C13_H04 | fbc48304-9df2-469f-9fae-009b2ca6506b | C01 | Respondent did not consent
2026-09-01 | enum_D_02 | idp_NG007004_C11 | idp_NG007004_C11_H02 | f4f66f08-cc4e-41df-a36a-5be6ffafe56f | C04 | Interview took 9 minutes
2026-09-01 | enum_D_05 | non_idp_NG007005_C16 | non_idp_NG007005_C16_H04 | 3c1a1003-d556-4983-9074-299cb73cc972 | C01 | Respondent did not consent
2026-09-01 | enum_D_07 | idp_NG007007_C12 | idp_NG007007_C12_H05 | d98c665f-05ae-44d3-8730-1ec6639cd02f | C02 | Same submission uploaded more than once
2026-09-01 | enum_D_15 | non_idp_NG007012_C91 | non_idp_NG007012_C02_H05 | 00ddb0a5-89a9-4175-a154-df1924f3bb6a | C05 | Cluster code not in the sample
2026-09-01 | enum_D_20 | non_idp_NG007020_C11 | non_idp_NG007020_C11_H02 | 1a37acbf-4f3d-446b-aac5-9887e910bf70 | C01 | Respondent did not consent
2026-09-01 | enum_D_20 | non_idp_NG007020_C11 | non_idp_NG007020_C11_R01 | 154383fd-c9a1-4094-b53d-f4bebc0e6e5e | C04 | Interview took 9 minutes
2026-09-01 | enum_D_25 | idp_NG007023_C05 | idp_NG007023_C05_H03 | 830330f4-9640-4260-a009-ea4c0e4f9894 | C03 | Household already interviewed in an earlier submission
2026-09-02 | enum_D_04 | idp_NG007005_C06 | idp_NG007005_C06_H06 | e6f622a6-56ab-4440-8afc-482b404e589a | C04 | Interview took 11 minutes
2026-09-02 | enum_D_07 | non_idp_NG007007_C01 | non_idp_NG007007_C01_H04 | 15bf9a34-1f6c-4cf8-835a-f7c831f07c5c | C04 | Interview took 11 minutes
2026-09-02 | enum_D_08 | non_idp_NG007007_C01 | non_idp_NG007007_C01_H06 | 645ac530-744e-4715-a4ed-d59de371174a | C01 | Respondent did not consent
2026-09-02 | enum_D_09 | non_idp_NG007009_C06 | non_idp_NG007009_C06_H02 | 5d4e2be8-4049-4372-bf37-36387fda4420 | C04 | Interview took 9 minutes
2026-09-02 | enum_D_12 | non_idp_NG007010_C02 | non_idp_NG007010_C02_H02 | 5b8dd21f-5d1a-4e19-9b4f-efbcc04e101c | C02 | Same submission uploaded more than once
2026-09-02 | enum_D_20 | non_idp_NG007020_C12 | non_idp_NG007020_C12_H03 | 334dd1f5-074f-4685-816f-20e03ee0a7ab | C02 | Same submission uploaded more than once
2026-09-02 | enum_D_20 | non_idp_NG007020_C12 | non_idp_NG007020_C12_H06 | 5527592d-f4f1-4e24-83a5-6175880024cf | C04 | Interview took 5 minutes
2026-09-02 | enum_D_24 | idp_NG007022_C07 | idp_NG007022_C07_H03 | d3d348ec-dc6f-4e1e-865c-49f584bf50af | C04 | Interview took 4 minutes
2026-09-03 | enum_D_16 | non_idp_NG007012_C04 | non_idp_NG007012_C04_H01 | 0835d695-1bcb-4307-8d87-07e42faccb42 | C04 | Interview took 9 minutes
2026-09-03 | enum_D_20 | non_idp_NG007020_C13 | non_idp_NG007020_C13_R01 | abd02378-08a2-41cd-a279-033c03e64372 | C04 | Interview took 4 minutes
2026-09-03 | enum_D_24 | idp_NG007022_C08 | idp_NG007022_C08_H03 | 4b750cf4-57aa-4d50-9789-20420a33bda7 | C04 | Interview took 11 minutes
2026-09-03 | enum_D_26 | idp_NG007023_C07 | idp_NG007023_C07_R01 | 15ea8f4f-0366-41b6-8949-66e30cd7d849 | C04 | Interview took 8 minutes
2026-09-04 | enum_D_03 | idp_NG007005_C07 | idp_NG007005_C07_H02 | fd2c3a2d-699f-49cc-ab6b-24ab38b0d527 | C04 | Interview took 7 minutes
2026-09-04 | enum_D_05 | idp_NG007007_C03 | idp_NG007007_C03_H05 | 968fec6f-393c-4494-beb0-ca037587fa9b | C01 | Respondent did not consent
2026-09-04 | enum_D_05 | idp_NG007007_C03 | idp_NG007007_C03_R01 | b6e280d9-0cfd-41bc-855d-a6b6b8f66cae | C01 | Respondent did not consent
2026-09-04 | enum_D_14 | non_idp_NG007011_C02 | non_idp_NG007011_C02_H01 | 17b08ceb-3378-44b3-8fb3-a81567b6998b | C04 | Interview took 8 minutes
2026-09-04 | enum_D_16 | non_idp_NG007012_C05 | non_idp_NG007012_C05_H05 | adefcb1d-7f2e-416c-82e1-de659527b2ad | C04 | Interview took 8 minutes
2026-09-04 | enum_D_24 | idp_NG007022_C09 | idp_NG007022_C09_H04 | 72da84e2-25a6-4cda-a47d-3bf285e81f77 | C04 | Interview took 11 minutes
2026-09-05 | enum_D_04 | idp_NG007005_C08 | idp_NG007005_C08_H05 | 9640cc67-fd0e-484e-898c-ff6d7b35127b | C01 | Respondent did not consent
2026-09-05 | enum_D_18 | idp_NG007020_C07 | idp_NG007020_C07_R02 | cf79346c-6486-42eb-89c2-d841f1ef8d27 | C01 | Respondent did not consent
2026-09-05 | enum_D_27 | non_idp_NG007023_C08 | non_idp_NG007023_C08_H06 | b4ada0dc-3e02-4474-a172-57a0959e6398 | C01 | Respondent did not consent
2026-09-06 | enum_D_02 | non_idp_NG007004_C04 | non_idp_NG007004_C04_H03 | 97fa30c3-2dfa-4d23-98d1-b2c1c91a2345 | C04 | Interview took 7 minutes
2026-09-06 | enum_D_03 | idp_NG007005_C09 | idp_NG007005_C09_H06 | 053af523-d95b-41b7-a4ac-3f47b2846dbf | C01 | Respondent did not consent
2026-09-06 | enum_D_04 | idp_NG007005_C09 | idp_NG007005_C09_H04 | d8d76cd3-1d02-410c-8306-4831e6bf3824 | C04 | Interview took 11 minutes
2026-09-06 | enum_D_17 | idp_NG007020_C08 | idp_NG007020_C08_H05 | 94f6489f-0d1c-46d0-9482-e7238962b8b5 | C04 | Interview took 11 minutes
2026-09-06 | enum_D_17 | idp_NG007020_C08 | idp_NG007020_C08_R02 | c4f9f928-640f-4a28-a47a-98ca605a95de | C01 | Respondent did not consent
2026-09-06 | enum_D_18 | idp_NG007020_C08 | idp_NG007020_C08_H02 | c8d2dac0-31d3-4bb4-8222-ffe0a12b99cc | C04 | Interview took 11 minutes
2026-09-06 | enum_D_22 | non_idp_NG007021_C03 | non_idp_NG007021_C03_H03 | 9d9673e6-b318-4fa3-9819-3ee68265ed9a | C04 | Interview took 7 minutes
2026-09-06 | enum_D_25 | idp_NG007023_C09 | idp_NG007023_C09_H04 | 8e4f7886-0a46-4807-9d93-5dcf972852bd | C02 | Same submission uploaded more than once
2026-09-06 | enum_D_26 | idp_NG007023_C09 | idp_NG007023_C09_H01 | 104d073e-ef30-4835-8852-422fb3902430 | C04 | Interview took 9 minutes
2026-09-07 | enum_D_08 | non_idp_NG007007_C07 | non_idp_NG007007_C07_R01 | 4d10a184-0555-46b1-922c-cbc44e02cf73 | C01 | Respondent did not consent
2026-09-07 | enum_D_11 | non_idp_NG007010_C11 | non_idp_NG007010_C11_H02 | 018bb6c2-0212-417c-b497-4a3a36642f6b | C04 | Interview took 6 minutes
2026-09-07 | enum_D_14 | non_idp_NG007011_C04 | non_idp_NG007011_C04_R01 | be958604-a33b-4112-9434-ccd596aa191e | C03 | Household already interviewed in an earlier submission
2026-09-07 | enum_D_18 | idp_NG007020_C09 | idp_NG007020_C09_H05 | d70fbd0a-4892-4a4f-8987-b3b45e918ed7 | C01 | Respondent did not consent
2026-09-07 | enum_D_20 | non_idp_NG007020_C16 | non_idp_NG007020_C16_H01 | 646641ec-5127-4495-9fb1-61e5b308bef1 | C03 | Household already interviewed in an earlier submission
2026-09-08 | enum_D_02 | non_idp_NG007004_C06 | non_idp_NG007004_C06_R02 | 3c506611-2ca9-4ac3-893f-672358e4450c | C04 | Interview took 9 minutes
2026-09-08 | enum_D_03 | idp_NG007005_C11 | idp_NG007005_C11_H06 | 3aff16f8-463f-42f9-b9ad-40e128f15ac3 | C01 | Respondent did not consent
2026-09-08 | enum_D_04 | idp_NG007005_C11 | idp_NG007005_C11_H05 | 91cf1c14-3e86-46be-9bf0-c0ff5f6e86bc | C02 | Same submission uploaded more than once
2026-09-08 | enum_D_09 | idp_NG007009_R1_05 | idp_NG007009_R1_05_H03 | 495f9714-4fb7-4522-b913-4efd05c31816 | C04 | Interview took 6 minutes
2026-09-08 | enum_D_24 | idp_NG007022_C13 | idp_NG007022_C13_H04 | 45f4fac2-5dc3-4a12-b0c4-d87753ec28d7 | C04 | Interview took 6 minutes
2026-09-08 | enum_D_25 | idp_NG007023_C10 | idp_NG007023_C10_H02 | 15b6529e-02f3-49a1-b27f-c45e9427e92c | C02 | Same submission uploaded more than once
2026-09-09 | enum_D_02 | non_idp_NG007004_C08 | non_idp_NG007004_C08_H03 | cde12978-6d2c-4b94-bdbc-3239c331c953 | C04 | Interview took 6 minutes
2026-09-09 | enum_D_05 | non_idp_NG007005_R1_C94 | non_idp_NG007005_R1_02_H05 | 3683a293-840a-4475-89fe-06f88aea7017 | C05 | Cluster code not in the sample
2026-09-09 | enum_D_20 | non_idp_NG007020_C17 | non_idp_NG007020_C17_H02 | f27790b4-15f6-4810-b085-75354e8d288c | C04 | Interview took 7 minutes
2026-09-09 | enum_D_20 | non_idp_NG007020_C17 | non_idp_NG007020_C17_H03 | e573347d-cfe5-4bb2-8a57-fdd1fc7c8390 | C04 | Interview took 7 minutes
2026-09-09 | enum_D_26 | idp_NG007023_C11 | idp_NG007023_C11_H03 | 68615b98-05e8-4c1d-9e93-5a6cab26f771 | C04 | Interview took 6 minutes
2026-09-10 | enum_D_05 | non_idp_NG007005_R1_04 | non_idp_NG007005_R1_04_H01 | d36f288a-943a-4f46-8ac6-a3fdb03205c5 | C04 | Interview took 10 minutes
2026-09-10 | enum_D_06 | non_idp_NG007005_R1_04 | non_idp_NG007005_R1_04_R01 | 3cff3776-5da0-42ac-9ca0-d5a7d788f65f | C04 | Interview took 4 minutes
2026-09-10 | enum_D_11 | non_idp_NG007010_C14 | non_idp_NG007010_C14_H06 | e965663e-ec75-46bf-a3e2-efedc47817c2 | C04 | Interview took 6 minutes
2026-09-10 | enum_D_27 | non_idp_NG007023_C09 | non_idp_NG007023_C09_H03 | de83f2d9-62d1-4900-b18e-d0d5584343c0 | C03 | Household already interviewed in an earlier submission
2026-09-11 | enum_D_01 | non_idp_NG007004_C10 | non_idp_NG007004_C10_H03 | c061c6b3-f79b-4d6e-84b3-af66d41a967a | C01 | Respondent did not consent
2026-09-11 | enum_D_21 | non_idp_NG007021_C94 | non_idp_NG007021_C06_H01 | 0078af6d-e7f5-4da1-b075-2fa5bfeeebc2 | C05 | Cluster code not in the sample
2026-09-12 | enum_D_01 | non_idp_NG007004_C11 | non_idp_NG007004_C11_R01 | c5c6f940-9106-40da-884b-e71fd80b831b | C04 | Interview took 10 minutes
2026-09-12 | enum_D_10 | idp_NG007009_R1_07 | idp_NG007009_R1_07_H04 | 9fad942e-fdb7-42ec-a18b-10a32d31700c | C03 | Household already interviewed in an earlier submission
2026-09-12 | enum_D_16 | non_idp_NG007012_C11 | non_idp_NG007012_C11_H04 | 1f0b0b6d-db0b-4fa3-9ff1-8b2734f4c228 | C04 | Interview took 12 minutes
2026-09-13 | enum_D_03 | idp_NG007005_C13 | idp_NG007005_C13_H03 | ce2405b2-f21d-4e2e-aa19-2d70e7b37fda | C01 | Respondent did not consent
2026-09-13 | enum_D_05 | non_idp_NG007005_R2_02 | non_idp_NG007005_R2_02_H05 | 67b3ab5d-07bd-4102-ac75-8b0f0d648007 | C03 | Household already interviewed in an earlier submission
2026-09-13 | enum_D_27 | non_idp_NG007023_C10 | non_idp_NG007023_C10_R01 | 26d555f9-4067-4dff-8106-348d3e5566a5 | C02 | Same submission uploaded more than once
2026-09-13 | enum_D_27 | non_idp_NG007023_C10 | non_idp_NG007023_C10_R02 | f7ed8751-c358-460c-a9f1-1a9195d87660 | C04 | Interview took 6 minutes
2026-09-14 | enum_D_02 | non_idp_NG007004_C12 | non_idp_NG007004_C12_H06 | 8660fea2-565d-4b1c-81ee-7bd58529bef8 | C04 | Interview took 8 minutes
2026-09-14 | enum_D_03 | idp_NG007005_C14 | idp_NG007005_C14_R01 | 3ed3fbf7-2067-4199-a160-8e916ba46c5d | C03 | Household already interviewed in an earlier submission
2026-09-14 | enum_D_04 | idp_NG007005_C14 | idp_NG007005_C14_H02 | fd37bf34-bf87-4c24-80eb-023a2e2b6b6f | C01 | Respondent did not consent
2026-09-14 | enum_D_07 | non_idp_NG007007_C11 | non_idp_NG007007_C11_H02 | 9b81c6bc-89ca-4331-8324-3750a3d37bc2 | C01 | Respondent did not consent
2026-09-14 | enum_D_07 | non_idp_NG007007_C11 | non_idp_NG007007_C11_H05 | cf85c9f6-26ec-4392-a734-8ea32685cdbe | C04 | Interview took 4 minutes
2026-09-14 | enum_D_15 | non_idp_NG007012_C12 | non_idp_NG007012_C12_H03 | 379f039b-7570-4e61-986c-66f3df5dda60 | C02 | Same submission uploaded more than once
2026-09-14 | enum_D_18 | idp_NG007020_C13 | idp_NG007020_C13_H06 | f9fdf442-b68b-4b56-b759-3bd4598f966c | C01 | Respondent did not consent
2026-09-14 | enum_D_18 | idp_NG007020_C13 | idp_NG007020_C13_R01 | 707b56e0-570c-4368-8a19-4c753544263f | C04 | Interview took 8 minutes
2026-09-14 | enum_D_28 | non_idp_NG007023_C11 | non_idp_NG007023_C11_H06 | 8d50614a-9db1-495c-871e-5df6e000bbc8 | C04 | Interview took 6 minutes
2026-09-15 | enum_D_20 | idp_NG007021_C05 | idp_NG007021_C05_H02 | 96ceebfb-7ea1-40ea-8e98-5089723bb850 | C01 | Respondent did not consent
2026-09-16 | enum_D_02 | non_idp_NG007004_C14 | non_idp_NG007004_C14_H06 | e9402e6d-f85b-4dba-812a-41b6628d682b | C01 | Respondent did not consent
2026-09-16 | enum_D_04 | idp_NG007005_C15 | idp_NG007005_C15_R01 | 9fb5f847-e664-4587-afa4-86e51187fabc | C02 | Same submission uploaded more than once
2026-09-16 | enum_D_07 | non_idp_NG007007_R1_01 | non_idp_NG007007_R1_01_H01 | 131e73e5-61ae-413d-8f0e-292743904dd8 | C04 | Interview took 11 minutes
2026-09-16 | enum_D_09 | idp_NG007009_R1_10 | idp_NG007009_R1_10_H02 | 68926d83-df49-44c4-b01a-4a7093504ec4 | C01 | Respondent did not consent
2026-09-16 | enum_D_16 | non_idp_NG007012_C13 | non_idp_NG007012_C13_H01 | cb904a24-3dea-4e12-a37d-953120ea9d87 | C04 | Interview took 11 minutes
2026-09-16 | enum_D_16 | non_idp_NG007012_C13 | non_idp_NG007012_C13_H02 | 23d5b024-9c43-4bdd-a4ec-cb73d0e2260f | C04 | Interview took 6 minutes
2026-09-16 | enum_D_17 | idp_NG007020_C14 | idp_NG007020_C14_H03 | 1a787110-616a-472f-8c3c-072b32cfef1e | C04 | Interview took 11 minutes
2026-09-16 | enum_D_22 | non_idp_NG007021_C92 | non_idp_NG007021_C11_H03 | 92170bc7-5b1a-4f0e-9551-dce7c372995c | C05 | Cluster code not in the sample
2026-09-16 | enum_D_22 | non_idp_NG007021_C11 | non_idp_NG007021_C11_H01 | 7de981b0-5920-4169-af82-0c5e4e80b700 | C03 | Household already interviewed in an earlier submission
2026-09-17 | enum_D_15 | non_idp_NG007012_C14 | non_idp_NG007012_C14_H02 | 0d88391a-5cdf-42a3-ba8a-47ea5159364e | C01 | Respondent did not consent
2026-09-18 | enum_D_03 | non_idp_NG007005_C01 | non_idp_NG007005_C01_R02 | 57bad04d-87de-448e-bee8-ec5285ed2798 | C04 | Interview took 6 minutes
2026-09-18 | enum_D_08 | non_idp_NG007007_R1_03 | non_idp_NG007007_R1_03_H06 | ae18e869-1aab-4db4-ab00-58cbb16c9cf4 | C02 | Same submission uploaded more than once
2026-09-18 | enum_D_22 | non_idp_NG007021_C12 | non_idp_NG007021_C12_H04 | 6a93bfd2-3d07-4adc-8149-54d72927cec3 | C04 | Interview took 4 minutes
2026-09-19 | enum_D_04 | non_idp_NG007004_R1_01 | non_idp_NG007004_R1_01_H04 | 7ce53244-5d0f-4a93-997a-439f17801e47 | C04 | Interview took 11 minutes
2026-09-19 | enum_D_17 | non_idp_NG007020_C03 | non_idp_NG007020_C03_H05 | 0e82c365-b580-4377-8fcc-b22307b7241e | C02 | Same submission uploaded more than once
2026-09-19 | enum_D_19 | idp_NG007021_C08 | idp_NG007021_C08_R01 | 7124a1f5-a605-44f8-8d63-640ebdcea82f | C03 | Household already interviewed in an earlier submission
2026-09-19 | enum_D_22 | non_idp_NG007021_C13 | non_idp_NG007021_C13_H03 | 1cb1769a-204c-4be1-a169-e9bfbba40e16 | C04 | Interview took 9 minutes
2026-09-21 | enum_D_08 | non_idp_NG007007_R2_02 | non_idp_NG007007_R2_02_H02 | f8a4fe21-928a-464b-8c98-fea96335ca68 | C01 | Respondent did not consent
2026-09-21 | enum_D_10 | idp_NG007009_R1_13 | idp_NG007009_R1_13_H02 | b2efa4f1-b48d-4921-b3a7-d42911513dab | C02 | Same submission uploaded more than once
2026-09-21 | enum_D_21 | non_idp_NG007021_C14 | non_idp_NG007021_C14_H06 | d52b52d6-9620-497f-8122-93cd9e16275c | C04 | Interview took 12 minutes
2026-09-21 | enum_D_24 | non_idp_NG007022_C07 | non_idp_NG007022_C07_H01 | bb4f11b9-5f3f-43ff-a541-8666d34f3228 | C03 | Household already interviewed in an earlier submission
2026-09-22 | enum_D_22 | non_idp_NG007021_C15 | non_idp_NG007021_C15_H03 | 27ef43f4-1543-4777-a88b-2a6ce3f69222 | C02 | Same submission uploaded more than once
2026-09-23 | enum_D_21 | non_idp_NG007021_C16 | non_idp_NG007021_C16_R02 | 0de30a55-a82e-431d-92af-571194ea825f | C04 | Interview took 5 minutes
2026-09-23 | enum_D_22 | non_idp_NG007021_C16 | non_idp_NG007021_C16_H06 | 6a90cb9a-5406-4abf-8aa6-92777936c8ac | C01 | Respondent did not consent
2026-09-24 | enum_D_15 | non_idp_NG007011_R1_01 | non_idp_NG007011_R1_01_H01 | 4bed3de3-4c49-4d18-af73-e145db97c202 | C01 | Respondent did not consent
2026-09-24 | enum_D_22 | non_idp_NG007021_C17 | non_idp_NG007021_C17_H03 | 28c8f2cc-67b4-4571-9988-b51af1e5e1dd | C04 | Interview took 6 minutes
2026-09-25 | enum_D_10 | non_idp_NG007007_R2_03 | non_idp_NG007007_R2_03_H03 | 1b134b34-9de3-463f-ae20-cdca7eeee5c9 | C04 | Interview took 5 minutes
2026-09-25 | enum_D_15 | non_idp_NG007011_R2_01 | non_idp_NG007011_R2_01_H03 | 2da6fe91-452e-4f3d-9907-693ce468090d | C04 | Interview took 10 minutes
2026-09-25 | enum_D_15 | non_idp_NG007011_R2_01 | non_idp_NG007011_R2_01_H05 | 0f98593b-d752-420b-a2b3-69b359409975 | C04 | Interview took 10 minutes
2026-09-26 | enum_D_24 | non_idp_NG007021_R1_02 | non_idp_NG007021_R1_02_R01 | 7aa69000-4921-44b7-bb47-73a4da91d795 | C01 | Respondent did not consent
2026-09-27 | enum_D_18 | non_idp_NG007012_R2_02 | non_idp_NG007012_R2_02_H03 | af863baa-ba3a-464a-91ca-5a172e5f392f | C04 | Interview took 8 minutes

## Enumerators
Enumerators
Synthetic data – not real findings
enumerator_id | interviews | median minutes | % repeated answers | interviews removed | interviews flagged | pattern
enum_D_01 | 74 | 42.4 | 0 | 2 | 3
enum_D_02 | 94 | 42.2 | 0 | 6 | 3
enum_D_03 | 70 | 42.1 | 5.7 | 8 | 5
enum_D_04 | 72 | 43.3 | 5.6 | 8 | 4
enum_D_05 | 69 | 38.9 | 0 | 9 | 9
enum_D_06 | 70 | 40.3 | 0 | 5 | 2
enum_D_07 | 78 | 42.2 | 2.6 | 5 | 3
enum_D_08 | 54 | 39 | 3.7 | 5 | 8
enum_D_09 | 67 | 42.2 | 0 | 4 | 6
enum_D_10 | 70 | 39.3 | 2.9 | 3 | 3
enum_D_11 | 71 | 42.6 | 0 | 4 | 4
enum_D_12 | 69 | 41.7 | 2.9 | 5 | 3
enum_D_13 | 65 | 44.8 | 3.1 | 2 | 6
enum_D_14 | 67 | 39.8 | 0 | 5 | 3
enum_D_15 | 65 | 42.9 | 3.1 | 7 | 7
enum_D_16 | 76 | 41 | 0 | 7 | 2
enum_D_17 | 72 | 43.7 | 2.8 | 5 | 4
enum_D_18 | 66 | 42.5 | 0 | 6 | 2
enum_D_19 | 66 | 40.8 | 0 | 1 | 6
enum_D_20 | 74 | 38 | 2.7 | 9 | 4
enum_D_21 | 58 | 40.6 | 0 | 5 | 3
enum_D_22 | 78 | 41.7 | 2.6 | 9 | 6
enum_D_23 | 68 | 44 | 0 | 1 | 5
enum_D_24 | 77 | 40.6 | 0 | 8 | 2
enum_D_25 | 83 | 40.5 | 9.6 | 11 | 1
enum_D_26 | 62 | 42.7 | 0 | 8 | 1
enum_D_27 | 65 | 38.7 | 6.2 | 8 | 4
enum_D_28 | 69 | 45 | 0 | 3 | 5

## Progress
Progress against target by LGA
Synthetic data – not real findings
adm1_name | adm2_name | pop_type | target | achieved | percent
Benue | Buruku | idp | 60 | 90 | 150
Benue | Buruku | non_idp | 102 | 102 | 100
Benue | Gboko | idp | 96 | 96 | 100
Benue | Gboko | non_idp | 102 | 102 | 100
Benue | Gwer East | idp | 72 | 72 | 100
Benue | Gwer East | non_idp | 102 | 102 | 100
Benue | Katsina-Ala | idp | 84 | 84 | 100
Benue | Katsina-Ala | non_idp | 102 | 102 | 100
Benue | Konshisha | non_idp | 102 | 102 | 100
Benue | Kwande | idp | 36 | 36 | 100
Benue | Kwande | non_idp | 102 | 102 | 100
Benue | Logo | non_idp | 102 | 102 | 100
Benue | Tarka | idp | 84 | 84 | 100
Benue | Tarka | non_idp | 102 | 102 | 100
Benue | Ukum | idp | 90 | 90 | 100
Benue | Ukum | non_idp | 102 | 102 | 100
Benue | Ushongo | idp | 90 | 96 | 106.7
Benue | Ushongo | non_idp | 102 | 102 | 100
Benue | Vandeikya | idp | 90 | 90 | 100
Benue | Vandeikya | non_idp | 102 | 102 | 100