## Summary
Data-quality digest: Partner E
Synthetic data – not real findings
Item | Value
Partner | Partner E
States | Borno
Data as of | 2026-09-27
Submissions received | 1216
Interviews kept | 1127
Interviews removed | 89
Values corrected | 11
Interviews flagged for follow-up | 76
Households targeted | 1218
Households achieved | 1127
Progress against target | 92.5%

## Follow up
Interviews flagged: please check with the enumerator
Synthetic data – not real findings
date | enumerator_id | cluster_id | household_id | _uuid | check | issue | value
2026-08-19 | enum_E_08 | non_idp_NG008009_C05 | non_idp_NG008009_C05_H06 | c15b4781-6f52-4a26-8d63-2f6590979f91 | fcs_flat | Every food group given the same number of days | 0
2026-08-20 | enum_E_05 | idp_NG008009_C02 | idp_NG008009_C02_R01 | 5ab85d92-c321-4b01-abf0-8dc655a67b5f | fcs_flat | Every food group given the same number of days | 7
2026-08-22 | enum_E_05 | idp_NG008009_C03 | idp_NG008009_C03_H01 | 0c7fa7e0-41ea-4f05-9d43-05ccc8d47a35 | fcs_hhs_contradiction | Acceptable food consumption with severe hunger | FCS 42.0, HHS 4
2026-08-22 | enum_E_05 | idp_NG008009_C03 | idp_NG008009_C03_H04 | a5ef2af5-d285-4032-a418-f3d505410ae2 | fcs_hhs_contradiction | Acceptable food consumption with severe hunger | FCS 48.5, HHS 4
2026-08-22 | enum_E_07 | non_idp_NG008009_C06 | non_idp_NG008009_C06_H06 | e58be5d2-cb7b-4cb7-99c4-a1a86e7f7199 | fcs_flat | Every food group given the same number of days | 7
2026-08-22 | enum_E_13 | idp_NG008020_C11 | idp_NG008020_C11_H02 | 56540953-6ad5-4be1-b6c7-3592ad72b008 | fcs_flat | Every food group given the same number of days | 7
2026-08-23 | enum_E_03 | non_idp_NG008006_C16 | non_idp_NG008006_C16_H01 | c0b2f34f-35bb-406a-9b06-efa254efef4f | children_exceed_hh | More children than household members | 2 + 7 children, household of 8
2026-08-23 | enum_E_09 | non_idp_NG008012_C05 | non_idp_NG008012_C05_H04 | 2d1e1319-c90c-4819-a60f-8c7639154736 | gps_far | GPS point 1.7 km from the household | 1714
2026-08-23 | enum_E_10 | non_idp_NG008012_C05 | non_idp_NG008012_C05_H06 | a3ab2b90-728b-40c4-a71c-959f9daaf9ae | gps_far | GPS point 1.9 km from the household | 1866
2026-08-23 | enum_E_17 | idp_NG008027_C11 | idp_NG008027_C11_R02 | b3798253-0cc6-43cb-ab22-e508eab05473 | children_exceed_hh | More children than household members | 0 + 8 children, household of 7
2026-08-25 | enum_E_04 | non_idp_NG008006_C17 | non_idp_NG008006_C17_H02 | 23276e4f-342c-4931-8bf6-33bbd64af1b7 | fcs_hhs_contradiction | Acceptable food consumption with severe hunger | FCS 41.0, HHS 5
2026-08-26 | enum_E_02 | non_idp_NG008004_C12 | non_idp_NG008004_C12_H04 | d2c3e996-eb65-4f7a-807f-e0877a02deaa | fcs_hhs_contradiction | Acceptable food consumption with severe hunger | FCS 36.5, HHS 4
2026-08-26 | enum_E_03 | idp_NG008007_C10 | idp_NG008007_C10_H06 | 5b8ed068-3ee6-4744-9091-bb6ad2c8b54e | gps_far | GPS point 1.0 km from the household | 985
2026-08-26 | enum_E_04 | idp_NG008007_C10 | idp_NG008007_C10_R01 | 027fc368-6fdd-481c-a1af-fee1857e4a10 | gps_far | GPS point 3.5 km from the household | 3472
2026-08-26 | enum_E_06 | non_idp_NG008004_C02 | non_idp_NG008004_C02_H03 | b82a5723-c4a2-4bb3-ad24-b18633905cb4 | fcs_hhs_contradiction | Acceptable food consumption with severe hunger | FCS 36.5, HHS 4
2026-08-26 | enum_E_06 | idp_NG008009_C05 | idp_NG008009_C05_R01 | 746f1b9f-c536-45e1-8eaa-d6884807f640 | fcs_flat | Every food group given the same number of days | 0
2026-08-26 | enum_E_08 | non_idp_NG008009_C08 | non_idp_NG008009_C08_H06 | db6e7a02-9f93-42e5-a83a-119acee9585a | gps_far | GPS point 4.9 km from the household | 4944
2026-08-27 | enum_E_03 | idp_NG008007_C11 | idp_NG008007_C11_H04 | 8fa8c3f2-bbba-4012-a1d5-9f99eab8a55d | attending_exceed_school_age | More children attending school than of school age | 4
2026-08-27 | enum_E_17 | non_idp_NG008027_C02 | non_idp_NG008027_C02_H06 | 1b217468-ee0d-4dfd-ba6b-0b9cd074d4f4 | gps_far | GPS point 1.6 km from the household | 1560
2026-08-28 | enum_E_05 | idp_NG008009_C11 | idp_NG008009_C11_H06 | aaaa4426-dc12-447b-aede-33ff316112ab | fcs_hhs_contradiction | Acceptable food consumption with severe hunger | FCS 39.5, HHS 5
2026-08-28 | enum_E_13 | non_idp_NG008020_C03 | non_idp_NG008020_C03_H03 | 3d6b6573-964d-4a39-b7bc-96e56fbce54b | fcs_flat | Every food group given the same number of days | 7
2026-08-28 | enum_E_14 | non_idp_NG008020_C03 | non_idp_NG008020_C03_H05 | d1f9124f-948d-4d6e-8403-5c33b733762e | gps_far | GPS point 1.8 km from the household | 1822
2026-08-28 | enum_E_18 | non_idp_NG008027_C03 | non_idp_NG008027_C03_H01 | a3a1e292-a026-4771-ac51-9e320b514e48 | fcs_flat | Every food group given the same number of days | 7
2026-08-28 | enum_E_18 | non_idp_NG008027_C03 | non_idp_NG008027_C03_H01 | a3a1e292-a026-4771-ac51-9e320b514e48 | fcs_hhs_contradiction | Acceptable food consumption with severe hunger | FCS 112.0, HHS 4
2026-08-29 | enum_E_07 | non_idp_NG008009_C10 | non_idp_NG008009_C10_H03 | 9047883a-1d10-4eaf-afe0-7553cb769703 | fcs_hhs_contradiction | Acceptable food consumption with severe hunger | FCS 42.5, HHS 4
2026-08-30 | enum_E_02 | non_idp_NG008006_C02 | non_idp_NG008006_C02_H05 | 878be635-01c1-4830-a2fa-d36cdd91b0c6 | attending_exceed_school_age | More children attending school than of school age | 7
2026-08-30 | enum_E_04 | idp_NG008007_C13 | idp_NG008007_C13_H05 | fb6998ab-fdec-4146-96bd-66334528f722 | fcs_flat | Every food group given the same number of days | 0
2026-08-30 | enum_E_06 | idp_NG008009_C13 | idp_NG008009_C13_H06 | 889696d9-39f3-499b-9a40-06d7cdef68ee | fcs_hhs_contradiction | Acceptable food consumption with severe hunger | FCS 47.0, HHS 4
2026-08-30 | enum_E_12 | non_idp_NG008018_C07 | non_idp_NG008018_C07_H04 | 8ccc6558-54bc-466e-94a3-c57cf10871a5 | children_exceed_hh | More children than household members | 0 + 5 children, household of 4
2026-08-30 | enum_E_18 | non_idp_NG008027_C05 | non_idp_NG008027_C05_H04 | d2ba2888-4f07-483d-a249-01fa298e479a | children_exceed_hh | More children than household members | 1 + 6 children, household of 5
2026-08-31 | enum_E_01 | non_idp_NG008006_C04 | non_idp_NG008006_C04_H01 | 2fb8e2da-4596-4873-bc37-8e2368293321 | gps_far | GPS point 3.6 km from the household | 3642
2026-09-01 | enum_E_05 | non_idp_NG008009_C02 | non_idp_NG008009_C02_H05 | 5736d6cd-205a-4b51-8137-1dec0b892a83 | fcs_hhs_contradiction | Acceptable food consumption with severe hunger | FCS 42.5, HHS 4
2026-09-01 | enum_E_10 | non_idp_NG008012_C10 | non_idp_NG008012_C10_H06 | 6cc37702-14a5-4fa8-b30a-182114d6fe9d | fcs_hhs_contradiction | Acceptable food consumption with severe hunger | FCS 41.5, HHS 4
2026-09-02 | enum_E_04 | idp_NG008007_C16 | idp_NG008007_C16_H06 | 4a06f78a-1558-430c-b0fe-9260a3b5beab | fcs_hhs_contradiction | Acceptable food consumption with severe hunger | FCS 56.0, HHS 4
2026-09-02 | enum_E_05 | non_idp_NG008009_C03 | non_idp_NG008009_C03_H06 | 29814e96-b545-44a8-904c-152d54dd2fc7 | fcs_hhs_contradiction | Acceptable food consumption with severe hunger | FCS 93.5, HHS 6
2026-09-02 | enum_E_08 | non_idp_NG008009_C13 | non_idp_NG008009_C13_H04 | 3e05e5be-f81c-4361-a607-38b4e7ce7a87 | gps_far | GPS point 1.5 km from the household | 1525
2026-09-02 | enum_E_13 | non_idp_NG008020_C09 | non_idp_NG008020_C09_H06 | 7dff7c3a-12e8-464d-a6cd-b2cbd8e5a54a | gps_far | GPS point 1.9 km from the household | 1908
2026-09-02 | enum_E_17 | non_idp_NG008027_C07 | non_idp_NG008027_C07_H03 | f4674803-8e35-46f4-bd35-4c8d6dd55d8f | fcs_hhs_contradiction | Acceptable food consumption with severe hunger | FCS 93.5, HHS 6
2026-09-02 | enum_E_17 | non_idp_NG008027_C07 | non_idp_NG008027_C07_R01 | 8b165203-c85a-40de-b0b8-a7207fa9590f | fcs_flat | Every food group given the same number of days | 7
2026-09-03 | enum_E_04 | non_idp_NG008007_C01 | non_idp_NG008007_C01_H02 | 92735833-05c6-465b-9892-896052104c43 | fcs_hhs_contradiction | Acceptable food consumption with severe hunger | FCS 93.5, HHS 6
2026-09-03 | enum_E_07 | non_idp_NG008009_C14 | non_idp_NG008009_C14_H02 | a3c37c15-298b-4469-82bc-fb8a10f8ec7d | gps_far | GPS point 4.9 km from the household | 4903
2026-09-03 | enum_E_10 | non_idp_NG008012_C12 | non_idp_NG008012_C12_H03 | 7b1d785a-b63d-4fb7-96df-41e823ea5800 | fcs_flat | Every food group given the same number of days | 0
2026-09-03 | enum_E_10 | non_idp_NG008012_C12 | non_idp_NG008012_C12_R01 | d544a45b-1fe8-4d26-a755-f56cafd260b4 | fcs_hhs_contradiction | Acceptable food consumption with severe hunger | FCS 93.5, HHS 6
2026-09-04 | enum_E_05 | non_idp_NG008007_R1_06 | non_idp_NG008007_R1_06_R01 | 1430114b-b514-4de6-afc7-3ecaa718fb67 | fcs_hhs_contradiction | Acceptable food consumption with severe hunger | FCS 40.0, HHS 4
2026-09-04 | enum_E_17 | non_idp_NG008027_C08 | non_idp_NG008027_C08_R03 | d572d9e1-d928-45ca-8d84-829818dff64b | gps_far | GPS point 1.4 km from the household | 1437
2026-09-05 | enum_E_03 | non_idp_NG008007_C13 | non_idp_NG008007_C13_H05 | 0324bb72-7de5-4f6d-b556-27ff9ae401aa | fcs_hhs_contradiction | Acceptable food consumption with severe hunger | FCS 38.0, HHS 6
2026-09-05 | enum_E_07 | non_idp_NG008009_C16 | non_idp_NG008009_C16_R01 | 89d1cdd8-ae13-4e7d-a644-85caba509759 | children_exceed_hh | More children than household members | 1 + 11 children, household of 9
2026-09-06 | enum_E_13 | non_idp_NG008020_C11 | non_idp_NG008020_C11_H03 | 2be332e7-62d9-40c6-a178-5b307d5fb769 | children_exceed_hh | More children than household members | 0 + 5 children, household of 3
2026-09-07 | enum_E_05 | non_idp_NG008007_R1_09 | non_idp_NG008007_R1_09_H06 | 07f0ece0-018d-437f-bbf7-414a30a24f36 | fcs_flat | Every food group given the same number of days | 0
2026-09-07 | enum_E_13 | non_idp_NG008020_C12 | non_idp_NG008020_C12_R01 | 74d5ddbe-29f5-461c-8bad-1b231dda9a65 | fcs_hhs_contradiction | Acceptable food consumption with severe hunger | FCS 93.5, HHS 6
2026-09-08 | enum_E_01 | non_idp_NG008004_R1_05 | non_idp_NG008004_R1_05_H04 | 1a5c3efa-521b-4678-89d7-af72e21098c4 | fcs_hhs_contradiction | Acceptable food consumption with severe hunger | FCS 39.0, HHS 4
2026-09-08 | enum_E_01 | non_idp_NG008004_R1_05 | non_idp_NG008004_R1_05_H04 | 2ab0ea70-30e9-4e1e-8e3a-7523cafe0b83 | fcs_hhs_contradiction | Acceptable food consumption with severe hunger | FCS 39.0, HHS 4
2026-09-08 | enum_E_11 | idp_NG008020_C02 | idp_NG008020_C02_H05 | 88c386f2-b85f-428e-8bf9-8906c909b55a | fcs_hhs_contradiction | Acceptable food consumption with severe hunger | FCS 51.5, HHS 4
2026-09-09 | enum_E_08 | idp_NG008012_C10 | idp_NG008012_C10_H06 | eb9174d6-ac50-497c-a54e-5c902d35a46c | fcs_hhs_contradiction | Acceptable food consumption with severe hunger | FCS 63.5, HHS 4
2026-09-09 | enum_E_11 | idp_NG008020_C03 | idp_NG008020_C03_H03 | 31b97f3d-dab4-463a-9c3e-335123ebdfe5 | fcs_hhs_contradiction | Acceptable food consumption with severe hunger | FCS 43.0, HHS 4
2026-09-10 | enum_E_07 | idp_NG008012_C11 | idp_NG008012_C11_H02 | 7e9eb167-741e-4c05-9dc8-b366ec38ebd9 | gps_far | GPS point 2.4 km from the household | 2432
2026-09-10 | enum_E_17 | non_idp_NG008027_C14 | non_idp_NG008027_C14_H05 | d0ec82a2-b294-4f27-a3a8-2c83953f221f | gps_far | GPS point 3.7 km from the household | 3690
2026-09-11 | enum_E_16 | idp_NG008027_C03 | idp_NG008027_C03_H05 | 026413f0-c1c2-4998-b019-f2477cc4ea3f | fcs_hhs_contradiction | Acceptable food consumption with severe hunger | FCS 42.5, HHS 4
2026-09-11 | enum_E_17 | non_idp_NG008027_C15 | non_idp_NG008027_C15_R01 | 00acf00e-ae84-4a2e-bb6b-1aa3231dc7ed | fcs_flat | Every food group given the same number of days | 7
2026-09-12 | enum_E_12 | idp_NG008020_C06 | idp_NG008020_C06_H02 | 382a7e37-7351-4717-862f-41da4d262783 | fcs_hhs_contradiction | Acceptable food consumption with severe hunger | FCS 41.0, HHS 4
2026-09-12 | enum_E_13 | non_idp_NG008023_C02 | non_idp_NG008023_C02_H06 | a1d44874-4ea3-480d-b61b-af3e02bcdcc4 | fcs_hhs_contradiction | Acceptable food consumption with severe hunger | FCS 93.5, HHS 6
2026-09-13 | enum_E_01 | non_idp_NG008004_R2_02 | non_idp_NG008004_R2_02_H02 | deade0f3-cb54-49e4-94c3-bf3fcf0e0b3d | gps_far | GPS point 3.0 km from the household | 3027
2026-09-13 | enum_E_15 | idp_NG008027_C04 | idp_NG008027_C04_H04 | 88b93d8e-100f-42ce-b585-0085f2db67fe | fcs_flat | Every food group given the same number of days | 0
2026-09-13 | enum_E_16 | idp_NG008027_C04 | idp_NG008027_C04_R01 | fe377402-d29b-4e59-9294-61d744e2ab1e | gps_far | GPS point 1.3 km from the household | 1310
2026-09-14 | enum_E_02 | non_idp_NG008004_R2_03 | non_idp_NG008004_R2_03_H01 | 6a5fe3b5-bdbc-4efc-a062-e90c7238ac1b | fcs_hhs_contradiction | Acceptable food consumption with severe hunger | FCS 93.5, HHS 6
2026-09-14 | enum_E_12 | idp_NG008020_C07 | idp_NG008020_C07_H03 | 912faa47-612d-4808-ae10-0b220d7b9224 | gps_far | GPS point 1.0 km from the household | 955
2026-09-14 | enum_E_12 | idp_NG008020_C07 | idp_NG008020_C07_H06 | bb36905c-425d-4655-b012-97aa4b0d26e3 | fcs_hhs_contradiction | Acceptable food consumption with severe hunger | FCS 37.0, HHS 4
2026-09-14 | enum_E_16 | idp_NG008027_C05 | idp_NG008027_C05_H01 | 0f631093-9fb8-4b35-a4ed-ca68ce20d17a | fcs_hhs_contradiction | Acceptable food consumption with severe hunger | FCS 93.5, HHS 6
2026-09-14 | enum_E_16 | idp_NG008027_C05 | idp_NG008027_C05_H04 | 4bc151d5-bbe0-4c40-b696-76552f07ce75 | fcs_flat | Every food group given the same number of days | 0
2026-09-14 | enum_E_16 | idp_NG008027_C05 | idp_NG008027_C05_H06 | b749d018-e0cd-42bc-a63c-eee5ee4f8be8 | fcs_hhs_contradiction | Acceptable food consumption with severe hunger | FCS 36.5, HHS 4
2026-09-14 | enum_E_16 | idp_NG008027_C05 | idp_NG008027_C05_H06 | b749d018-e0cd-42bc-a63c-eee5ee4f8be8 | attending_exceed_school_age | More children attending school than of school age | 5
2026-09-15 | enum_E_05 | non_idp_NG008007_R2_03 | non_idp_NG008007_R2_03_R01 | 49acf8b3-b146-48fc-81e5-8cf97c525324 | fcs_hhs_contradiction | Acceptable food consumption with severe hunger | FCS 93.5, HHS 6
2026-09-15 | enum_E_17 | non_idp_NG008027_C17 | non_idp_NG008027_C17_H01 | 536eee61-c270-4dd6-a175-648f7e03a556 | fcs_flat | Every food group given the same number of days | 0
2026-09-17 | enum_E_15 | idp_NG008027_C08 | idp_NG008027_C08_H03 | 0cf15e61-0df4-488e-90b9-91c04a163df2 | fcs_flat | Every food group given the same number of days | 0
2026-09-18 | enum_E_10 | non_idp_NG008018_C03 | non_idp_NG008018_C03_H04 | 71f9c8dc-2b62-423e-92cf-274158f22db3 | fcs_hhs_contradiction | Acceptable food consumption with severe hunger | FCS 93.5, HHS 6
2026-09-21 | enum_E_12 | non_idp_NG008018_R2_01 | non_idp_NG008018_R2_01_R03 | 353704a1-6a51-409f-84c8-252d8fba6489 | children_exceed_hh | More children than household members | 1 + 7 children, household of 6
2026-09-22 | enum_E_15 | non_idp_NG008023_R2_02 | non_idp_NG008023_R2_02_H06 | bf8b16e5-2744-4c51-ab51-72d23fc35945 | fcs_hhs_contradiction | Acceptable food consumption with severe hunger | FCS 40.0, HHS 4
2026-09-22 | enum_E_16 | non_idp_NG008023_R2_02 | non_idp_NG008023_R2_02_H04 | 60d9c45b-c8f9-4a17-ae35-9a4679108a50 | gps_far | GPS point 4.7 km from the household | 4671

## Removed
Interviews removed from the dataset, and why
Synthetic data – not real findings
date | enumerator_id | cluster_id | household_id | _uuid | check_id | reason
2026-08-18 | enum_E_05 | non_idp_NG008007_C17 | non_idp_NG008007_C17_R01 | c98aff4b-d2bc-4602-91c6-627ebfd4fd69 | C04 | Interview took 8 minutes
2026-08-19 | enum_E_08 | non_idp_NG008009_C05 | non_idp_NG008009_C05_H01 | 9f692acb-d11e-4a8c-a231-af4fbf9896b3 | C04 | Interview took 8 minutes
2026-08-20 | enum_E_05 | idp_NG008009_C02 | idp_NG008009_C02_H01 | 27e7a6d1-7a95-4149-844d-89dbe2c94692 | C04 | Interview took 10 minutes
2026-08-20 | enum_E_05 | idp_NG008009_C02 | idp_NG008009_C02_H03 | 5d7b3092-9ecf-4063-9b57-3acc946ae54c | C01 | Respondent did not consent
2026-08-22 | enum_E_04 | non_idp_NG008006_C15 | non_idp_NG008006_C15_H04 | ca50f056-0bca-4e8b-8bcd-0d15156fd0af | C01 | Respondent did not consent
2026-08-22 | enum_E_13 | idp_NG008020_C95 | idp_NG008020_C11_H06 | 61197511-502a-4411-9f2b-e2b9bd49a115 | C05 | Cluster code not in the sample
2026-08-22 | enum_E_18 | idp_NG008027_C10 | idp_NG008027_C10_H05 | 3aa8dcc1-03d5-49ab-ab62-77bf60ee0079 | C04 | Interview took 6 minutes
2026-08-23 | enum_E_18 | idp_NG008027_C11 | idp_NG008027_C11_H06 | 195baca8-6c10-44e3-9949-66225d21ee16 | C04 | Interview took 4 minutes
2026-08-24 | enum_E_02 | non_idp_NG008004_C04 | non_idp_NG008004_C04_H03 | 78b9de22-6de9-4d19-8444-0d10451f1808 | C02 | Same submission uploaded more than once
2026-08-24 | enum_E_09 | non_idp_NG008012_C06 | non_idp_NG008012_C06_H04 | eba6db5d-cd04-4a41-a860-65fee8e5b326 | C04 | Interview took 8 minutes
2026-08-25 | enum_E_10 | non_idp_NG008004_C02 | non_idp_NG008004_C02_H02 | 7b18b9ec-b2dc-46a6-b34c-449b7d5dfc7e | C06 | Cluster had been reported inaccessible
2026-08-25 | enum_E_14 | non_idp_NG008020_C01 | non_idp_NG008020_C01_H04 | c6d86d32-d337-4359-b8dc-2fe36204efd4 | C01 | Respondent did not consent
2026-08-26 | enum_E_02 | non_idp_NG008004_C12 | non_idp_NG008004_C12_H03 | 7b2a5d5e-9392-4d36-9af4-0cf5c7de41b0 | C01 | Respondent did not consent
2026-08-26 | enum_E_06 | non_idp_NG008004_C02 | non_idp_NG008004_C02_H03 | b82a5723-c4a2-4bb3-ad24-b18633905cb4 | C06 | Cluster had been reported inaccessible
2026-08-26 | enum_E_06 | idp_NG008009_C05 | idp_NG008009_C05_H05 | 28ff4934-6527-45f0-a372-664b01491df9 | C04 | Interview took 9 minutes
2026-08-26 | enum_E_17 | non_idp_NG008027_C01 | non_idp_NG008027_C01_H04 | 5cfe8883-21b3-468b-afda-5db7b944e864 | C04 | Interview took 4 minutes
2026-08-27 | enum_E_03 | idp_NG008007_C11 | idp_NG008007_C11_H03 | 4618fdde-eb95-4471-b57f-eef563f68d05 | C04 | Interview took 9 minutes
2026-08-28 | enum_E_07 | non_idp_NG008004_C02 | non_idp_NG008004_C02_H04 | 6a48ab69-0328-406c-83a5-13fd6f9b4ecb | C06 | Cluster had been reported inaccessible
2026-08-28 | enum_E_14 | non_idp_NG008020_C03 | non_idp_NG008020_C03_H02 | 0a92fb7d-26dd-4903-a605-cc1be22244ff | C01 | Respondent did not consent
2026-08-28 | enum_E_14 | non_idp_NG008020_C03 | non_idp_NG008020_C03_R01 | 12ae0f7e-05c4-454a-819a-f6d7a3a43e66 | C03 | Household already interviewed in an earlier submission
2026-08-29 | enum_E_07 | non_idp_NG008009_C10 | non_idp_NG008009_C10_H04 | 0de4b2eb-2b78-461c-8da8-24a40d1eee2c | C04 | Interview took 8 minutes
2026-08-29 | enum_E_12 | non_idp_NG008018_C06 | non_idp_NG008018_C06_H06 | e6363dc6-273a-4114-b743-8cae9076552d | C02 | Same submission uploaded more than once
2026-08-29 | enum_E_17 | non_idp_NG008027_C04 | non_idp_NG008027_C04_H03 | 934f2647-7c27-4ca8-96bb-9c0b679475e3 | C01 | Respondent did not consent
2026-08-29 | enum_E_17 | non_idp_NG008027_C04 | non_idp_NG008027_C04_H06 | c924c943-10c8-4d18-8841-30b297ecea35 | C04 | Interview took 6 minutes
2026-08-30 | enum_E_03 | idp_NG008007_C13 | idp_NG008007_C13_H04 | 6d1108d6-36bc-42fa-ada3-e83943abab5a | C03 | Household already interviewed in an earlier submission
2026-08-30 | enum_E_17 | non_idp_NG008027_C05 | non_idp_NG008027_C05_H03 | c7e2caa1-aafe-4b42-929a-d834bfe7aef3 | C01 | Respondent did not consent
2026-08-31 | enum_E_04 | idp_NG008007_C14 | idp_NG008007_C14_H05 | a41b1430-f7bd-43fc-950f-61cd89bd4121 | C02 | Same submission uploaded more than once
2026-08-31 | enum_E_05 | non_idp_NG008009_C01 | non_idp_NG008009_C01_H02 | 068cb196-c86f-43ca-af70-8584bb554457 | C04 | Interview took 11 minutes
2026-08-31 | enum_E_07 | non_idp_NG008009_C11 | non_idp_NG008009_C11_H02 | 3febb23f-c5e2-404a-8c04-c9f8de0116ce | C04 | Interview took 10 minutes
2026-08-31 | enum_E_16 | non_idp_NG008023_C08 | non_idp_NG008023_C08_H01 | 8a704f8a-2bbc-43c6-8c03-81bc36e3e865 | C04 | Interview took 7 minutes
2026-08-31 | enum_E_16 | non_idp_NG008023_C08 | non_idp_NG008023_C08_H02 | 896cb7a0-8cef-4f3f-a5d3-7b44ee6455f4 | C04 | Interview took 7 minutes
2026-09-01 | enum_E_03 | idp_NG008007_C15 | idp_NG008007_C15_H02 | ef6aabb2-0369-4d87-8ee5-4f4b40bbeb55 | C04 | Interview took 11 minutes
2026-09-01 | enum_E_07 | non_idp_NG008009_C12 | non_idp_NG008009_C12_H05 | a61f7cd9-e998-4ede-9436-a520db7e712f | C04 | Interview took 9 minutes
2026-09-01 | enum_E_09 | non_idp_NG008012_C10 | non_idp_NG008012_C10_R01 | f94a3d18-0a92-40c4-be3f-81f7ea8d22ea | C04 | Interview took 8 minutes
2026-09-01 | enum_E_17 | non_idp_NG008027_C06 | non_idp_NG008027_C06_H06 | 24bd4283-4ea7-4486-a518-9b72654aad09 | C04 | Interview took 9 minutes
2026-09-02 | enum_E_12 | non_idp_NG008018_C10 | non_idp_NG008018_C10_H06 | 5edecfaa-9991-42e2-bfcc-b13dc41b02aa | C04 | Interview took 11 minutes
2026-09-02 | enum_E_14 | non_idp_NG008020_C09 | non_idp_NG008020_C09_H01 | 7d4b7fc4-b7b6-4954-84e2-b23edde632f3 | C04 | Interview took 6 minutes
2026-09-03 | enum_E_01 | non_idp_NG008006_C12 | non_idp_NG008006_C12_H06 | a44e1ab3-a7e7-4b21-b3a4-cf6a208f8e89 | C04 | Interview took 8 minutes
2026-09-03 | enum_E_02 | non_idp_NG008006_C12 | non_idp_NG008006_C12_H01 | fedfc672-cbdd-4985-b9bf-2c1059a3f02a | C04 | Interview took 10 minutes
2026-09-03 | enum_E_05 | non_idp_NG008007_R1_02 | non_idp_NG008007_R1_02_H01 | 04ed4a1b-34cb-43f9-b3e5-e8c6e1989e13 | C01 | Respondent did not consent
2026-09-03 | enum_E_08 | non_idp_NG008009_C14 | non_idp_NG008009_C14_H01 | 9ceb6031-8b9b-43a3-9f0f-1311377c6e29 | C03 | Household already interviewed in an earlier submission
2026-09-03 | enum_E_09 | non_idp_NG008012_C12 | non_idp_NG008012_C12_R02 | 67cd074f-177e-4377-b23e-5a78f7770e1a | C04 | Interview took 8 minutes
2026-09-03 | enum_E_13 | non_idp_NG008020_C10 | non_idp_NG008020_C10_H05 | 51e9c75d-5986-468f-b439-b784a3bbabc0 | C04 | Interview took 7 minutes
2026-09-04 | enum_E_11 | non_idp_NG008018_C12 | non_idp_NG008018_C12_H04 | 53c1d75e-ab44-4e33-8427-9660abba39cd | C04 | Interview took 6 minutes
2026-09-04 | enum_E_18 | non_idp_NG008027_C97 | non_idp_NG008027_C08_H04 | 7887a043-c9e6-4491-a1f1-7db43c96f1aa | C05 | Cluster code not in the sample
2026-09-04 | enum_E_18 | non_idp_NG008027_C08 | non_idp_NG008027_C08_R01 | 8ae6a11d-8e38-45a8-9288-97c4ae3473ab | C01 | Respondent did not consent
2026-09-05 | enum_E_02 | non_idp_NG008004_R1_02 | non_idp_NG008004_R1_02_H04 | 1834af42-e1ec-4958-b6cd-cbb6bc9d3469 | C04 | Interview took 7 minutes
2026-09-05 | enum_E_05 | non_idp_NG008007_R1_07 | non_idp_NG008007_R1_07_H05 | 73fda7f5-35e7-45e1-8548-7d2b2ce78162 | C03 | Household already interviewed in an earlier submission
2026-09-05 | enum_E_07 | non_idp_NG008009_C16 | non_idp_NG008009_C16_H03 | 12193437-ea70-4004-8e15-3d4332aaf6e1 | C04 | Interview took 9 minutes
2026-09-05 | enum_E_15 | non_idp_NG008023_C15 | non_idp_NG008023_C15_H05 | d43c6039-b622-4087-91fd-b542020dd587 | C04 | Interview took 11 minutes
2026-09-06 | enum_E_03 | non_idp_NG008007_C14 | non_idp_NG008007_C14_H03 | 7be02f0e-1364-4427-aff7-1b33677c32b5 | C02 | Same submission uploaded more than once
2026-09-06 | enum_E_05 | non_idp_NG008007_R1_08 | non_idp_NG008007_R1_08_H03 | 93214f72-79b0-4d2b-aad0-164aa2efb932 | C01 | Respondent did not consent
2026-09-06 | enum_E_05 | non_idp_NG008007_R1_08 | non_idp_NG008007_R1_08_H04 | ea336944-d975-490c-a4ca-65c507fe687a | C04 | Interview took 9 minutes
2026-09-06 | enum_E_06 | non_idp_NG008007_R1_08 | non_idp_NG008007_R1_08_R01 | 3e5e6b08-08c9-4baa-a4b9-d70631eccd40 | C04 | Interview took 6 minutes
2026-09-06 | enum_E_14 | non_idp_NG008020_C92 | non_idp_NG008020_C11_H06 | 0291e5f4-8673-4cea-a57a-629e3f391929 | C05 | Cluster code not in the sample
2026-09-06 | enum_E_15 | non_idp_NG008023_C16 | non_idp_NG008023_C16_H02 | 4da3d020-fbef-485f-8880-9f73733b25a1 | C04 | Interview took 5 minutes
2026-09-07 | enum_E_07 | non_idp_NG008009_C17 | non_idp_NG008009_C17_H03 | 03ac857b-25e0-4865-86fb-d593ff7becec | C03 | Household already interviewed in an earlier submission
2026-09-08 | enum_E_01 | non_idp_NG008004_R1_05 | non_idp_NG008004_R1_05_H02 | 4c3a318b-231c-4c65-95c3-eaad04c5d5c9 | C04 | Interview took 4 minutes
2026-09-08 | enum_E_01 | non_idp_NG008004_R1_05 | non_idp_NG008004_R1_05_H04 | 2ab0ea70-30e9-4e1e-8e3a-7523cafe0b83 | C03 | Household already interviewed in an earlier submission
2026-09-08 | enum_E_13 | non_idp_NG008020_C13 | non_idp_NG008020_C13_H03 | c0b90f5c-ce3c-49e5-ba4b-55564dbe3fd2 | C01 | Respondent did not consent
2026-09-08 | enum_E_18 | non_idp_NG008027_C11 | non_idp_NG008027_C11_H02 | c2acd9bb-3f83-4359-ab58-7d05112467fc | C04 | Interview took 7 minutes
2026-09-08 | enum_E_18 | non_idp_NG008027_C11 | non_idp_NG008027_C11_H03 | 4fb25394-32b0-4af7-913d-b42b31df83be | C04 | Interview took 12 minutes
2026-09-08 | enum_E_18 | non_idp_NG008027_C11 | non_idp_NG008027_C11_H05 | e09c2008-7a53-421f-aaa5-036eebea1c0e | C04 | Interview took 5 minutes
2026-09-09 | enum_E_08 | idp_NG008012_C10 | idp_NG008012_C10_H04 | dad0c40e-cdbc-47e4-82dd-3ea69c9ad0fb | C04 | Interview took 5 minutes
2026-09-09 | enum_E_12 | idp_NG008020_C03 | idp_NG008020_C03_H04 | 59127dde-1658-4f96-9845-e8dd3e5695a3 | C04 | Interview took 12 minutes
2026-09-09 | enum_E_14 | non_idp_NG008020_C15 | non_idp_NG008020_C15_H03 | aad924fa-e052-470f-aef0-aaf53f3feab0 | C04 | Interview took 12 minutes
2026-09-10 | enum_E_17 | non_idp_NG008027_C14 | non_idp_NG008027_C14_H04 | 94bc82c2-da49-4ea6-aa52-02ffc817db9d | C04 | Interview took 6 minutes
2026-09-11 | enum_E_08 | idp_NG008012_C13 | idp_NG008012_C13_H05 | adec5671-d6b0-477c-809f-3ee1fd4bac4f | C04 | Interview took 4 minutes
2026-09-11 | enum_E_10 | idp_NG008018_C02 | idp_NG008018_C02_H02 | 0da668b3-8d10-47c6-b181-54a7f1d32c5a | C01 | Respondent did not consent
2026-09-13 | enum_E_02 | non_idp_NG008004_R2_02 | non_idp_NG008004_R2_02_H01 | 6241a125-6ea3-4b2e-8518-4ec43e65fb0b | C04 | Interview took 4 minutes
2026-09-13 | enum_E_03 | non_idp_NG008006_R1_06 | non_idp_NG008006_R1_06_H04 | 3920e9b6-717d-45ec-91d6-feab17aecfc9 | C01 | Respondent did not consent
2026-09-13 | enum_E_07 | non_idp_NG008004_C02 | non_idp_NG008004_C02_H01 | f47b64d7-0943-4029-bc82-dc2a93bcc317 | C06 | Cluster had been reported inaccessible
2026-09-14 | enum_E_01 | non_idp_NG008004_R2_03 | non_idp_NG008004_R2_03_H04 | 469bb6d1-7cd9-483b-aa42-14e37b7f0ca6 | C02 | Same submission uploaded more than once
2026-09-14 | enum_E_06 | non_idp_NG008007_R2_02 | non_idp_NG008007_R2_02_H01 | bff8eb4c-9e17-4ccf-b244-4c2f8fac2e84 | C04 | Interview took 5 minutes
2026-09-14 | enum_E_08 | non_idp_NG008012_C01 | non_idp_NG008012_C01_H02 | 304a6c38-51f5-40d5-9c07-b1b37a32bf4d | C01 | Respondent did not consent
2026-09-14 | enum_E_11 | non_idp_NG008004_C02 | non_idp_NG008004_C02_H06 | 4d85ec15-57ea-43db-ad5f-1f5f628c9f7a | C06 | Cluster had been reported inaccessible
2026-09-14 | enum_E_16 | idp_NG008027_C05 | idp_NG008027_C05_H03 | 785c83d3-af70-40eb-bb53-33d6d255aa3b | C01 | Respondent did not consent
2026-09-15 | enum_E_15 | idp_NG008027_C06 | idp_NG008027_C06_H01 | 05ab5961-f0d1-45d5-ac34-f3503a64856f | C02 | Same submission uploaded more than once
2026-09-16 | enum_E_02 | non_idp_NG008004_R2_05 | non_idp_NG008004_R2_05_H02 | 8f53b1d0-98b2-46a6-9b06-93fbf33e61f4 | C01 | Respondent did not consent
2026-09-16 | enum_E_02 | non_idp_NG008004_R2_05 | non_idp_NG008004_R2_05_H04 | 709da7c7-ffaf-423c-a730-a325529c5863 | C04 | Interview took 7 minutes
2026-09-16 | enum_E_08 | non_idp_NG008004_C02 | non_idp_NG008004_C02_H05 | 572bc9ef-3f2b-47a8-b866-c4426b05d9a8 | C06 | Cluster had been reported inaccessible
2026-09-16 | enum_E_11 | non_idp_NG008018_R1_01 | non_idp_NG008018_R1_01_H03 | 88bb787a-6f45-4884-9ed7-4ff389a0aad8 | C01 | Respondent did not consent
2026-09-16 | enum_E_13 | non_idp_NG008020_R1_04 | non_idp_NG008020_R1_04_H05 | 943fc4c1-f092-41af-96e4-d79adbadf9d3 | C01 | Respondent did not consent
2026-09-16 | enum_E_18 | non_idp_NG008027_R1_01 | non_idp_NG008027_R1_01_H05 | 7515d892-1292-4eef-bfcd-d7a0d20f380d | C04 | Interview took 10 minutes
2026-09-17 | enum_E_15 | idp_NG008027_C08 | idp_NG008027_C08_H06 | 0b88c61d-b47c-4041-bc55-3c3c515f8c0d | C04 | Interview took 9 minutes
2026-09-17 | enum_E_17 | idp_NG008027_R2_01 | idp_NG008027_R2_01_H06 | 05a2510c-7deb-486f-bbb8-d5eeaa25938b | C01 | Respondent did not consent
2026-09-17 | enum_E_18 | idp_NG008027_R2_01 | idp_NG008027_R2_01_R02 | 946bfe9c-63e8-4b90-9943-feb4e01dd5bf | C04 | Interview took 7 minutes
2026-09-18 | enum_E_15 | idp_NG008027_C09 | idp_NG008027_C09_H01 | 42aa51c0-0d17-4d05-ad84-7d3a2be85064 | C01 | Respondent did not consent
2026-09-19 | enum_E_10 | non_idp_NG008018_C04 | non_idp_NG008018_C04_H01 | 456f8cb8-9e32-42d8-9951-2162751cff5f | C01 | Respondent did not consent

## Enumerators
Enumerators
Synthetic data – not real findings
enumerator_id | interviews | median minutes | % repeated answers | interviews removed | interviews flagged | pattern
enum_E_01 | 68 | 43.6 | 5.9 | 4 | 4
enum_E_02 | 66 | 42.3 | 3 | 7 | 3
enum_E_03 | 67 | 39.2 | 3 | 5 | 4
enum_E_04 | 67 | 42.3 | 3 | 2 | 5
enum_E_05 | 74 | 42.7 | 0 | 8 | 9
enum_E_06 | 60 | 39.7 | 0 | 4 | 3
enum_E_07 | 75 | 40.8 | 0 | 7 | 5
enum_E_08 | 62 | 43.6 | 0 | 6 | 4
enum_E_09 | 60 | 40 | 0 | 3 | 1
enum_E_10 | 72 | 39.2 | 0 | 3 | 5
enum_E_11 | 67 | 44.3 | 0 | 3 | 2
enum_E_12 | 67 | 41 | 3 | 3 | 5
enum_E_13 | 74 | 44.6 | 0 | 4 | 6
enum_E_14 | 58 | 42.3 | 0 | 6 | 1
enum_E_15 | 70 | 41.5 | 2.9 | 5 | 3
enum_E_16 | 62 | 40.7 | 0 | 3 | 6
enum_E_17 | 63 | 39.8 | 0 | 7 | 8
enum_E_18 | 63 | 37.5 | 0 | 9 | 2

## Progress
Progress against target by LGA
Synthetic data – not real findings
adm1_name | adm2_name | pop_type | target | achieved | percent
Borno | Bayo | non_idp | 96 | 85 | 88.5
Borno | Chibok | non_idp | 102 | 99 | 97.1
Borno | Damboa | idp | 42 | 40 | 95.2
Borno | Damboa | non_idp | 102 | 86 | 84.3
Borno | Gubio | idp | 54 | 52 | 96.3
Borno | Gubio | non_idp | 102 | 96 | 94.1
Borno | Hawul | idp | 30 | 28 | 93.3
Borno | Hawul | non_idp | 102 | 99 | 97.1
Borno | Kwaya Kusar | idp | 30 | 29 | 96.7
Borno | Kwaya Kusar | non_idp | 102 | 100 | 98
Borno | Magumeri | idp | 72 | 70 | 97.2
Borno | Magumeri | non_idp | 102 | 91 | 89.2
Borno | Mobbar | non_idp | 102 | 92 | 90.2
Borno | Shani | idp | 78 | 67 | 85.9
Borno | Shani | non_idp | 102 | 93 | 91.2