## Summary
Data-quality digest: Partner G
Synthetic data – not real findings
Item | Value
Partner | Partner G
States | Kaduna
Data as of | 2026-09-27
Submissions received | 1155
Interviews kept | 1058
Interviews removed | 97
Values corrected | 10
Interviews flagged for follow-up | 57
Households targeted | 1038
Households achieved | 1058
Progress against target | 101.9%

## Follow up
Interviews flagged: please check with the enumerator
Synthetic data – not real findings
date | enumerator_id | cluster_id | household_id | _uuid | check | issue | value
2026-08-18 | enum_G_08 | non_idp_NG019003_C04 | non_idp_NG019003_C04_H01 | 82525189-20aa-4a47-9e0c-f79c576f1f1a | fcs_flat | Every food group given the same number of days | 0
2026-08-20 | enum_G_03 | non_idp_NG019001_C15 | non_idp_NG019001_C15_H02 | 0c654676-c2c7-4b35-8e1b-6bc29079e081 | fcs_hhs_contradiction | Acceptable food consumption with severe hunger | FCS 49.5, HHS 4
2026-08-20 | enum_G_15 | idp_NG019011_C11 | idp_NG019011_C11_H06 | 16bbbc42-173d-4221-912b-fd05af342420 | fcs_hhs_contradiction | Acceptable food consumption with severe hunger | FCS 36.5, HHS 4
2026-08-21 | enum_G_07 | non_idp_NG019003_C09 | non_idp_NG019003_C09_H06 | bc5489ec-b928-488b-bfee-78582c6c57bb | fcs_flat | Every food group given the same number of days | 7
2026-08-21 | enum_G_07 | non_idp_NG019003_C09 | non_idp_NG019003_C09_H06 | bc5489ec-b928-488b-bfee-78582c6c57bb | fcs_hhs_contradiction | Acceptable food consumption with severe hunger | FCS 112.0, HHS 4
2026-08-22 | enum_G_11 | non_idp_NG019009_C06 | non_idp_NG019009_C06_H02 | 9bbfbd03-67c4-4930-bcd7-b7342a1447b3 | gps_far | GPS point 0.8 km from the household | 833
2026-08-22 | enum_G_15 | idp_NG019011_C12 | idp_NG019011_C12_H05 | f7c958f9-bc6d-477f-bac7-45e9b1127e47 | gps_far | GPS point 1.8 km from the household | 1811
2026-08-24 | enum_G_11 | non_idp_NG019009_C08 | non_idp_NG019009_C08_R01 | 467ad59b-324c-44af-84ce-07641af386a3 | fcs_flat | Every food group given the same number of days | 7
2026-08-24 | enum_G_12 | non_idp_NG019009_C08 | non_idp_NG019009_C08_H02 | f08c460c-035b-48b5-8ac1-25a838b907bf | fcs_flat | Every food group given the same number of days | 7
2026-08-25 | enum_G_03 | non_idp_NG019002_C09 | non_idp_NG019002_C09_H03 | 766878de-ac54-4aa4-9cd2-85a87abb5f34 | gps_far | GPS point 1.5 km from the household | 1524
2026-08-25 | enum_G_05 | idp_NG019003_C03 | idp_NG019003_C03_H06 | 752bfba9-bf22-4288-83ef-5f62af606ae7 | fcs_hhs_contradiction | Acceptable food consumption with severe hunger | FCS 44.5, HHS 6
2026-08-25 | enum_G_14 | non_idp_NG019010_C06 | non_idp_NG019010_C06_H02 | 91831a0c-cb61-48cc-b8b9-6f6845ec1014 | fcs_hhs_contradiction | Acceptable food consumption with severe hunger | FCS 39.0, HHS 4
2026-08-27 | enum_G_09 | idp_NG019004_C12 | idp_NG019004_C12_R01 | 617ef4d6-a4db-4fa7-b492-31777b16685e | fcs_hhs_contradiction | Acceptable food consumption with severe hunger | FCS 39.0, HHS 6
2026-08-27 | enum_G_15 | non_idp_NG019011_C02 | non_idp_NG019011_C02_H01 | 79c64b85-62df-494f-a66e-1846383aca81 | fcs_hhs_contradiction | Acceptable food consumption with severe hunger | FCS 59.0, HHS 4
2026-08-27 | enum_G_15 | non_idp_NG019011_C02 | non_idp_NG019011_C02_H03 | e7dfb1a6-f18c-41dd-a401-850de0153875 | gps_far | GPS point 3.5 km from the household | 3474
2026-08-28 | enum_G_01 | idp_NG019001_C02 | idp_NG019001_C02_H06 | 98f163fd-a944-4e4f-9e9c-23eaa7f9bb6f | children_exceed_hh | More children than household members | 0 + 5 children, household of 3
2026-08-28 | enum_G_02 | idp_NG019001_C02 | idp_NG019001_C02_H01 | ced8c7cc-3fb2-4f5b-a133-6b17d913744f | fcs_hhs_contradiction | Acceptable food consumption with severe hunger | FCS 93.5, HHS 6
2026-08-28 | enum_G_08 | non_idp_NG019003_C15 | non_idp_NG019003_C15_H06 | 0f46ff1e-ff85-41ed-9f26-4fe28d6c555b | fcs_flat | Every food group given the same number of days | 7
2026-08-28 | enum_G_09 | non_idp_NG019004_C04 | non_idp_NG019004_C04_R02 | 5047131a-7bdc-45fd-a05e-21a855035964 | children_exceed_hh | More children than household members | 0 + 8 children, household of 5
2026-08-29 | enum_G_08 | non_idp_NG019003_C16 | non_idp_NG019003_C16_R01 | ae98942c-6911-40b4-8a83-e4b27456367f | fcs_hhs_contradiction | Acceptable food consumption with severe hunger | FCS 93.5, HHS 6
2026-09-01 | enum_G_02 | idp_NG019001_C06 | idp_NG019001_C06_R01 | caa7c3e6-1671-417f-a968-206cdd4113d1 | gps_far | GPS point 4.9 km from the household | 4931
2026-09-01 | enum_G_03 | non_idp_NG019002_C17 | non_idp_NG019002_C17_H02 | 7cb2ac29-f953-4b0d-8eb0-446138d4e217 | children_exceed_hh | More children than household members | 1 + 4 children, household of 4
2026-09-01 | enum_G_10 | non_idp_NG019004_C12 | non_idp_NG019004_C12_R01 | 927bc6d0-1e14-42d4-a86f-25df74c193c8 | fcs_flat | Every food group given the same number of days | 7
2026-09-02 | enum_G_01 | idp_NG019001_C07 | idp_NG019001_C07_H04 | 81df5a7a-2edf-4cfc-b994-590390be545e | fcs_hhs_contradiction | Acceptable food consumption with severe hunger | FCS 93.5, HHS 6
2026-09-02 | enum_G_05 | idp_NG019003_C06 | idp_NG019003_C06_H06 | ce3a099c-d457-4802-be7d-401de5f192b3 | fcs_hhs_contradiction | Acceptable food consumption with severe hunger | FCS 36.0, HHS 5
2026-09-03 | enum_G_01 | idp_NG019001_C08 | idp_NG019001_C08_H05 | 86772804-3f3f-45d7-996e-f37411365ad0 | fcs_hhs_contradiction | Acceptable food consumption with severe hunger | FCS 37.5, HHS 4
2026-09-03 | enum_G_09 | non_idp_NG019004_C14 | non_idp_NG019004_C14_H06 | 6ebe4b61-432d-41e3-b05a-fb1d74694be0 | attending_exceed_school_age | More children attending school than of school age | 4
2026-09-03 | enum_G_12 | non_idp_NG019009_C14 | non_idp_NG019009_C14_H01 | 3e2be18a-1b54-4890-9415-24c67689ccd0 | gps_far | GPS point 3.8 km from the household | 3779
2026-09-04 | enum_G_02 | idp_NG019001_C09 | idp_NG019001_C09_H05 | fba1765c-edfb-4929-bd24-c0c11647d840 | fcs_hhs_contradiction | Acceptable food consumption with severe hunger | FCS 36.5, HHS 4
2026-09-04 | enum_G_11 | non_idp_NG019009_C15 | non_idp_NG019009_C15_H04 | d122986a-9c9d-4001-be09-1affc04a19ee | gps_far | GPS point 0.9 km from the household | 897
2026-09-05 | enum_G_06 | idp_NG019003_C08 | idp_NG019003_C08_H03 | 37bf0300-47c2-4c7b-a5e2-028db5dfee95 | fcs_hhs_contradiction | Acceptable food consumption with severe hunger | FCS 38.5, HHS 4
2026-09-05 | enum_G_07 | idp_NG019004_C01 | idp_NG019004_C01_H05 | 91659611-3787-4643-8ee0-610daf706608 | fcs_hhs_contradiction | Acceptable food consumption with severe hunger | FCS 39.0, HHS 6
2026-09-05 | enum_G_15 | non_idp_NG019011_C10 | non_idp_NG019011_C10_H04 | 0a4f2947-514d-4876-a510-5d97a90e71e6 | gps_far | GPS point 4.8 km from the household | 4829
2026-09-06 | enum_G_07 | idp_NG019004_C02 | idp_NG019004_C02_R01 | e071b4fb-f28f-41b8-991b-75b8be332813 | gps_far | GPS point 4.0 km from the household | 4030
2026-09-06 | enum_G_08 | idp_NG019004_C02 | idp_NG019004_C02_H01 | b8e00d0e-e4f0-4c6b-9971-cd64183a5124 | fcs_hhs_contradiction | Acceptable food consumption with severe hunger | FCS 40.0, HHS 5
2026-09-06 | enum_G_15 | non_idp_NG019011_C11 | non_idp_NG019011_C11_H02 | 09376688-d7ed-4f75-ba49-aa251b524868 | gps_far | GPS point 4.9 km from the household | 4941
2026-09-07 | enum_G_03 | non_idp_NG019002_R1_02 | non_idp_NG019002_R1_02_H05 | b3fa36c2-0435-43f9-aa43-a93428d38665 | fcs_hhs_contradiction | Acceptable food consumption with severe hunger | FCS 51.0, HHS 4
2026-09-08 | enum_G_04 | non_idp_NG019002_R1_03 | non_idp_NG019002_R1_03_H02 | 1e72cc7f-0f4f-4c02-858c-5bc9f6abe1cc | fcs_hhs_contradiction | Acceptable food consumption with severe hunger | FCS 38.0, HHS 4
2026-09-08 | enum_G_11 | idp_NG019010_C12 | idp_NG019010_C12_H04 | 276e58f1-dc79-4bab-87ff-98a6f728b609 | fcs_hhs_contradiction | Acceptable food consumption with severe hunger | FCS 93.5, HHS 6
2026-09-09 | enum_G_04 | non_idp_NG019002_R1_05 | non_idp_NG019002_R1_05_R01 | fb82cf4f-215f-4b5a-a57c-4ff6e4159466 | fcs_flat | Every food group given the same number of days | 7
2026-09-09 | enum_G_04 | non_idp_NG019002_R1_05 | non_idp_NG019002_R1_05_R01 | fb82cf4f-215f-4b5a-a57c-4ff6e4159466 | fcs_hhs_contradiction | Acceptable food consumption with severe hunger | FCS 112.0, HHS 5
2026-09-09 | enum_G_10 | non_idp_NG019004_R1_04 | non_idp_NG019004_R1_04_H06 | 6540171d-9220-4360-b8c9-c5165b42a7df | gps_far | GPS point 3.1 km from the household | 3120
2026-09-09 | enum_G_12 | non_idp_NG019010_C02 | non_idp_NG019010_C02_H04 | 9cf4f291-f721-4702-8015-defece86636d | gps_far | GPS point 3.6 km from the household | 3611
2026-09-10 | enum_G_08 | idp_NG019004_C04 | idp_NG019004_C04_H06 | f194ec70-eb60-495b-a0c8-c7e72dcf6cfa | fcs_hhs_contradiction | Acceptable food consumption with severe hunger | FCS 93.5, HHS 6
2026-09-10 | enum_G_12 | non_idp_NG019010_C03 | non_idp_NG019010_C03_H04 | 876e7ef6-17e4-4f8f-961f-72c78e77ab2f | fcs_flat | Every food group given the same number of days | 7
2026-09-11 | enum_G_02 | non_idp_NG019001_C03 | non_idp_NG019001_C03_H01 | 4055f9b1-abb1-43c9-a0f6-b4e4db9c8473 | attending_exceed_school_age | More children attending school than of school age | 6
2026-09-11 | enum_G_04 | non_idp_NG019002_R1_07 | non_idp_NG019002_R1_07_H02 | 6c22c09f-7313-4031-af9a-27e5c986f08c | fcs_hhs_contradiction | Acceptable food consumption with severe hunger | FCS 93.5, HHS 6
2026-09-11 | enum_G_11 | non_idp_NG019010_C04 | non_idp_NG019010_C04_H05 | 5d7d05ae-56d6-483c-9ce6-30c55bb83d10 | gps_far | GPS point 4.8 km from the household | 4811
2026-09-11 | enum_G_14 | idp_NG019011_C09 | idp_NG019011_C09_H05 | 4b70db9a-db56-407e-988e-059518a04ae1 | fcs_flat | Every food group given the same number of days | 7
2026-09-13 | enum_G_02 | non_idp_NG019001_C07 | non_idp_NG019001_C07_H05 | fe6a17b3-cec9-44cd-aff6-d814e9d39974 | fcs_flat | Every food group given the same number of days | 0
2026-09-14 | enum_G_05 | idp_NG019003_C15 | idp_NG019003_C15_H06 | ac448279-5a0e-444c-b7bf-7693f66be343 | fcs_hhs_contradiction | Acceptable food consumption with severe hunger | FCS 42.0, HHS 4
2026-09-15 | enum_G_10 | non_idp_NG019004_R2_03 | non_idp_NG019004_R2_03_H06 | dd70d93c-f8c1-4243-af57-ea6f18aa03d8 | fcs_hhs_contradiction | Acceptable food consumption with severe hunger | FCS 50.5, HHS 4
2026-09-16 | enum_G_01 | non_idp_NG019001_C10 | non_idp_NG019001_C10_R01 | 3f7fe7f5-50f0-4de4-8a92-fe2baaa3139c | fcs_hhs_contradiction | Acceptable food consumption with severe hunger | FCS 37.0, HHS 6
2026-09-16 | enum_G_02 | non_idp_NG019001_C10 | non_idp_NG019001_C10_H05 | 0d454d37-35f7-4b09-8ea2-7fe0055fb5e5 | fcs_flat | Every food group given the same number of days | 7
2026-09-16 | enum_G_14 | non_idp_NG019010_R1_02 | non_idp_NG019010_R1_02_H04 | c9a6a09f-230f-47e7-ac6c-4abdd6a88cc5 | fcs_hhs_contradiction | Acceptable food consumption with severe hunger | FCS 93.5, HHS 6
2026-09-17 | enum_G_07 | idp_NG019004_C09 | idp_NG019004_C09_H05 | 909602c9-65d7-440a-9e2e-15be59278d0c | fcs_hhs_contradiction | Acceptable food consumption with severe hunger | FCS 93.5, HHS 6
2026-09-20 | enum_G_13 | non_idp_NG019010_R1_06 | non_idp_NG019010_R1_06_H02 | 066ec116-ff9f-4509-9888-a0841a469b09 | gps_far | GPS point 1.7 km from the household | 1670
2026-09-20 | enum_G_13 | non_idp_NG019010_R1_06 | non_idp_NG019010_R1_06_H03 | 41b63ebe-2657-48ab-a162-662738ab8797 | children_exceed_hh | More children than household members | 1 + 11 children, household of 9
2026-09-23 | enum_G_05 | non_idp_NG019002_R2_01 | non_idp_NG019002_R2_01_H02 | 3fcd66fc-8535-497e-90f4-37da55ca0246 | fcs_hhs_contradiction | Acceptable food consumption with severe hunger | FCS 36.0, HHS 4

## Removed
Interviews removed from the dataset, and why
Synthetic data – not real findings
date | enumerator_id | cluster_id | household_id | _uuid | check_id | reason
2026-08-18 | enum_G_11 | non_idp_NG019009_C02 | non_idp_NG019009_C02_H04 | 5233998b-436d-4efb-9bd1-08b761ace7ad | C01 | Respondent did not consent
2026-08-19 | enum_G_12 | non_idp_NG019009_C95 | non_idp_NG019009_C03_H05 | 797c1d65-6b8c-4b4b-b508-d42db8fea69b | C05 | Cluster code not in the sample
2026-08-19 | enum_G_15 | idp_NG019011_C10 | idp_NG019011_C10_R01 | b0968cab-a0a8-4b53-908b-206c59c35bd7 | C01 | Respondent did not consent
2026-08-19 | enum_G_16 | idp_NG019011_C10 | idp_NG019011_C10_H04 | 68107570-354d-40e0-bc57-557d71d043d6 | C01 | Respondent did not consent
2026-08-20 | enum_G_16 | idp_NG019011_C11 | idp_NG019011_C11_H05 | e2a82823-f04f-4a2a-9c90-7c0bc0a66b9b | C02 | Same submission uploaded more than once
2026-08-22 | enum_G_09 | idp_NG019004_C12 | idp_NG019004_C12_H04 | c71ca197-8629-40bd-917e-e74964addcfe | C04 | Interview took 12 minutes
2026-08-23 | enum_G_03 | non_idp_NG019002_C08 | non_idp_NG019002_C08_R03 | d4796907-2a3e-4647-b481-22aa7ab8496d | C04 | Interview took 8 minutes
2026-08-23 | enum_G_07 | non_idp_NG019003_C10 | non_idp_NG019003_C10_H04 | ea95c20b-f9d4-41c0-ba29-bbb741f6089e | C04 | Interview took 5 minutes
2026-08-23 | enum_G_08 | non_idp_NG019003_C10 | non_idp_NG019003_C10_H06 | 0b2733f6-4bad-4807-a91e-0ffbe278984a | C02 | Same submission uploaded more than once
2026-08-25 | enum_G_07 | non_idp_NG019003_C12 | non_idp_NG019003_C12_H05 | 5b217319-e4c3-4901-ab2d-21422e694b6e | C03 | Household already interviewed in an earlier submission
2026-08-26 | enum_G_12 | non_idp_NG019009_C09 | non_idp_NG019009_C09_H01 | 180d3549-7411-4561-965e-fe3951c6faac | C01 | Respondent did not consent
2026-08-26 | enum_G_13 | non_idp_NG019010_C07 | non_idp_NG019010_C07_H01 | 4d5cca6a-b5fa-4320-8b80-8661099a8f9c | C01 | Respondent did not consent
2026-08-26 | enum_G_15 | non_idp_NG019011_C01 | non_idp_NG019011_C01_H06 | 262fe423-488b-4563-a3fd-558f999718bb | C04 | Interview took 8 minutes
2026-08-27 | enum_G_01 | idp_NG019001_C01 | idp_NG019001_C01_H04 | b266418f-811d-407e-93f9-fbd15d2e6151 | C01 | Respondent did not consent
2026-08-27 | enum_G_02 | idp_NG019001_C01 | idp_NG019001_C01_H05 | a5e76e44-828e-4881-b478-f846b97182b5 | C01 | Respondent did not consent
2026-08-27 | enum_G_07 | non_idp_NG019003_C14 | non_idp_NG019003_C14_H03 | 91b2cd1c-34c8-4c0b-a8cc-15bbd4b45950 | C01 | Respondent did not consent
2026-08-27 | enum_G_15 | non_idp_NG019011_C02 | non_idp_NG019011_C02_H01 | 79c64b85-62df-494f-a66e-1846383aca81 | C04 | Interview took 10 minutes
2026-08-28 | enum_G_06 | idp_NG019003_C04 | idp_NG019003_C04_H06 | 78e09795-a611-43b1-a183-e72e861e3041 | C04 | Interview took 10 minutes
2026-08-28 | enum_G_07 | non_idp_NG019003_C15 | non_idp_NG019003_C15_H04 | f5b511c8-02c4-425c-90e9-763f5d3d1c5e | C04 | Interview took 6 minutes
2026-08-28 | enum_G_13 | non_idp_NG019004_R1_01 | non_idp_NG019004_R1_01_H03 | db2cf752-e07f-4ea6-9924-80d43bb8da0f | C06 | Cluster had been reported inaccessible
2026-08-29 | enum_G_09 | non_idp_NG019004_C05 | non_idp_NG019004_C05_R01 | a34a9ab7-e433-4f8a-8a95-953e4a89127f | C01 | Respondent did not consent
2026-08-29 | enum_G_13 | non_idp_NG019010_C09 | non_idp_NG019010_C09_H06 | 89d47996-500e-44c9-88ff-908a2572bd22 | C01 | Respondent did not consent
2026-08-30 | enum_G_09 | non_idp_NG019004_C10 | non_idp_NG019004_C10_H01 | 1ded508a-f864-4c5a-9efe-46f2a317d2dd | C01 | Respondent did not consent
2026-08-30 | enum_G_13 | non_idp_NG019010_C10 | non_idp_NG019010_C10_H02 | f03c72a4-0710-4b3a-b4e1-fff02729b663 | C04 | Interview took 9 minutes
2026-08-30 | enum_G_13 | non_idp_NG019004_R1_01 | non_idp_NG019004_R1_01_H02 | d6df926d-d644-4abb-8766-2f0614a76848 | C06 | Cluster had been reported inaccessible
2026-08-31 | enum_G_01 | non_idp_NG019004_R1_01 | non_idp_NG019004_R1_01_H06 | 88e10402-b4f6-4201-ab9c-d6c782fd6332 | C06 | Cluster had been reported inaccessible
2026-08-31 | enum_G_15 | non_idp_NG019004_R1_01 | non_idp_NG019004_R1_01_H04 | d6493bf7-ffe9-41a5-afb5-5bbaea8f4611 | C06 | Cluster had been reported inaccessible
2026-08-31 | enum_G_16 | non_idp_NG019011_C06 | non_idp_NG019011_C06_H02 | ae322ee6-65c6-49e2-89cd-7794205b3afd | C04 | Interview took 10 minutes
2026-08-31 | enum_G_16 | non_idp_NG019011_C99 | non_idp_NG019011_C06_H04 | d6332427-0df7-4325-9ffa-902d830c66f2 | C05 | Cluster code not in the sample
2026-09-01 | enum_G_04 | non_idp_NG019002_C17 | non_idp_NG019002_C17_R01 | ca5490d1-0771-4326-a17e-34a2372428f4 | C01 | Respondent did not consent
2026-09-01 | enum_G_08 | non_idp_NG019003_C17 | non_idp_NG019003_C17_H03 | ff08610f-2f67-4f85-a04a-c4fcf878cbd7 | C02 | Same submission uploaded more than once
2026-09-01 | enum_G_09 | non_idp_NG019004_C12 | non_idp_NG019004_C12_H04 | 4c497b2d-f25c-4def-895e-17b0797ea80b | C03 | Household already interviewed in an earlier submission
2026-09-01 | enum_G_13 | idp_NG019011_C01 | idp_NG019011_C01_H02 | 8762616a-8018-4e86-9509-e1bbc03cec72 | C01 | Respondent did not consent
2026-09-02 | enum_G_04 | non_idp_NG019001_R1_01 | non_idp_NG019001_R1_01_H01 | 3d074740-96de-45e1-bbe0-d3fe174d8afe | C04 | Interview took 5 minutes
2026-09-02 | enum_G_05 | idp_NG019003_C06 | idp_NG019003_C06_H04 | 52350370-2dc7-47b1-86f0-1a64b172e7c5 | C01 | Respondent did not consent
2026-09-02 | enum_G_10 | non_idp_NG019004_C13 | non_idp_NG019004_C13_H01 | 64edc995-a705-4c6e-9889-66aaf81b859b | C04 | Interview took 10 minutes
2026-09-02 | enum_G_16 | non_idp_NG019011_C07 | non_idp_NG019011_C07_R01 | 8f5fe86c-50eb-46e1-8692-c00437da1a20 | C01 | Respondent did not consent
2026-09-03 | enum_G_09 | non_idp_NG019004_C14 | non_idp_NG019004_C14_H02 | 6613e557-26fd-4c6f-8dec-d3bb96411ac4 | C02 | Same submission uploaded more than once
2026-09-03 | enum_G_10 | non_idp_NG019004_C14 | non_idp_NG019004_C14_H01 | 8756c080-34f5-497e-99b9-9683b292687c | C04 | Interview took 8 minutes
2026-09-04 | enum_G_06 | idp_NG019003_C07 | idp_NG019003_C07_H02 | d5f3aab1-6730-426d-9ce6-5fec5160f042 | C01 | Respondent did not consent
2026-09-04 | enum_G_13 | idp_NG019011_C96 | idp_NG019011_C04_H06 | 5b086ec0-95e4-4bf7-addf-92555897196d | C05 | Cluster code not in the sample
2026-09-04 | enum_G_14 | idp_NG019011_C04 | idp_NG019011_C04_H03 | 96077a2f-52b9-4239-b450-149a1cf5b737 | C04 | Interview took 5 minutes
2026-09-04 | enum_G_14 | idp_NG019011_C04 | idp_NG019011_C04_R02 | 7c179aef-f80a-4ea7-b1f6-7168d42d3d6f | C04 | Interview took 11 minutes
2026-09-05 | enum_G_06 | idp_NG019003_C08 | idp_NG019003_C08_H05 | 8888b66c-8d74-4ca1-b200-189cf367f719 | C04 | Interview took 4 minutes
2026-09-05 | enum_G_07 | idp_NG019004_C01 | idp_NG019004_C01_H03 | 775a778e-cff9-469e-96fd-710d2556a84b | C04 | Interview took 4 minutes
2026-09-05 | enum_G_12 | non_idp_NG019009_C16 | non_idp_NG019009_C16_H06 | 04a81564-d8db-47d5-97c4-3964cf286f0f | C01 | Respondent did not consent
2026-09-05 | enum_G_13 | idp_NG019011_C05 | idp_NG019011_C05_H06 | 752db6b4-dc10-4599-b291-c3aa207ea1b3 | C04 | Interview took 11 minutes
2026-09-05 | enum_G_14 | idp_NG019011_C97 | idp_NG019011_C05_R02 | a8771afd-d0b6-4d70-8de5-1e74900a8074 | C05 | Cluster code not in the sample
2026-09-05 | enum_G_16 | non_idp_NG019011_C10 | non_idp_NG019011_C10_H06 | 8ba81f2d-3efd-4c84-89bf-3906299e63ab | C01 | Respondent did not consent
2026-09-05 | enum_G_16 | non_idp_NG019011_C10 | non_idp_NG019011_C10_R01 | 17ce4c14-1347-4f82-8729-ed787de9f89f | C03 | Household already interviewed in an earlier submission
2026-09-07 | enum_G_02 | idp_NG019001_C12 | idp_NG019001_C12_H03 | 63f0eceb-46f4-4921-9a13-ae82b2b5a307 | C01 | Respondent did not consent
2026-09-07 | enum_G_02 | idp_NG019001_C12 | idp_NG019001_C12_H04 | 1be1886f-d22a-4e35-8cae-391b04d001cf | C01 | Respondent did not consent
2026-09-07 | enum_G_05 | idp_NG019003_C09 | idp_NG019003_C09_H02 | 7067969f-8a77-45b0-94e4-ad091103f224 | C01 | Respondent did not consent
2026-09-07 | enum_G_14 | idp_NG019011_C06 | idp_NG019011_C06_H05 | a7ab1a93-4d48-44cd-a2af-3eeccfa75199 | C01 | Respondent did not consent
2026-09-08 | enum_G_10 | non_idp_NG019004_R1_03 | non_idp_NG019004_R1_03_H06 | 27c9392c-9e23-4507-acd2-3f06b671fcfc | C01 | Respondent did not consent
2026-09-08 | enum_G_10 | non_idp_NG019004_R1_03 | non_idp_NG019004_R1_03_H05 | e87acc90-674e-4c84-a0c4-ffe0e51cb1fd | C03 | Household already interviewed in an earlier submission
2026-09-08 | enum_G_12 | idp_NG019010_C12 | idp_NG019010_C12_H01 | fe3b3e6f-072c-4a4b-8d04-96206ed0ac78 | C04 | Interview took 11 minutes
2026-09-08 | enum_G_16 | non_idp_NG019011_C13 | non_idp_NG019011_C13_H02 | 3491320f-29f9-41a2-81d8-52041cd4b7dc | C01 | Respondent did not consent
2026-09-09 | enum_G_01 | non_idp_NG019001_C01 | non_idp_NG019001_C01_H01 | 4c5fd306-f71b-4053-89ab-b2b9f804a07d | C04 | Interview took 10 minutes
2026-09-09 | enum_G_01 | non_idp_NG019001_C01 | non_idp_NG019001_C01_H03 | 04076ae2-e454-4249-b6a4-ce66b10abeaa | C01 | Respondent did not consent
2026-09-09 | enum_G_05 | idp_NG019003_C10 | idp_NG019003_C10_H06 | 402c38d7-ac53-4961-8f2e-216af2cf877d | C04 | Interview took 8 minutes
2026-09-09 | enum_G_12 | non_idp_NG019010_C02 | non_idp_NG019010_C02_H06 | 0ec20613-7062-4a1d-9168-ef98c30a7d4f | C04 | Interview took 8 minutes
2026-09-09 | enum_G_14 | idp_NG019011_C08 | idp_NG019011_C08_H02 | 62554722-f05a-4818-801f-27ed8ddb146b | C03 | Household already interviewed in an earlier submission
2026-09-10 | enum_G_05 | idp_NG019003_C11 | idp_NG019003_C11_H04 | 5bf99530-eb03-4fef-b70f-0f5f4f15e1b9 | C04 | Interview took 9 minutes
2026-09-10 | enum_G_11 | non_idp_NG019010_C03 | non_idp_NG019010_C03_R01 | 865ff030-5339-41e8-9a18-4706de37d606 | C01 | Respondent did not consent
2026-09-10 | enum_G_12 | non_idp_NG019010_C03 | non_idp_NG019010_C03_H03 | 778bd4b4-92b2-4116-abd0-32945dbe85b6 | C01 | Respondent did not consent
2026-09-11 | enum_G_01 | non_idp_NG019001_C03 | non_idp_NG019001_C03_H06 | 3679da35-41a2-4b7b-8f25-c30f05aa8123 | C01 | Respondent did not consent
2026-09-11 | enum_G_06 | idp_NG019003_C12 | idp_NG019003_C12_H03 | a77882f4-e881-4ed3-9ff0-1cf3c145b22b | C04 | Interview took 11 minutes
2026-09-11 | enum_G_07 | idp_NG019004_C05 | idp_NG019004_C05_H04 | 6412409b-4d7f-4109-aae0-82238454bfbc | C01 | Respondent did not consent
2026-09-11 | enum_G_11 | non_idp_NG019010_C04 | non_idp_NG019010_C04_H02 | 2fe1cb2a-dcfc-438f-8ac9-9f90023915ad | C01 | Respondent did not consent
2026-09-11 | enum_G_13 | idp_NG019011_C09 | idp_NG019011_C09_H03 | e1aff30f-264d-4c95-b421-6b581f3c87cc | C04 | Interview took 5 minutes
2026-09-12 | enum_G_06 | idp_NG019003_C13 | idp_NG019003_C13_H05 | bb6e89e1-4bd9-4950-84b5-c4833d2bc13d | C04 | Interview took 8 minutes
2026-09-13 | enum_G_02 | non_idp_NG019001_C07 | non_idp_NG019001_C07_H02 | 13e510d7-2bff-4281-8b22-d03d7bb63719 | C04 | Interview took 6 minutes
2026-09-13 | enum_G_06 | idp_NG019003_C14 | idp_NG019003_C14_H03 | e443faee-8c0c-4d85-b48b-41844dca3084 | C02 | Same submission uploaded more than once
2026-09-14 | enum_G_06 | idp_NG019003_C15 | idp_NG019003_C15_H05 | 77f0e140-5535-4520-8e5f-865f7ebb050d | C04 | Interview took 11 minutes
2026-09-15 | enum_G_01 | non_idp_NG019001_C09 | non_idp_NG019001_C09_H06 | b2ca9799-bb06-49b1-b33d-0fba33de9996 | C01 | Respondent did not consent
2026-09-15 | enum_G_01 | non_idp_NG019004_R1_01 | non_idp_NG019004_R1_01_H01 | d718c2b9-57cf-43a0-b2f3-e2fae7ba8ea2 | C06 | Cluster had been reported inaccessible
2026-09-15 | enum_G_06 | non_idp_NG019004_R1_01 | non_idp_NG019004_R1_01_H05 | 296f3cbc-8180-434b-a88d-621fe6d689c3 | C06 | Cluster had been reported inaccessible
2026-09-15 | enum_G_09 | non_idp_NG019004_R2_03 | non_idp_NG019004_R2_03_H04 | 80132fe1-7312-45cd-ab41-e56076d4286f | C02 | Same submission uploaded more than once
2026-09-15 | enum_G_13 | non_idp_NG019010_R1_C93 | non_idp_NG019010_R1_01_H04 | 1b40a403-8970-4622-8aae-99747679572a | C05 | Cluster code not in the sample
2026-09-15 | enum_G_14 | non_idp_NG019010_R1_01 | non_idp_NG019010_R1_01_H01 | 38b1b408-7ae8-4dd2-8acc-997c864b4cb5 | C04 | Interview took 12 minutes
2026-09-16 | enum_G_01 | non_idp_NG019001_C10 | non_idp_NG019001_C10_H04 | e04495fd-7cd5-4673-9dec-de0fafbfaab2 | C01 | Respondent did not consent
2026-09-16 | enum_G_05 | non_idp_NG019003_C90 | non_idp_NG019003_C01_H03 | 2fd9fca5-cbad-46eb-b720-747dc9c7b5da | C05 | Cluster code not in the sample
2026-09-16 | enum_G_06 | non_idp_NG019003_C01 | non_idp_NG019003_C01_H04 | 6dfe4a35-1e30-49e8-a2ed-f085668963f6 | C02 | Same submission uploaded more than once
2026-09-16 | enum_G_13 | non_idp_NG019010_R1_02 | non_idp_NG019010_R1_02_H03 | f64ac8b1-fdc8-46af-a837-60b1ca307589 | C04 | Interview took 9 minutes
2026-09-17 | enum_G_13 | non_idp_NG019010_R1_03 | non_idp_NG019010_R1_03_R03 | 2eb5a477-b005-47c3-bb55-723a0ca99e70 | C03 | Household already interviewed in an earlier submission
2026-09-17 | enum_G_14 | non_idp_NG019010_R1_03 | non_idp_NG019010_R1_03_R01 | 3b98a693-ee1f-4767-8cd5-0083f8195724 | C01 | Respondent did not consent
2026-09-17 | enum_G_15 | non_idp_NG019011_R2_01 | non_idp_NG019011_R2_01_H03 | 1110203a-3d6e-4ed5-a129-877da778d5d0 | C04 | Interview took 7 minutes
2026-09-18 | enum_G_05 | non_idp_NG019003_C02 | non_idp_NG019003_C02_H03 | 6a096cf1-b082-4182-8866-16e11defbc81 | C04 | Interview took 4 minutes
2026-09-18 | enum_G_08 | non_idp_NG019003_R1_01 | non_idp_NG019003_R1_01_H03 | 38221a76-cf4c-4f4d-bad8-40215a84e44d | C01 | Respondent did not consent
2026-09-18 | enum_G_14 | non_idp_NG019010_R1_04 | non_idp_NG019010_R1_04_H02 | ea4bd568-46f0-41e6-bb5b-d3674a5c8345 | C03 | Household already interviewed in an earlier submission
2026-09-19 | enum_G_08 | non_idp_NG019003_R2_01 | non_idp_NG019003_R2_01_H01 | 8286ad82-772b-4cbe-9ec8-d2c13296fde7 | C02 | Same submission uploaded more than once
2026-09-19 | enum_G_13 | non_idp_NG019010_R1_05 | non_idp_NG019010_R1_05_H01 | 5b380dd0-d969-46c5-a925-1d99b58c043d | C03 | Household already interviewed in an earlier submission
2026-09-19 | enum_G_14 | non_idp_NG019010_R1_05 | non_idp_NG019010_R1_05_H04 | e3c62fc9-4852-4876-9eef-9abb040948bf | C01 | Respondent did not consent
2026-09-22 | enum_G_06 | non_idp_NG019002_R1_08 | non_idp_NG019002_R1_08_R02 | 6eeb6b35-f19f-4178-8298-11cd0a5d05fd | C01 | Respondent did not consent
2026-09-24 | enum_G_06 | non_idp_NG019002_R2_02 | non_idp_NG019002_R2_02_H02 | 824a3a87-aa60-4dec-9d0d-e21ea39db2c7 | C04 | Interview took 7 minutes
2026-09-24 | enum_G_06 | non_idp_NG019002_R2_02 | non_idp_NG019002_R2_02_H03 | 46773004-a5b0-4b40-8051-92a25a96fd66 | C01 | Respondent did not consent

## Enumerators
Enumerators
Synthetic data – not real findings
enumerator_id | interviews | median minutes | % repeated answers | interviews removed | interviews flagged | pattern
enum_G_01 | 76 | 41.5 | 0 | 8 | 4
enum_G_02 | 60 | 43 | 0 | 4 | 6
enum_G_03 | 69 | 40.7 | 0 | 1 | 4
enum_G_04 | 65 | 44.9 | 0 | 2 | 3
enum_G_05 | 65 | 41.9 | 0 | 6 | 4
enum_G_06 | 74 | 41 | 5.4 | 12 | 1
enum_G_07 | 75 | 42 | 0 | 6 | 4
enum_G_08 | 70 | 42.6 | 8.6 | 4 | 5
enum_G_09 | 68 | 42.9 | 5.9 | 6 | 3
enum_G_10 | 71 | 40.9 | 0 | 4 | 3
enum_G_11 | 66 | 44.5 | 0 | 3 | 5
enum_G_12 | 74 | 39.1 | 0 | 6 | 4
enum_G_13 | 94 | 40.9 | 0 | 13 | 2
enum_G_14 | 57 | 42.8 | 0 | 9 | 3
enum_G_15 | 69 | 42.9 | 0 | 5 | 6
enum_G_16 | 65 | 41 | 3.1 | 8 | 0

## Progress
Progress against target by LGA
Synthetic data – not real findings
adm1_name | adm2_name | pop_type | target | achieved | percent
Kaduna | Birnin-Gwari | idp | 78 | 78 | 100
Kaduna | Birnin-Gwari | non_idp | 102 | 102 | 100
Kaduna | Chikun | non_idp | 102 | 102 | 100
Kaduna | Giwa | idp | 90 | 90 | 100
Kaduna | Giwa | non_idp | 102 | 102 | 100
Kaduna | Igabi | idp | 72 | 78 | 108.3
Kaduna | Igabi | non_idp | 102 | 102 | 100
Kaduna | Kaduna North | non_idp | 102 | 102 | 100
Kaduna | Kaduna South | idp | 12 | 20 | 166.7
Kaduna | Kaduna South | non_idp | 96 | 102 | 106.2
Kaduna | Kagarko | idp | 78 | 78 | 100
Kaduna | Kagarko | non_idp | 102 | 102 | 100