## Summary
Data-quality digest: Partner H
Synthetic data – not real findings
Item | Value
Partner | Partner H
States | Kaduna
Data as of | 2026-09-27
Submissions received | 964
Interviews kept | 906
Interviews removed | 58
Values corrected | 10
Interviews flagged for follow-up | 61
Households targeted | 900
Households achieved | 906
Progress against target | 100.7%

## Follow up
Interviews flagged: please check with the enumerator
Synthetic data – not real findings
date | enumerator_id | cluster_id | household_id | _uuid | check | issue | value
2026-08-18 | enum_H_02 | non_idp_NG019006_C01 | non_idp_NG019006_C01_H01 | adc89fc9-97b5-423d-bcdc-718f9415bcdc | gps_far | GPS point 4.2 km from the household | 4240
2026-08-20 | enum_H_02 | non_idp_NG019006_C03 | non_idp_NG019006_C03_H02 | 02522125-2507-4cae-bbed-9f17023ca04b | gps_far | GPS point 4.8 km from the household | 4773
2026-08-21 | enum_H_07 | non_idp_NG019018_C02 | non_idp_NG019018_C02_H01 | e8e2c9b2-3fd9-4319-bd59-9941e77950d9 | children_exceed_hh | More children than household members | 0 + 11 children, household of 9
2026-08-21 | enum_H_11 | idp_NG019021_C07 | idp_NG019021_C07_H04 | d073f8e8-4fa2-491f-ac8c-424a857e618e | fcs_hhs_contradiction | Acceptable food consumption with severe hunger | FCS 93.5, HHS 6
2026-08-22 | enum_H_14 | non_idp_NG019021_C16 | non_idp_NG019021_C16_H04 | 2155831b-40b4-4db6-9bb3-612fd4cd89bb | fcs_hhs_contradiction | Acceptable food consumption with severe hunger | FCS 93.5, HHS 6
2026-08-23 | enum_H_02 | non_idp_NG019006_C06 | non_idp_NG019006_C06_H03 | 0d0c8bcf-ae83-4bf0-91dc-425fc21f820c | gps_far | GPS point 4.0 km from the household | 3968
2026-08-23 | enum_H_07 | non_idp_NG019018_C04 | non_idp_NG019018_C04_H03 | 3e368fbe-ae4f-4226-8fed-17a2030cba9f | fcs_hhs_contradiction | Acceptable food consumption with severe hunger | FCS 93.5, HHS 6
2026-08-24 | enum_H_08 | non_idp_NG019018_C05 | non_idp_NG019018_C05_H06 | 9b99dada-be05-48eb-b713-220e25f3613b | fcs_hhs_contradiction | Acceptable food consumption with severe hunger | FCS 38.0, HHS 4
2026-08-24 | enum_H_11 | idp_NG019021_C10 | idp_NG019021_C10_H05 | 4822cf58-4d72-4171-8c7d-dfb2ba016289 | fcs_hhs_contradiction | Acceptable food consumption with severe hunger | FCS 48.0, HHS 4
2026-08-25 | enum_H_08 | non_idp_NG019018_C06 | non_idp_NG019018_C06_H02 | 87bb4f6b-df35-4671-aec4-6348746059c1 | fcs_hhs_contradiction | Acceptable food consumption with severe hunger | FCS 93.5, HHS 6
2026-08-25 | enum_H_12 | idp_NG019021_C11 | idp_NG019021_C11_H06 | d7161abc-2268-423e-9826-0a6acc11954e | fcs_hhs_contradiction | Acceptable food consumption with severe hunger | FCS 93.5, HHS 6
2026-08-26 | enum_H_11 | idp_NG019021_C12 | idp_NG019021_C12_H04 | b7d15625-1b69-459d-857f-3757355557d5 | gps_far | GPS point 4.9 km from the household | 4874
2026-08-27 | enum_H_10 | non_idp_NG019019_C01 | non_idp_NG019019_C01_H04 | f49f099c-9068-4782-a398-3626ed428253 | fcs_flat | Every food group given the same number of days | 7
2026-08-27 | enum_H_10 | non_idp_NG019019_C01 | non_idp_NG019019_C01_R02 | 7a8dd9e1-ee50-4e1c-930b-6d9ba192f605 | children_exceed_hh | More children than household members | 1 + 4 children, household of 4
2026-08-28 | enum_H_06 | non_idp_NG019012_C16 | non_idp_NG019012_C16_H02 | a39bc08e-0109-49a6-a983-8ec954ebb96f | fcs_hhs_contradiction | Acceptable food consumption with severe hunger | FCS 93.5, HHS 6
2026-08-28 | enum_H_14 | non_idp_NG019023_C01 | non_idp_NG019023_C01_H01 | 4394d8b5-9ec6-4c0e-9179-bb9a19082a05 | fcs_flat | Every food group given the same number of days | 0
2026-08-29 | enum_H_11 | non_idp_NG019021_C02 | non_idp_NG019021_C02_H04 | ae539b15-0245-4e8b-b5e8-1a78325238ff | gps_far | GPS point 3.6 km from the household | 3617
2026-08-29 | enum_H_12 | non_idp_NG019021_C02 | non_idp_NG019021_C02_H01 | 47604c0c-d034-4a62-a7d7-269a3a334dcd | fcs_hhs_contradiction | Acceptable food consumption with severe hunger | FCS 40.0, HHS 4
2026-08-29 | enum_H_13 | non_idp_NG019023_C03 | non_idp_NG019023_C03_H04 | b2a1ad1d-dd1b-4978-862f-b357f026bc68 | fcs_hhs_contradiction | Acceptable food consumption with severe hunger | FCS 93.5, HHS 6
2026-08-30 | enum_H_02 | non_idp_NG019006_C13 | non_idp_NG019006_C13_H02 | 60339ee8-d598-409c-8223-145ad4ddda22 | fcs_flat | Every food group given the same number of days | 7
2026-08-30 | enum_H_03 | non_idp_NG019008_C13 | non_idp_NG019008_C13_H05 | bfd3efcb-9729-4f92-85fb-ec35a5f7ac80 | fcs_flat | Every food group given the same number of days | 7
2026-08-30 | enum_H_03 | non_idp_NG019008_C13 | non_idp_NG019008_C13_H05 | bfd3efcb-9729-4f92-85fb-ec35a5f7ac80 | fcs_hhs_contradiction | Acceptable food consumption with severe hunger | FCS 112.0, HHS 4
2026-08-30 | enum_H_06 | non_idp_NG019016_C01 | non_idp_NG019016_C01_H02 | 3f8fa09e-1e2d-419e-a156-00e5ba93672a | fcs_flat | Every food group given the same number of days | 0
2026-08-30 | enum_H_07 | non_idp_NG019018_C12 | non_idp_NG019018_C12_H04 | daa70a7a-29d1-4d55-868e-2fe196da9c63 | gps_far | GPS point 3.4 km from the household | 3437
2026-08-30 | enum_H_08 | non_idp_NG019018_C12 | non_idp_NG019018_C12_H05 | 7816a7d5-f8f7-4ff8-9bf0-d497685f1f19 | fcs_hhs_contradiction | Acceptable food consumption with severe hunger | FCS 93.5, HHS 6
2026-08-30 | enum_H_11 | non_idp_NG019021_C03 | non_idp_NG019021_C03_H04 | 5881a4d0-c2fd-48f8-9308-443fc774ef70 | fcs_hhs_contradiction | Acceptable food consumption with severe hunger | FCS 93.5, HHS 6
2026-08-31 | enum_H_02 | non_idp_NG019006_C15 | non_idp_NG019006_C15_R01 | 8309f0af-f149-46f3-aaf5-8866f940b14e | fcs_hhs_contradiction | Acceptable food consumption with severe hunger | FCS 43.0, HHS 4
2026-08-31 | enum_H_07 | non_idp_NG019018_C13 | non_idp_NG019018_C13_R01 | e53caf86-0dde-452e-bf26-3f8076c87a91 | gps_far | GPS point 0.9 km from the household | 898
2026-09-01 | enum_H_02 | non_idp_NG019006_C16 | non_idp_NG019006_C16_H01 | b8009d6f-5008-4174-b82b-8eb1e9ddc7aa | fcs_hhs_contradiction | Acceptable food consumption with severe hunger | FCS 42.0, HHS 4
2026-09-01 | enum_H_05 | non_idp_NG019016_C02 | non_idp_NG019016_C02_H01 | 0e588f00-0e6a-4efb-a840-10d17e8f309d | fcs_flat | Every food group given the same number of days | 7
2026-09-01 | enum_H_09 | non_idp_NG019019_C07 | non_idp_NG019019_C07_H01 | cc02b2cb-76e7-47d5-b9e7-318db83ecac4 | gps_far | GPS point 4.8 km from the household | 4776
2026-09-01 | enum_H_11 | non_idp_NG019021_C05 | non_idp_NG019021_C05_H04 | f079c140-9b7c-401c-901c-5b0cc16ecdd4 | fcs_flat | Every food group given the same number of days | 7
2026-09-02 | enum_H_03 | idp_NG019012_C01 | idp_NG019012_C01_H01 | 630860d5-e696-4856-9ede-52e24aec0223 | fcs_hhs_contradiction | Acceptable food consumption with severe hunger | FCS 93.5, HHS 6
2026-09-02 | enum_H_08 | non_idp_NG019018_C15 | non_idp_NG019018_C15_H04 | 313b7fd6-579e-4126-811c-5464965ed8aa | fcs_hhs_contradiction | Acceptable food consumption with severe hunger | FCS 41.0, HHS 4
2026-09-02 | enum_H_10 | non_idp_NG019019_C12 | non_idp_NG019019_C12_R02 | 455cb52b-6466-40fb-930e-2f6f05bfc072 | fcs_hhs_contradiction | Acceptable food consumption with severe hunger | FCS 44.0, HHS 4
2026-09-03 | enum_H_03 | non_idp_NG019012_C02 | non_idp_NG019012_C02_H05 | 34de6b31-f32f-4ce4-bd2b-2de46da244bd | fcs_hhs_contradiction | Acceptable food consumption with severe hunger | FCS 93.5, HHS 6
2026-09-03 | enum_H_07 | non_idp_NG019018_C16 | non_idp_NG019018_C16_H02 | 821937d8-2a2a-40c4-a47d-25ea4e087a52 | fcs_flat | Every food group given the same number of days | 7
2026-09-03 | enum_H_12 | non_idp_NG019021_C07 | non_idp_NG019021_C07_H04 | e68beb6d-f2b1-4cd2-9070-2198c0df115f | fcs_flat | Every food group given the same number of days | 7
2026-09-04 | enum_H_03 | non_idp_NG019012_C06 | non_idp_NG019012_C06_H02 | fd0c2c7a-9f63-431a-8094-228f29e2b3d5 | fcs_hhs_contradiction | Acceptable food consumption with severe hunger | FCS 93.5, HHS 6
2026-09-06 | enum_H_13 | non_idp_NG019023_C08 | non_idp_NG019023_C08_H01 | a8cf6b28-e726-449c-ad2c-6fee81c17f81 | fcs_hhs_contradiction | Acceptable food consumption with severe hunger | FCS 41.5, HHS 6
2026-09-07 | enum_H_10 | non_idp_NG019019_C16 | non_idp_NG019019_C16_H03 | 114aa10a-39ba-4a71-8899-ea4455c489e7 | fcs_flat | Every food group given the same number of days | 7
2026-09-08 | enum_H_11 | non_idp_NG019021_C11 | non_idp_NG019021_C11_H04 | 33b59ca7-00d7-40bd-930d-836a0ae9fcf6 | fcs_hhs_contradiction | Acceptable food consumption with severe hunger | FCS 93.5, HHS 6
2026-09-08 | enum_H_13 | non_idp_NG019023_C10 | non_idp_NG019023_C10_H02 | 05d0bf31-8506-44d3-9d00-b62596ed5c97 | attending_exceed_school_age | More children attending school than of school age | 4
2026-09-08 | enum_H_13 | non_idp_NG019023_C10 | non_idp_NG019023_C10_H05 | 217ba797-e932-4947-af5b-9fe0ba674e11 | fcs_hhs_contradiction | Acceptable food consumption with severe hunger | FCS 93.5, HHS 6
2026-09-10 | enum_H_05 | non_idp_NG019016_C08 | non_idp_NG019016_C08_H01 | b851134f-8382-4851-a30d-aa90f8a6d965 | fcs_hhs_contradiction | Acceptable food consumption with severe hunger | FCS 93.5, HHS 6
2026-09-10 | enum_H_06 | non_idp_NG019016_C08 | non_idp_NG019016_C08_H02 | ea0d0ecc-c125-4402-b06f-4ea21ea10685 | gps_far | GPS point 1.2 km from the household | 1183
2026-09-10 | enum_H_10 | idp_NG019021_C02 | idp_NG019021_C02_H01 | ae68b76f-acee-4108-887d-10fe31db68ac | gps_far | GPS point 3.3 km from the household | 3284
2026-09-10 | enum_H_10 | idp_NG019021_C02 | idp_NG019021_C02_H04 | 5ea172a4-f709-40d1-bbe4-218c3ec850f8 | gps_far | GPS point 2.8 km from the household | 2832
2026-09-10 | enum_H_14 | non_idp_NG019023_C12 | non_idp_NG019023_C12_H03 | 8848d092-642b-428e-97ef-4f9b597ba3ae | children_exceed_hh | More children than household members | 3 + 7 children, household of 8
2026-09-11 | enum_H_04 | non_idp_NG019012_C10 | non_idp_NG019012_C10_H06 | 1c18bdfb-ae9c-4c9c-9fa4-ee9fd509b6e7 | fcs_hhs_contradiction | Acceptable food consumption with severe hunger | FCS 93.5, HHS 6
2026-09-11 | enum_H_05 | non_idp_NG019016_C10 | non_idp_NG019016_C10_H03 | be970385-3530-48eb-9734-c0dd3404b351 | gps_far | GPS point 1.3 km from the household | 1349
2026-09-12 | enum_H_08 | non_idp_NG019016_R2_01 | non_idp_NG019016_R2_01_H04 | 086e3e60-55af-486e-888b-6afb83943abb | fcs_flat | Every food group given the same number of days | 7
2026-09-13 | enum_H_05 | non_idp_NG019016_C11 | non_idp_NG019016_C11_H04 | 80388782-66a3-46fe-aefd-91fdc107512b | fcs_hhs_contradiction | Acceptable food consumption with severe hunger | FCS 93.5, HHS 6
2026-09-13 | enum_H_07 | non_idp_NG019018_R2_01 | non_idp_NG019018_R2_01_H03 | 39ad9f55-bfb9-4db2-bc30-4578604d872a | gps_far | GPS point 3.9 km from the household | 3878
2026-09-13 | enum_H_09 | idp_NG019021_C04 | idp_NG019021_C04_R01 | 92c6f65b-5b2a-443b-9c22-dba831bed948 | fcs_flat | Every food group given the same number of days | 7
2026-09-14 | enum_H_11 | non_idp_NG019021_C15 | non_idp_NG019021_C15_R02 | 66e47857-f9e9-4612-a139-a63ffaa69665 | fcs_flat | Every food group given the same number of days | 7
2026-09-14 | enum_H_12 | non_idp_NG019021_C15 | non_idp_NG019021_C15_R01 | a645e036-18a1-4d72-9d58-0070c0d61278 | fcs_flat | Every food group given the same number of days | 7
2026-09-15 | enum_H_04 | non_idp_NG019008_R1_01 | non_idp_NG019008_R1_01_H06 | 64d34739-b959-4ffd-929a-4f3bfb66d304 | fcs_hhs_contradiction | Acceptable food consumption with severe hunger | FCS 93.5, HHS 6
2026-09-16 | enum_H_13 | non_idp_NG019023_C17 | non_idp_NG019023_C17_H02 | 83c67b99-657d-40a1-8cbf-c703e6e314a2 | fcs_hhs_contradiction | Acceptable food consumption with severe hunger | FCS 49.5, HHS 4
2026-09-17 | enum_H_14 | non_idp_NG019023_R1_01 | non_idp_NG019023_R1_01_H05 | df1d5916-7b6f-44d9-a5a7-08e24049207b | fcs_hhs_contradiction | Acceptable food consumption with severe hunger | FCS 93.5, HHS 6
2026-09-18 | enum_H_03 | non_idp_NG019008_R2_01 | non_idp_NG019008_R2_01_H05 | a363aac2-5437-43a7-93e6-1b647e0a4860 | attending_exceed_school_age | More children attending school than of school age | 4
2026-09-19 | enum_H_06 | non_idp_NG019012_R1_02 | non_idp_NG019012_R1_02_H02 | 87411dc0-c8e1-453b-8d7c-a0579c7e6617 | gps_far | GPS point 1.5 km from the household | 1477

## Removed
Interviews removed from the dataset, and why
Synthetic data – not real findings
date | enumerator_id | cluster_id | household_id | _uuid | check_id | reason
2026-08-18 | enum_H_02 | non_idp_NG019006_C01 | non_idp_NG019006_C01_H03 | 1a90a531-c552-4ba1-92b1-32a2363d0c15 | C01 | Respondent did not consent
2026-08-20 | enum_H_01 | non_idp_NG019006_C03 | non_idp_NG019006_C03_H06 | eecba11f-f83a-4bd7-b14a-c466fc84b234 | C04 | Interview took 10 minutes
2026-08-25 | enum_H_03 | non_idp_NG019008_C08 | non_idp_NG019008_C08_H03 | 8a4091f8-ac12-4de6-871a-9b1ff44c0000 | C01 | Respondent did not consent
2026-08-25 | enum_H_13 | idp_NG019023_C01 | idp_NG019023_C01_H06 | a7fe0dc5-9b38-441a-bd62-0c885349bd70 | C01 | Respondent did not consent
2026-08-25 | enum_H_13 | idp_NG019023_C01 | idp_NG019023_C01_H02 | eb502ede-7dcb-4317-ba10-48e539441f38 | C03 | Household already interviewed in an earlier submission
2026-08-26 | enum_H_04 | non_idp_NG019008_C10 | non_idp_NG019008_C10_H06 | c68bc71a-2a69-4f1a-98a0-8e3b7dde342a | C04 | Interview took 11 minutes
2026-08-26 | enum_H_04 | non_idp_NG019008_C10 | non_idp_NG019008_C10_R01 | b5398214-060a-4071-8e6a-c49c1c2889b9 | C04 | Interview took 7 minutes
2026-08-27 | enum_H_01 | non_idp_NG019006_C10 | non_idp_NG019006_C10_H04 | a6ef493e-d625-4c42-be88-757d91a4fa8b | C01 | Respondent did not consent
2026-08-27 | enum_H_08 | non_idp_NG019018_C08 | non_idp_NG019018_C08_H03 | ee74e773-a0e1-4dc0-b67c-0e582f90c785 | C04 | Interview took 6 minutes
2026-08-27 | enum_H_11 | non_idp_NG019021_C01 | non_idp_NG019021_C01_H06 | 4bfb93df-e72e-475d-994b-8e367bdea925 | C04 | Interview took 11 minutes
2026-08-27 | enum_H_12 | non_idp_NG019021_C01 | non_idp_NG019021_C01_H02 | 329da80f-83d6-4d18-83ca-503fad24e854 | C04 | Interview took 10 minutes
2026-08-28 | enum_H_05 | non_idp_NG019012_C16 | non_idp_NG019012_C16_H05 | 5cdd4946-53fd-4d28-95c7-4f6f4986ef80 | C01 | Respondent did not consent
2026-08-28 | enum_H_06 | non_idp_NG019012_C16 | non_idp_NG019012_C16_H03 | cdbed6ac-3d69-45a4-8dc4-035e898923e7 | C03 | Household already interviewed in an earlier submission
2026-08-29 | enum_H_13 | non_idp_NG019023_C98 | non_idp_NG019023_C03_H06 | 3cde37bc-0396-4c1b-beae-ba01873bf0bc | C05 | Cluster code not in the sample
2026-09-01 | enum_H_05 | non_idp_NG019016_C02 | non_idp_NG019016_C02_H02 | eae90be5-4477-447f-8cef-855a6910f500 | C01 | Respondent did not consent
2026-09-01 | enum_H_10 | non_idp_NG019019_C07 | non_idp_NG019019_C07_H03 | 24de6caa-b725-4784-a4ce-b9e3c4beed81 | C04 | Interview took 10 minutes
2026-09-02 | enum_H_02 | non_idp_NG019008_C01 | non_idp_NG019008_C01_R02 | e66cdc5b-e751-4133-9327-7155a7add222 | C04 | Interview took 6 minutes
2026-09-03 | enum_H_04 | non_idp_NG019012_C02 | non_idp_NG019012_C02_H06 | b23dc89d-642d-4f9b-8f33-b6b588c45cb6 | C02 | Same submission uploaded more than once
2026-09-03 | enum_H_08 | non_idp_NG019018_C16 | non_idp_NG019018_C16_H05 | 45db6026-e1c0-4d8f-add8-4f5b050348a5 | C02 | Same submission uploaded more than once
2026-09-04 | enum_H_02 | non_idp_NG019008_C03 | non_idp_NG019008_C03_R01 | 58a898e0-18b7-4188-9f8f-42ecc596ae94 | C04 | Interview took 10 minutes
2026-09-04 | enum_H_03 | non_idp_NG019012_C06 | non_idp_NG019012_C06_H05 | 5a7462f1-e7fa-4cfb-bcda-f174078d6187 | C01 | Respondent did not consent
2026-09-04 | enum_H_05 | non_idp_NG019016_C04 | non_idp_NG019016_C04_H03 | 6e3c69c3-fbf4-4fb2-b2c0-290128e88754 | C04 | Interview took 12 minutes
2026-09-04 | enum_H_07 | non_idp_NG019018_C17 | non_idp_NG019018_C17_H04 | 42c80b25-4cc8-48d1-b9dc-b77f33cb3fd1 | C04 | Interview took 8 minutes
2026-09-05 | enum_H_09 | non_idp_NG019019_C91 | non_idp_NG019019_C14_H02 | 948ff210-91c7-4666-af4d-deb429eb6bd3 | C05 | Cluster code not in the sample
2026-09-06 | enum_H_03 | non_idp_NG019012_C07 | non_idp_NG019012_C07_H06 | aa07bd67-5f25-40f9-9ba2-687c26b072cd | C04 | Interview took 9 minutes
2026-09-06 | enum_H_04 | non_idp_NG019012_C07 | non_idp_NG019012_C07_H03 | bbf63ec5-5b44-4f65-b510-1b2d95f78e80 | C01 | Respondent did not consent
2026-09-06 | enum_H_04 | non_idp_NG019012_C07 | non_idp_NG019012_C07_H04 | 1d9aa607-c526-4070-860a-5ccb77e44d10 | C04 | Interview took 7 minutes
2026-09-06 | enum_H_14 | non_idp_NG019023_C08 | non_idp_NG019023_C08_H05 | 0ef45317-1778-44ee-aeb2-a17453be3056 | C01 | Respondent did not consent
2026-09-07 | enum_H_02 | non_idp_NG019006_R1_01 | non_idp_NG019006_R1_01_H01 | 4ad87939-218c-4d93-a569-f1d90c879f04 | C04 | Interview took 10 minutes
2026-09-07 | enum_H_07 | non_idp_NG019018_R1_01 | non_idp_NG019018_R1_01_H01 | c900825f-68c4-4b0f-9ee9-a8c9ad22b772 | C04 | Interview took 8 minutes
2026-09-07 | enum_H_10 | non_idp_NG019019_C16 | non_idp_NG019019_C16_H05 | 92a5c2ff-640a-4e03-94de-43814de47251 | C01 | Respondent did not consent
2026-09-10 | enum_H_14 | non_idp_NG019023_C12 | non_idp_NG019023_C12_H06 | abd7b64f-ef74-4b91-b53c-60ef5652fe6e | C01 | Respondent did not consent
2026-09-11 | enum_H_03 | non_idp_NG019012_C10 | non_idp_NG019012_C10_H04 | 6c06c38a-eb27-4537-8865-f2b9d6868de5 | C04 | Interview took 11 minutes
2026-09-11 | enum_H_13 | non_idp_NG019023_C13 | non_idp_NG019023_C13_H05 | da4ae190-6800-4d70-9670-d0b781b62455 | C01 | Respondent did not consent
2026-09-11 | enum_H_14 | non_idp_NG019023_C13 | non_idp_NG019023_C13_H02 | 823e19e0-7fcb-4f57-a410-27192b25d560 | C01 | Respondent did not consent
2026-09-11 | enum_H_14 | non_idp_NG019023_C91 | non_idp_NG019023_C13_R03 | c23bacc1-4b9e-4964-8a89-f27b16923a07 | C05 | Cluster code not in the sample
2026-09-12 | enum_H_01 | non_idp_NG019006_R2_01 | non_idp_NG019006_R2_01_H04 | 7c564cd6-91cc-4259-b537-01eae2dbdd90 | C04 | Interview took 6 minutes
2026-09-12 | enum_H_04 | non_idp_NG019012_C11 | non_idp_NG019012_C11_H05 | fe330125-6b1e-409c-901e-f12fc4597412 | C04 | Interview took 12 minutes
2026-09-12 | enum_H_09 | idp_NG019021_C03 | idp_NG019021_C03_H05 | 9695fa8b-9cca-4ba6-9798-d826d4b1cd65 | C04 | Interview took 6 minutes
2026-09-12 | enum_H_13 | non_idp_NG019023_C14 | non_idp_NG019023_C14_H01 | 5dfc28c5-424d-4365-9a53-9f92ee7ca8df | C04 | Interview took 10 minutes
2026-09-12 | enum_H_14 | non_idp_NG019023_C14 | non_idp_NG019023_C14_H04 | 07fa95d0-e423-4e5f-aac5-ccd8ef6d7b85 | C04 | Interview took 10 minutes
2026-09-13 | enum_H_12 | non_idp_NG019021_C14 | non_idp_NG019021_C14_H05 | 2e140c65-ada1-4caa-9159-461843f3e1fe | C01 | Respondent did not consent
2026-09-13 | enum_H_12 | non_idp_NG019021_C14 | non_idp_NG019021_C14_R02 | 1b91d3e1-fe52-4298-a857-3c47e9745a10 | C04 | Interview took 10 minutes
2026-09-14 | enum_H_05 | non_idp_NG019016_C12 | non_idp_NG019016_C12_H05 | 5103da63-7a6c-4620-8025-ade7d6d1724c | C02 | Same submission uploaded more than once
2026-09-15 | enum_H_06 | non_idp_NG019016_C13 | non_idp_NG019016_C13_H01 | 3bce7284-a7b7-44ae-9254-7791af682526 | C04 | Interview took 12 minutes
2026-09-16 | enum_H_03 | non_idp_NG019008_R1_02 | non_idp_NG019008_R1_02_H02 | 31621a8a-504c-47b9-942d-3181dc4d8bf0 | C02 | Same submission uploaded more than once
2026-09-16 | enum_H_14 | non_idp_NG019023_C17 | non_idp_NG019023_C17_H03 | a937917e-1b6e-49e0-b8f5-70da961d4e0b | C04 | Interview took 11 minutes
2026-09-17 | enum_H_09 | non_idp_NG019019_R1_C90 | non_idp_NG019019_R1_04_H05 | a7b16df6-652d-4514-b2bf-95566025a1f8 | C05 | Cluster code not in the sample
2026-09-17 | enum_H_13 | non_idp_NG019023_R1_01 | non_idp_NG019023_R1_01_R01 | 30202d1b-a82f-46e4-9e17-c663d53ef231 | C02 | Same submission uploaded more than once
2026-09-18 | enum_H_03 | non_idp_NG019008_R2_01 | non_idp_NG019008_R2_01_H01 | 8b483bde-91bf-4590-8d1d-9c50932541ea | C01 | Respondent did not consent
2026-09-18 | enum_H_04 | non_idp_NG019008_R2_01 | non_idp_NG019008_R2_01_H03 | e787d249-1c07-4793-b58c-b000c211edfd | C04 | Interview took 10 minutes
2026-09-19 | enum_H_03 | non_idp_NG019008_R2_02 | non_idp_NG019008_R2_02_H05 | e99b8ed6-d738-4ffe-a22f-9719c5677a6c | C04 | Interview took 8 minutes
2026-09-19 | enum_H_09 | non_idp_NG019019_R1_06 | non_idp_NG019019_R1_06_H03 | 51999ef1-f505-4f04-a667-b71f090b344b | C01 | Respondent did not consent
2026-09-20 | enum_H_05 | non_idp_NG019012_R1_03 | non_idp_NG019012_R1_03_H01 | 0e3a2bd9-535d-4987-9859-aa09eaf2e025 | C04 | Interview took 11 minutes
2026-09-20 | enum_H_10 | non_idp_NG019019_R2_01 | non_idp_NG019019_R2_01_H01 | a78399cb-d6b5-4bf3-bd4d-cff541109935 | C04 | Interview took 6 minutes
2026-09-20 | enum_H_10 | non_idp_NG019019_R2_01 | non_idp_NG019019_R2_01_H03 | dbddefe5-e649-4a02-bae1-663e9a53b6b7 | C01 | Respondent did not consent
2026-09-20 | enum_H_10 | non_idp_NG019019_R2_01 | non_idp_NG019019_R2_01_H05 | 379c0a7a-ac49-4f55-993a-c174005b401a | C04 | Interview took 11 minutes
2026-09-22 | enum_H_03 | non_idp_NG019008_R2_03 | non_idp_NG019008_R2_03_H03 | c31af34d-59ed-416e-8466-409a480b67eb | C01 | Respondent did not consent

## Enumerators
Enumerators
Synthetic data – not real findings
enumerator_id | interviews | median minutes | % repeated answers | interviews removed | interviews flagged | pattern
enum_H_01 | 67 | 45.2 | 0 | 3 | 0
enum_H_02 | 70 | 42.7 | 0 | 4 | 6
enum_H_03 | 65 | 41.9 | 3.1 | 8 | 5
enum_H_04 | 71 | 42.9 | 2.8 | 7 | 2
enum_H_05 | 73 | 43.6 | 2.7 | 5 | 4
enum_H_06 | 64 | 43.6 | 0 | 2 | 4
enum_H_07 | 73 | 43 | 0 | 2 | 6
enum_H_08 | 57 | 42.7 | 3.5 | 2 | 5
enum_H_09 | 83 | 42.3 | 0 | 4 | 2
enum_H_10 | 60 | 41.7 | 0 | 5 | 6
enum_H_11 | 59 | 42.6 | 0 | 1 | 8
enum_H_12 | 71 | 43.4 | 0 | 3 | 4
enum_H_13 | 68 | 42.6 | 2.9 | 6 | 5
enum_H_14 | 65 | 40.4 | 0 | 6 | 4

## Progress
Progress against target by LGA
Synthetic data – not real findings
adm1_name | adm2_name | pop_type | target | achieved | percent
Kaduna | Jaba | non_idp | 102 | 102 | 100
Kaduna | Kachia | non_idp | 102 | 102 | 100
Kaduna | Kajuru | idp | 6 | 6 | 100
Kaduna | Kajuru | non_idp | 102 | 102 | 100
Kaduna | Kudan | non_idp | 102 | 102 | 100
Kaduna | Markafi | non_idp | 102 | 102 | 100
Kaduna | Sabon-Gari | non_idp | 102 | 102 | 100
Kaduna | Soba | idp | 72 | 78 | 108.3
Kaduna | Soba | non_idp | 102 | 102 | 100
Kaduna | Zaria | idp | 6 | 6 | 100
Kaduna | Zaria | non_idp | 102 | 102 | 100