## Summary
Data-quality digest: Partner J
Synthetic data – not real findings
Item | Value
Partner | Partner J
States | Katsina
Data as of | 2026-09-27
Submissions received | 1230
Interviews kept | 1149
Interviews removed | 81
Values corrected | 24
Interviews flagged for follow-up | 67
Households targeted | 1242
Households achieved | 1149
Progress against target | 92.5%

## Follow up
Interviews flagged: please check with the enumerator
Synthetic data – not real findings
date | enumerator_id | cluster_id | household_id | _uuid | check | issue | value
2026-08-17 | enum_J_08 | non_idp_NG021008_C04 | non_idp_NG021008_C04_H04 | 2b945061-9321-4bcd-869d-b8d77f5bfb4a | gps_far | GPS point 2.5 km from the household | 2535
2026-08-18 | enum_J_06 | non_idp_NG021007_C02 | non_idp_NG021007_C02_H01 | b319eabc-a96b-4082-8649-c152c1a7ebb2 | children_exceed_hh | More children than household members | 2 + 8 children, household of 7
2026-08-18 | enum_J_07 | non_idp_NG021008_C05 | non_idp_NG021008_C05_R01 | cc3929d8-ff6a-4d4c-b920-9405becf93d0 | fcs_flat | Every food group given the same number of days | 0
2026-08-19 | enum_J_04 | non_idp_NG021003_C02 | non_idp_NG021003_C02_H01 | 3a007e80-679f-4677-b2b6-a9e741c52803 | attending_exceed_school_age | More children attending school than of school age | 4
2026-08-19 | enum_J_07 | non_idp_NG021008_C06 | non_idp_NG021008_C06_H05 | f6cda145-fcd7-486d-88d9-6a42922b1e46 | fcs_hhs_contradiction | Acceptable food consumption with severe hunger | FCS 93.5, HHS 6
2026-08-21 | enum_J_04 | non_idp_NG021003_C04 | non_idp_NG021003_C04_H04 | 7ce3cbf5-81b1-4c34-8041-b052c7c121cf | gps_far | GPS point 3.9 km from the household | 3874
2026-08-22 | enum_J_05 | non_idp_NG021007_C06 | non_idp_NG021007_C06_H04 | e04fafa9-cb8e-4621-8b14-4660ce196ab2 | gps_far | GPS point 2.5 km from the household | 2538
2026-08-22 | enum_J_08 | non_idp_NG021008_C09 | non_idp_NG021008_C09_H06 | 4faea977-7d5b-4555-9f22-b3bc546a0985 | attending_exceed_school_age | More children attending school than of school age | 4
2026-08-24 | enum_J_20 | idp_NG021032_C08 | idp_NG021032_C08_H01 | eb3bb941-aba9-4ebb-93a6-ca8823510103 | fcs_hhs_contradiction | Acceptable food consumption with severe hunger | FCS 93.5, HHS 6
2026-08-26 | enum_J_02 | idp_NG021001_C06 | idp_NG021001_C06_H03 | eba5e96a-afea-4d67-9f73-27601a6022b7 | fcs_hhs_contradiction | Acceptable food consumption with severe hunger | FCS 41.5, HHS 4
2026-08-26 | enum_J_03 | non_idp_NG021003_C11 | non_idp_NG021003_C11_H04 | a167289f-b38e-4072-b2c2-45bc273b4afb | children_exceed_hh | More children than household members | 1 + 5 children, household of 5
2026-08-26 | enum_J_04 | non_idp_NG021003_C11 | non_idp_NG021003_C11_H06 | c9d25ef9-a040-4076-9d16-5cffdb30e0b1 | gps_far | GPS point 3.1 km from the household | 3108
2026-08-27 | enum_J_14 | idp_NG021022_C07 | idp_NG021022_C07_H03 | 9e680204-1271-45f1-92bd-bc940b0f4fcd | fcs_hhs_contradiction | Acceptable food consumption with severe hunger | FCS 46.0, HHS 4
2026-08-27 | enum_J_14 | idp_NG021022_C07 | idp_NG021022_C07_H04 | 2e9c418d-2a78-4fbf-b584-e66a56033f9c | fcs_hhs_contradiction | Acceptable food consumption with severe hunger | FCS 37.5, HHS 4
2026-08-28 | enum_J_04 | non_idp_NG021003_C12 | non_idp_NG021003_C12_H03 | 5c16c191-89e3-474b-a56a-b91bbf949e1e | attending_exceed_school_age | More children attending school than of school age | 2
2026-08-28 | enum_J_13 | idp_NG021022_C08 | idp_NG021022_C08_H02 | 7c1136b0-4fd5-4e7d-962c-96aad6559944 | fcs_hhs_contradiction | Acceptable food consumption with severe hunger | FCS 38.0, HHS 5
2026-08-28 | enum_J_15 | non_idp_NG021022_C17 | non_idp_NG021022_C17_H03 | 89f5d354-d8bc-4cc0-b3f3-d6ae420587f1 | gps_far | GPS point 1.6 km from the household | 1612
2026-08-28 | enum_J_15 | non_idp_NG021022_C17 | non_idp_NG021022_C17_H06 | ccff91c6-8895-422c-bbf1-a4b49dec88da | fcs_flat | Every food group given the same number of days | 0
2026-08-28 | enum_J_18 | non_idp_NG021031_C13 | non_idp_NG021031_C13_H01 | 12cfbcd6-a61f-4bd0-8518-f05434ffcaf0 | gps_far | GPS point 2.9 km from the household | 2939
2026-08-28 | enum_J_18 | non_idp_NG021031_C13 | non_idp_NG021031_C13_H03 | 33267e7c-1ff6-45b2-b1f9-900cd243c2e9 | gps_far | GPS point 1.3 km from the household | 1251
2026-08-29 | enum_J_04 | non_idp_NG021003_C14 | non_idp_NG021003_C14_H04 | 937c4a03-e122-4f0e-a87e-97d39cd23a41 | fcs_flat | Every food group given the same number of days | 0
2026-08-29 | enum_J_10 | non_idp_NG021014_C12 | non_idp_NG021014_C12_H01 | 4db2b743-4d26-4f05-a2bf-7d6b4b0351e7 | fcs_hhs_contradiction | Acceptable food consumption with severe hunger | FCS 93.5, HHS 6
2026-08-29 | enum_J_10 | non_idp_NG021014_C12 | non_idp_NG021014_C12_H03 | ba0a7b10-c38a-48b8-99f8-fcc294ab1525 | fcs_hhs_contradiction | Acceptable food consumption with severe hunger | FCS 38.0, HHS 6
2026-08-29 | enum_J_13 | idp_NG021022_C10 | idp_NG021022_C10_H01 | aeff0ba5-397a-42cb-97bf-35834abfb5ab | gps_far | GPS point 0.9 km from the household | 920
2026-08-30 | enum_J_16 | idp_NG021031_C02 | idp_NG021031_C02_H04 | b03f752e-5610-4745-ae3a-008853b582dd | gps_far | GPS point 1.2 km from the household | 1189
2026-08-30 | enum_J_18 | non_idp_NG021031_C15 | non_idp_NG021031_C15_H02 | 87a46098-b34c-4acd-a65f-c5dec581b7c5 | fcs_hhs_contradiction | Acceptable food consumption with severe hunger | FCS 47.0, HHS 4
2026-08-31 | enum_J_10 | non_idp_NG021014_C13 | non_idp_NG021014_C13_H04 | 81f5f4f7-df29-46bd-bf7a-13c905d508fe | attending_exceed_school_age | More children attending school than of school age | 4
2026-08-31 | enum_J_12 | non_idp_NG021019_C17 | non_idp_NG021019_C17_H04 | b376c210-d793-4706-bae3-59470f39375c | fcs_flat | Every food group given the same number of days | 0
2026-08-31 | enum_J_19 | non_idp_NG021032_C05 | non_idp_NG021032_C05_H04 | dc7e5903-5849-4b70-ba87-8086fcce19a8 | fcs_hhs_contradiction | Acceptable food consumption with severe hunger | FCS 47.0, HHS 4
2026-09-01 | enum_J_02 | non_idp_NG021001_C01 | non_idp_NG021001_C01_H06 | ca84c67e-4a21-42c4-8fc5-7c34eb34c035 | fcs_hhs_contradiction | Acceptable food consumption with severe hunger | FCS 93.5, HHS 6
2026-09-01 | enum_J_20 | non_idp_NG021032_C06 | non_idp_NG021032_C06_H05 | fb578c8b-ce29-4efd-ac09-9856ff076e7d | gps_far | GPS point 4.1 km from the household | 4136
2026-09-02 | enum_J_03 | non_idp_NG021001_R1_01 | non_idp_NG021001_R1_01_R01 | 1d41fb55-e1db-4e83-8335-57e1d88f1230 | fcs_hhs_contradiction | Acceptable food consumption with severe hunger | FCS 93.5, HHS 6
2026-09-02 | enum_J_18 | idp_NG021032_C01 | idp_NG021032_C01_R02 | 38066d5d-e3ed-48ed-855a-439979d1947c | gps_far | GPS point 3.5 km from the household | 3478
2026-09-03 | enum_J_18 | idp_NG021032_C02 | idp_NG021032_C02_H04 | 7f7a9718-d660-406e-b738-c5005b481f08 | fcs_flat | Every food group given the same number of days | 7
2026-09-04 | enum_J_06 | non_idp_NG021007_C15 | non_idp_NG021007_C15_R01 | 3f3d3cfd-d957-4266-a329-dbafb8f689a6 | gps_far | GPS point 1.9 km from the household | 1907
2026-09-04 | enum_J_12 | idp_NG021022_C03 | idp_NG021022_C03_H03 | a187131e-5e17-4631-9348-f8a5f5a61371 | fcs_hhs_contradiction | Acceptable food consumption with severe hunger | FCS 44.0, HHS 6
2026-09-04 | enum_J_13 | idp_NG021022_C12 | idp_NG021022_C12_H01 | 1ee9ee91-1fdb-44f5-8bf1-3451f42ff890 | gps_far | GPS point 2.3 km from the household | 2260
2026-09-04 | enum_J_13 | idp_NG021022_C12 | idp_NG021022_C12_H06 | 73616b45-c33e-458a-8959-5ba5559427e5 | gps_far | GPS point 1.8 km from the household | 1835
2026-09-04 | enum_J_17 | idp_NG021032_C03 | idp_NG021032_C03_H04 | 8a6fb496-016a-4bff-ba7b-b655c6a3c78e | fcs_flat | Every food group given the same number of days | 7
2026-09-04 | enum_J_17 | idp_NG021032_C03 | idp_NG021032_C03_H04 | 8a6fb496-016a-4bff-ba7b-b655c6a3c78e | fcs_hhs_contradiction | Acceptable food consumption with severe hunger | FCS 112.0, HHS 4
2026-09-05 | enum_J_03 | non_idp_NG021003_R1_03 | non_idp_NG021003_R1_03_R01 | 0cd650ad-403b-425a-b8e3-a3d9e4568d53 | gps_far | GPS point 2.6 km from the household | 2616
2026-09-05 | enum_J_12 | non_idp_NG021019_R1_01 | non_idp_NG021019_R1_01_H06 | 78fc2e3c-7416-4d16-9604-ddf2394f70eb | gps_far | GPS point 1.7 km from the household | 1748
2026-09-06 | enum_J_12 | non_idp_NG021019_R1_03 | non_idp_NG021019_R1_03_R01 | ae5fe502-66cd-48bb-91ec-e0f388a8c8a5 | gps_far | GPS point 1.8 km from the household | 1817
2026-09-06 | enum_J_12 | non_idp_NG021019_R1_03 | non_idp_NG021019_R1_03_R02 | 6af15f97-4fbc-408c-954c-ecd84b95d469 | fcs_flat | Every food group given the same number of days | 0
2026-09-06 | enum_J_19 | non_idp_NG021032_C12 | non_idp_NG021032_C12_H06 | d080c3cc-df9d-4688-8b41-88d898906a26 | children_exceed_hh | More children than household members | 2 + 7 children, household of 8
2026-09-07 | enum_J_02 | non_idp_NG021001_C10 | non_idp_NG021001_C10_H03 | 220a317e-28d1-4818-a3cd-e0280b7b7c3b | fcs_hhs_contradiction | Acceptable food consumption with severe hunger | FCS 40.0, HHS 5
2026-09-07 | enum_J_14 | non_idp_NG021022_C02 | non_idp_NG021022_C02_H04 | 75014c46-f2a5-4190-b65a-ef2d677c1248 | fcs_hhs_contradiction | Acceptable food consumption with severe hunger | FCS 42.5, HHS 4
2026-09-08 | enum_J_07 | non_idp_NG021014_C07 | non_idp_NG021014_C07_H04 | 93961a40-7c3b-44f7-8a6c-7362647b00c2 | gps_far | GPS point 4.3 km from the household | 4297
2026-09-08 | enum_J_08 | non_idp_NG021014_C07 | non_idp_NG021014_C07_H06 | 0f47be2f-1785-43ec-911e-007ea0780e7a | fcs_hhs_contradiction | Acceptable food consumption with severe hunger | FCS 36.0, HHS 5
2026-09-09 | enum_J_01 | non_idp_NG021001_C11 | non_idp_NG021001_C11_H06 | 805660a0-7cc9-49f5-b8b0-f179b925caaf | gps_far | GPS point 3.1 km from the household | 3128
2026-09-09 | enum_J_02 | non_idp_NG021001_C11 | non_idp_NG021001_C11_H01 | ba2aa45d-8bd6-4022-8504-e415e344e38b | fcs_hhs_contradiction | Acceptable food consumption with severe hunger | FCS 44.5, HHS 4
2026-09-09 | enum_J_06 | non_idp_NG021008_C03 | non_idp_NG021008_C03_H05 | 9e0a04c0-168f-40cb-bce1-6522b7cef9a8 | fcs_hhs_contradiction | Acceptable food consumption with severe hunger | FCS 93.5, HHS 6
2026-09-09 | enum_J_08 | non_idp_NG021014_C08 | non_idp_NG021014_C08_H06 | 5450dd72-4226-412b-9b00-2c558f41747b | attending_exceed_school_age | More children attending school than of school age | 4
2026-09-09 | enum_J_14 | non_idp_NG021022_C05 | non_idp_NG021022_C05_H02 | 63e5e680-8a1d-4f0f-8573-a5d5ccab4614 | gps_far | GPS point 2.2 km from the household | 2211
2026-09-09 | enum_J_19 | non_idp_NG021032_C15 | non_idp_NG021032_C15_R01 | b85a799d-7fd2-4199-bb62-6e1daf74430b | gps_far | GPS point 4.5 km from the household | 4482
2026-09-09 | enum_J_20 | non_idp_NG021032_C15 | non_idp_NG021032_C15_H01 | 160123a3-5f23-400b-820e-fdc1c4937e0a | gps_far | GPS point 1.4 km from the household | 1385
2026-09-10 | enum_J_05 | non_idp_NG021007_R1_03 | non_idp_NG021007_R1_03_H06 | b05f33bc-65ce-40a0-ac29-cb323cf5cd01 | gps_far | GPS point 4.4 km from the household | 4431
2026-09-12 | enum_J_05 | non_idp_NG021007_R1_05 | non_idp_NG021007_R1_05_H06 | f789f41c-d026-44cd-ba5d-958f289d0612 | fcs_hhs_contradiction | Acceptable food consumption with severe hunger | FCS 93.5, HHS 6
2026-09-12 | enum_J_16 | non_idp_NG021031_C04 | non_idp_NG021031_C04_H01 | fcc28d95-8968-443a-bc4f-4a758b66b021 | fcs_flat | Every food group given the same number of days | 7
2026-09-14 | enum_J_05 | non_idp_NG021003_R2_01 | non_idp_NG021003_R2_01_H04 | 10b670b1-f54a-4628-a9ea-7559d8278203 | fcs_flat | Every food group given the same number of days | 7
2026-09-14 | enum_J_09 | idp_NG021019_C05 | idp_NG021019_C05_R01 | 238129d6-d700-4a79-897c-bea1298f8f2c | fcs_hhs_contradiction | Acceptable food consumption with severe hunger | FCS 93.5, HHS 6
2026-09-14 | enum_J_18 | non_idp_NG021031_R2_03 | non_idp_NG021031_R2_03_H01 | 86b766d1-47ec-4bda-8433-d6bc91c12ea5 | gps_far | GPS point 2.8 km from the household | 2846
2026-09-14 | enum_J_20 | non_idp_NG021032_R2_01 | non_idp_NG021032_R2_01_H06 | 83501435-3b5c-4aec-96bb-3c15080663ca | gps_far | GPS point 4.2 km from the household | 4151
2026-09-15 | enum_J_18 | non_idp_NG021031_R2_04 | non_idp_NG021031_R2_04_H05 | 8d665e58-1d64-48ed-9378-d3fe58c3520c | children_exceed_hh | More children than household members | 1 + 8 children, household of 6
2026-09-16 | enum_J_19 | non_idp_NG021032_R2_02 | non_idp_NG021032_R2_02_H05 | 65c9085a-bf0d-40d0-91e1-f707987d958d | gps_far | GPS point 2.3 km from the household | 2273
2026-09-18 | enum_J_06 | non_idp_NG021007_R2_03 | non_idp_NG021007_R2_03_H02 | b7531a98-f6e2-4e86-8560-cc73532fe39c | fcs_flat | Every food group given the same number of days | 7
2026-09-23 | enum_J_09 | non_idp_NG021014_R1_01 | non_idp_NG021014_R1_01_H01 | b9a8f078-9783-4c00-866a-dac91dbfa8eb | fcs_flat | Every food group given the same number of days | 7
2026-09-23 | enum_J_10 | non_idp_NG021014_R1_01 | non_idp_NG021014_R1_01_H04 | 1917999e-2073-49a4-b4f1-86aa09582e34 | gps_far | GPS point 1.4 km from the household | 1443

## Removed
Interviews removed from the dataset, and why
Synthetic data – not real findings
date | enumerator_id | cluster_id | household_id | _uuid | check_id | reason
2026-08-18 | enum_J_05 | non_idp_NG021007_C02 | non_idp_NG021007_C02_H06 | 875949be-0e96-4c26-9255-cbc6b651bcdc | C04 | Interview took 12 minutes
2026-08-19 | enum_J_04 | non_idp_NG021003_C02 | non_idp_NG021003_C02_R01 | 81db087d-fe24-4d7d-a2cc-837f9bc72e58 | C03 | Household already interviewed in an earlier submission
2026-08-20 | enum_J_05 | non_idp_NG021007_C05 | non_idp_NG021007_C05_H01 | fd716a7c-a106-4fc9-88b4-755d92e0eb44 | C04 | Interview took 8 minutes
2026-08-22 | enum_J_08 | non_idp_NG021008_C09 | non_idp_NG021008_C09_H04 | abc65c5a-753f-463c-a208-9b15bc6ece84 | C04 | Interview took 9 minutes
2026-08-22 | enum_J_12 | non_idp_NG021019_C04 | non_idp_NG021019_C04_H05 | 42862f9f-4edb-4257-ac36-3b368e9ef48d | C04 | Interview took 6 minutes
2026-08-23 | enum_J_03 | non_idp_NG021003_C08 | non_idp_NG021003_C08_H01 | 24ab14c0-cc18-4168-a8ee-bf5b1fa709a5 | C04 | Interview took 7 minutes
2026-08-23 | enum_J_06 | non_idp_NG021007_C07 | non_idp_NG021007_C07_H02 | 7fc1d681-9bfd-484e-9535-4ab628cf16de | C04 | Interview took 10 minutes
2026-08-23 | enum_J_07 | non_idp_NG021008_C10 | non_idp_NG021008_C10_H01 | 53f51b10-0c9d-47e4-8037-03f1065e39d5 | C02 | Same submission uploaded more than once
2026-08-23 | enum_J_07 | non_idp_NG021008_C10 | non_idp_NG021008_C10_H06 | dd93b545-dbb3-4686-b21a-0735be4cd9d3 | C04 | Interview took 9 minutes
2026-08-23 | enum_J_08 | non_idp_NG021008_C10 | non_idp_NG021008_C10_H02 | fb6bdd8c-259c-4bb7-bba2-44420772a7fb | C01 | Respondent did not consent
2026-08-23 | enum_J_11 | non_idp_NG021019_C05 | non_idp_NG021019_C05_H02 | 339ae2b6-5f6a-4146-acc9-86cb5da1313b | C04 | Interview took 10 minutes
2026-08-24 | enum_J_07 | non_idp_NG021008_C11 | non_idp_NG021008_C11_H01 | 3516cc0a-259d-4389-a21c-9d75d6c8325e | C04 | Interview took 7 minutes
2026-08-24 | enum_J_12 | non_idp_NG021019_C06 | non_idp_NG021019_C06_H01 | 927c0872-fed5-4935-ba35-c4daf5d48f09 | C04 | Interview took 6 minutes
2026-08-25 | enum_J_11 | non_idp_NG021019_C11 | non_idp_NG021019_C11_H03 | f2a3ff3b-25ff-46ef-ba1e-7841e31bca58 | C01 | Respondent did not consent
2026-08-26 | enum_J_02 | idp_NG021001_C06 | idp_NG021001_C06_H01 | 2f888fc4-69e8-458c-abbe-916cf7ad5a8f | C04 | Interview took 8 minutes
2026-08-26 | enum_J_14 | idp_NG021022_C06 | idp_NG021022_C06_H02 | 89197c8e-4072-4790-8ab9-fb0a32e954da | C01 | Respondent did not consent
2026-08-27 | enum_J_12 | non_idp_NG021019_C14 | non_idp_NG021019_C14_H06 | b4cc4c6d-2275-4e9a-9abc-f94b3aee50a3 | C04 | Interview took 9 minutes
2026-08-27 | enum_J_20 | non_idp_NG021032_C02 | non_idp_NG021032_C02_R01 | 09b7a3c9-6f08-43ec-b5c6-69fc50150fff | C04 | Interview took 11 minutes
2026-08-28 | enum_J_08 | non_idp_NG021008_C14 | non_idp_NG021008_C14_H01 | 00604f38-b48a-42f9-9b65-1eb9d7195d9f | C04 | Interview took 7 minutes
2026-08-28 | enum_J_09 | non_idp_NG021014_C11 | non_idp_NG021014_C11_H04 | 1ade5d18-b69f-4880-85ac-2edb0da0d824 | C01 | Respondent did not consent
2026-08-28 | enum_J_15 | non_idp_NG021022_C17 | non_idp_NG021022_C17_H05 | 60e79d2c-9cb1-4822-8735-6f34c918cf06 | C04 | Interview took 11 minutes
2026-08-29 | enum_J_02 | idp_NG021001_C08 | idp_NG021001_C08_H05 | 5e8f9807-dc21-4e9b-8589-f9654932f7ed | C01 | Respondent did not consent
2026-08-29 | enum_J_03 | non_idp_NG021003_C14 | non_idp_NG021003_C14_H02 | e3f16fe8-914a-41f5-ac43-0ebe9743f3b6 | C04 | Interview took 10 minutes
2026-08-29 | enum_J_04 | non_idp_NG021003_C14 | non_idp_NG021003_C14_H01 | a0c1ed49-56bf-494b-b912-832cee61f452 | C04 | Interview took 6 minutes
2026-08-31 | enum_J_04 | non_idp_NG021003_C16 | non_idp_NG021003_C16_H06 | 048c77d6-915d-4ca5-b1bc-f012569676ab | C04 | Interview took 10 minutes
2026-08-31 | enum_J_07 | non_idp_NG021008_C17 | non_idp_NG021008_C17_R02 | 70baf6de-2683-452c-a01b-04dd1a913012 | C04 | Interview took 9 minutes
2026-09-01 | enum_J_03 | non_idp_NG021003_C17 | non_idp_NG021003_C17_H05 | 53772e18-9ff8-4fb5-84e1-766c87e34d4a | C04 | Interview took 9 minutes
2026-09-01 | enum_J_04 | non_idp_NG021003_C17 | non_idp_NG021003_C17_H04 | 52cb8d94-217d-4ea5-9c3d-ae2651ec03ff | C04 | Interview took 6 minutes
2026-09-01 | enum_J_08 | non_idp_NG021014_C02 | non_idp_NG021014_C02_H05 | b49ceb20-3bca-4dcc-941d-5e0b3942262c | C04 | Interview took 7 minutes
2026-09-01 | enum_J_19 | non_idp_NG021032_C06 | non_idp_NG021032_C06_H06 | 4749262b-55aa-454e-b45b-784f823c029d | C01 | Respondent did not consent
2026-09-02 | enum_J_02 | non_idp_NG021001_C02 | non_idp_NG021001_C02_R01 | cdfd47d7-fddf-486c-a814-7135b7e35104 | C01 | Respondent did not consent
2026-09-02 | enum_J_05 | non_idp_NG021007_C10 | non_idp_NG021007_C10_H06 | dd1ce632-3cc4-4e3a-a35e-06b2c778feae | C04 | Interview took 10 minutes
2026-09-02 | enum_J_06 | non_idp_NG021007_C10 | non_idp_NG021007_C10_H03 | 4c872885-0440-49c7-b95c-538555799420 | C04 | Interview took 9 minutes
2026-09-02 | enum_J_12 | idp_NG021022_C01 | idp_NG021022_C01_H06 | 29ab24dd-cafc-4472-9b06-66a1e9205318 | C03 | Household already interviewed in an earlier submission
2026-09-02 | enum_J_18 | idp_NG021032_C01 | idp_NG021032_C01_H04 | 87a51015-c5ca-41ab-8536-f8f76a9c403d | C01 | Respondent did not consent
2026-09-02 | enum_J_18 | idp_NG021032_C01 | idp_NG021032_C01_H05 | 1f799abe-e1c5-44b9-a42b-a7625dcf89f1 | C04 | Interview took 11 minutes
2026-09-03 | enum_J_02 | non_idp_NG021001_C03 | non_idp_NG021001_C03_H03 | 70fa5290-aa34-4837-a316-9609e7e26abf | C01 | Respondent did not consent
2026-09-03 | enum_J_05 | non_idp_NG021007_C11 | non_idp_NG021007_C11_H03 | c3771f75-d9d3-42b1-9dc2-5645dc9bc523 | C01 | Respondent did not consent
2026-09-03 | enum_J_11 | idp_NG021022_C02 | idp_NG021022_C02_R02 | 398b0bc0-1f2b-4a08-b875-961e2dbbd18d | C03 | Household already interviewed in an earlier submission
2026-09-04 | enum_J_01 | non_idp_NG021001_C05 | non_idp_NG021001_C05_H01 | 0d05c445-f3a1-497a-bac0-18689997ccd7 | C04 | Interview took 9 minutes
2026-09-04 | enum_J_01 | non_idp_NG021001_C05 | non_idp_NG021001_C05_H05 | dae15f25-e194-4691-9900-2208ebd0a907 | C02 | Same submission uploaded more than once
2026-09-04 | enum_J_13 | idp_NG021022_C12 | idp_NG021022_C12_H04 | 7ab5d59e-4c4f-4a61-9abb-7f2de110a591 | C01 | Respondent did not consent
2026-09-05 | enum_J_02 | non_idp_NG021001_C06 | non_idp_NG021001_C06_H06 | 9e63f998-a3cb-4eb9-b652-b50460efd66d | C04 | Interview took 10 minutes
2026-09-05 | enum_J_15 | idp_NG021031_C10 | idp_NG021031_C10_H03 | ad666481-70f0-4108-bb52-4b7083bec3f7 | C01 | Respondent did not consent
2026-09-05 | enum_J_15 | idp_NG021031_C10 | idp_NG021031_C10_R01 | 1bab2552-1601-42b0-8f8c-2921286b5dc9 | C01 | Respondent did not consent
2026-09-06 | enum_J_01 | non_idp_NG021001_C08 | non_idp_NG021001_C08_H03 | a7398a7f-ffc2-43fa-be3e-558c5eae03da | C01 | Respondent did not consent
2026-09-06 | enum_J_11 | non_idp_NG021019_R1_03 | non_idp_NG021019_R1_03_H01 | 7aca21c8-d605-4960-8882-438ed8cefa26 | C02 | Same submission uploaded more than once
2026-09-06 | enum_J_16 | idp_NG021031_C11 | idp_NG021031_C11_H02 | 0391e51f-fd8a-4e6f-ae0a-7802feba4b01 | C01 | Respondent did not consent
2026-09-06 | enum_J_16 | idp_NG021031_C11 | idp_NG021031_C11_R01 | eda766f7-6709-43a0-a575-9521407a78c7 | C04 | Interview took 7 minutes
2026-09-07 | enum_J_05 | non_idp_NG021008_C01 | non_idp_NG021008_C01_H05 | aa2b0574-0a2c-4504-a192-2190735fea6c | C04 | Interview took 11 minutes
2026-09-07 | enum_J_06 | non_idp_NG021008_C01 | non_idp_NG021008_C01_H01 | ac611169-e6aa-4566-85b2-d56d184ed362 | C03 | Household already interviewed in an earlier submission
2026-09-07 | enum_J_07 | non_idp_NG021014_C06 | non_idp_NG021014_C06_H03 | f8e2de05-a227-48bd-b2a9-d8bfcb016ac9 | C04 | Interview took 6 minutes
2026-09-08 | enum_J_20 | non_idp_NG021032_C14 | non_idp_NG021032_C14_H03 | 1ed72b44-56cd-4151-8ecf-e272781fe330 | C04 | Interview took 8 minutes
2026-09-09 | enum_J_16 | idp_NG021031_C14 | idp_NG021031_C14_H03 | 341738f9-03e1-47d3-ae44-7c42191b46dd | C01 | Respondent did not consent
2026-09-09 | enum_J_20 | non_idp_NG021032_C15 | non_idp_NG021032_C15_H04 | 7e597554-1ef1-4e01-b075-1947773135ad | C01 | Respondent did not consent
2026-09-10 | enum_J_06 | non_idp_NG021007_R1_03 | non_idp_NG021007_R1_03_H05 | 2547ab69-1cd8-48e1-bad6-5f8cf18feac6 | C01 | Respondent did not consent
2026-09-10 | enum_J_06 | non_idp_NG021007_R1_03 | non_idp_NG021007_R1_03_R02 | 1894aed5-79c2-4dc7-9b1d-2a23913cab57 | C04 | Interview took 5 minutes
2026-09-10 | enum_J_09 | idp_NG021019_C02 | idp_NG021019_C02_R02 | 544b8323-fd10-4c20-ab55-e4340c507885 | C04 | Interview took 11 minutes
2026-09-10 | enum_J_15 | non_idp_NG021031_C01 | non_idp_NG021031_C01_H02 | cc7a261a-ad8f-4949-b297-fb419a025e81 | C02 | Same submission uploaded more than once
2026-09-10 | enum_J_19 | non_idp_NG021032_C16 | non_idp_NG021032_C16_R01 | b5cb10bc-c1e8-40d3-aee7-367271f9f8b2 | C01 | Respondent did not consent
2026-09-10 | enum_J_20 | non_idp_NG021032_C16 | non_idp_NG021032_C16_H01 | 25f5d8ef-4195-4b25-9437-0931d17f41c1 | C01 | Respondent did not consent
2026-09-10 | enum_J_20 | non_idp_NG021032_C16 | non_idp_NG021032_C16_R02 | 875951f6-dcda-474e-98df-a8685594745b | C03 | Household already interviewed in an earlier submission
2026-09-11 | enum_J_06 | non_idp_NG021007_R1_04 | non_idp_NG021007_R1_04_H06 | 035c6317-ba05-4898-9531-4e6cb545e087 | C04 | Interview took 6 minutes
2026-09-11 | enum_J_16 | non_idp_NG021031_C03 | non_idp_NG021031_C03_H06 | a1930535-1f33-41c8-840c-e33791bb30f1 | C01 | Respondent did not consent
2026-09-12 | enum_J_04 | non_idp_NG021001_R2_01 | non_idp_NG021001_R2_01_H05 | e600bc97-ca51-405e-b383-adccc364456e | C04 | Interview took 6 minutes
2026-09-12 | enum_J_10 | idp_NG021019_C03 | idp_NG021019_C03_R01 | 60e25964-6b85-482b-96c1-c8de2def591c | C04 | Interview took 7 minutes
2026-09-13 | enum_J_03 | non_idp_NG021001_R2_02 | non_idp_NG021001_R2_02_H01 | 797a3ce2-01b6-467b-a3d4-69eb57b4116e | C01 | Respondent did not consent
2026-09-13 | enum_J_09 | idp_NG021019_C04 | idp_NG021019_C04_H04 | 6ca47855-5088-494a-a1fe-f46afeb0d1cf | C02 | Same submission uploaded more than once
2026-09-13 | enum_J_11 | non_idp_NG021019_R2_01 | non_idp_NG021019_R2_01_H06 | 117d42ab-4d8f-49c8-861a-f4e92b349877 | C03 | Household already interviewed in an earlier submission
2026-09-13 | enum_J_15 | non_idp_NG021022_R1_01 | non_idp_NG021022_R1_01_H01 | 0a3417c9-e6bf-427c-8577-6cc2f003641f | C04 | Interview took 5 minutes
2026-09-13 | enum_J_19 | non_idp_NG021032_R1_01 | non_idp_NG021032_R1_01_H04 | fa44d764-a291-4e2d-aef7-1a0d0f08342a | C04 | Interview took 5 minutes
2026-09-14 | enum_J_06 | non_idp_NG021003_R2_C99 | non_idp_NG021003_R2_01_H05 | db7db2b7-4853-4e79-aeb7-d2620e911ee3 | C05 | Cluster code not in the sample
2026-09-15 | enum_J_01 | non_idp_NG021001_C15 | non_idp_NG021001_C15_H01 | 83d7e3f9-4f6f-42bc-8078-3576cdacab01 | C01 | Respondent did not consent
2026-09-15 | enum_J_12 | non_idp_NG021019_R2_03 | non_idp_NG021019_R2_03_H03 | 4235a910-f41d-4528-8d1a-3fe5c4462d7b | C01 | Respondent did not consent
2026-09-15 | enum_J_13 | non_idp_NG021022_C08 | non_idp_NG021022_C08_H05 | bbeaa9d8-8a1e-4cc9-bd0b-6a88a0539c35 | C01 | Respondent did not consent
2026-09-15 | enum_J_14 | non_idp_NG021022_C08 | non_idp_NG021022_C08_R01 | eae88522-e1e4-4e81-a06f-18144bf05610 | C04 | Interview took 6 minutes
2026-09-15 | enum_J_15 | non_idp_NG021022_R2_02 | non_idp_NG021022_R2_02_H01 | 094f76c8-318f-4b29-a402-2cbfb182451c | C01 | Respondent did not consent
2026-09-16 | enum_J_05 | non_idp_NG021007_R2_01 | non_idp_NG021007_R2_01_R01 | f751161a-bcb3-4d42-a688-3ab8fa982026 | C04 | Interview took 6 minutes
2026-09-16 | enum_J_09 | idp_NG021019_C07 | idp_NG021019_C07_R01 | b03719b9-9f30-4d69-ab27-b2297893cc5f | C04 | Interview took 10 minutes
2026-09-16 | enum_J_10 | idp_NG021019_C07 | idp_NG021019_C07_H02 | e99c01d3-e3dc-4370-83fe-123abc906fa0 | C04 | Interview took 7 minutes
2026-09-22 | enum_J_14 | non_idp_NG021022_C15 | non_idp_NG021022_C15_H01 | 48e2e393-8336-4507-97c1-3350094a060f | C04 | Interview took 10 minutes

## Enumerators
Enumerators
Synthetic data – not real findings
enumerator_id | interviews | median minutes | % repeated answers | interviews removed | interviews flagged | pattern
enum_J_01 | 60 | 41 | 3.3 | 4 | 1
enum_J_02 | 60 | 37.8 | 0 | 5 | 4
enum_J_03 | 70 | 41 | 0 | 4 | 3
enum_J_04 | 51 | 39.5 | 0 | 5 | 5
enum_J_05 | 57 | 39.1 | 0 | 6 | 4
enum_J_06 | 64 | 42.6 | 0 | 7 | 4
enum_J_07 | 63 | 42.3 | 3.2 | 5 | 3
enum_J_08 | 58 | 40.2 | 0 | 4 | 4
enum_J_09 | 67 | 38.6 | 3 | 4 | 2
enum_J_10 | 54 | 41.4 | 0 | 2 | 4
enum_J_11 | 54 | 43.4 | 3.7 | 5 | 0
enum_J_12 | 70 | 42.1 | 0 | 5 | 5
enum_J_13 | 55 | 45 | 0 | 2 | 4
enum_J_14 | 65 | 43.4 | 0 | 3 | 4
enum_J_15 | 63 | 41 | 3.2 | 6 | 2
enum_J_16 | 58 | 44.6 | 0 | 4 | 2
enum_J_17 | 61 | 44.2 | 0 | 0 | 1
enum_J_18 | 59 | 41.7 | 0 | 2 | 7
enum_J_19 | 58 | 45.4 | 0 | 3 | 4
enum_J_20 | 57 | 40.7 | 0 | 5 | 4

## Progress
Progress against target by LGA
Synthetic data – not real findings
adm1_name | adm2_name | pop_type | target | achieved | percent
Katsina | Bakori | idp | 54 | 46 | 85.2
Katsina | Bakori | non_idp | 102 | 93 | 91.2
Katsina | Batsari | non_idp | 102 | 95 | 93.1
Katsina | Dan Musa | non_idp | 102 | 88 | 86.3
Katsina | Dandume | non_idp | 102 | 96 | 94.1
Katsina | Funtua | non_idp | 102 | 100 | 98
Katsina | Kankara | idp | 60 | 56 | 93.3
Katsina | Kankara | non_idp | 102 | 92 | 90.2
Katsina | Kurfi | idp | 72 | 66 | 91.7
Katsina | Kurfi | non_idp | 102 | 98 | 96.1
Katsina | Sabuwa | idp | 84 | 71 | 84.5
Katsina | Sabuwa | non_idp | 102 | 102 | 100
Katsina | Safana | idp | 54 | 53 | 98.1
Katsina | Safana | non_idp | 102 | 93 | 91.2