## Summary
Data-quality digest: Partner K
Synthetic data – not real findings
Item | Value
Partner | Partner K
States | Katsina
Data as of | 2026-09-27
Submissions received | 1350
Interviews kept | 1249
Interviews removed | 101
Values corrected | 15
Interviews flagged for follow-up | 82
Households targeted | 1248
Households achieved | 1249
Progress against target | 100.1%

## Follow up
Interviews flagged: please check with the enumerator
Synthetic data – not real findings
date | enumerator_id | cluster_id | household_id | _uuid | check | issue | value
2026-08-19 | enum_K_08 | non_idp_NG021012_C01 | non_idp_NG021012_C01_H01 | 032a73d9-7fce-42f1-85de-74f7a03580ea | fcs_hhs_contradiction | Acceptable food consumption with severe hunger | FCS 51.0, HHS 4
2026-08-20 | enum_K_03 | non_idp_NG021006_C05 | non_idp_NG021006_C05_H05 | 66fa20db-c387-4dfa-ba68-ad29ccc61e27 | fcs_hhs_contradiction | Acceptable food consumption with severe hunger | FCS 93.5, HHS 6
2026-08-20 | enum_K_07 | non_idp_NG021012_C02 | non_idp_NG021012_C02_H06 | a6d3f57e-8db6-4278-951a-6616dd407aa2 | gps_far | GPS point 2.2 km from the household | 2221
2026-08-20 | enum_K_08 | non_idp_NG021012_C02 | non_idp_NG021012_C02_H05 | 8995092f-8e38-48dc-8e9a-9335ba720950 | gps_far | GPS point 4.3 km from the household | 4266
2026-08-23 | enum_K_02 | non_idp_NG021002_C01 | non_idp_NG021002_C01_R01 | f3f399ea-b25b-4bdd-a286-daec1f31f754 | children_exceed_hh | More children than household members | 0 + 8 children, household of 5
2026-08-24 | enum_K_03 | non_idp_NG021006_C07 | non_idp_NG021006_C07_H05 | dfb417fb-941d-4074-bf84-fc489dd50c0e | children_exceed_hh | More children than household members | 1 + 13 children, household of 12
2026-08-24 | enum_K_07 | non_idp_NG021012_C04 | non_idp_NG021012_C04_H02 | 46ee06de-ddef-4cac-a645-0abf86ddbbe7 | attending_exceed_school_age | More children attending school than of school age | 3
2026-08-25 | enum_K_01 | non_idp_NG021002_C04 | non_idp_NG021002_C04_H04 | 61a8fee4-dc22-41d9-a641-754ef5d04190 | gps_far | GPS point 1.0 km from the household | 1021
2026-08-25 | enum_K_01 | non_idp_NG021002_C04 | non_idp_NG021002_C04_H05 | a197356e-eeba-4f8a-99e9-296ca5f973d9 | fcs_flat | Every food group given the same number of days | 7
2026-08-25 | enum_K_03 | non_idp_NG021006_C08 | non_idp_NG021006_C08_H01 | 57fac970-fdc9-4c94-8ab4-c46eaa1600af | fcs_hhs_contradiction | Acceptable food consumption with severe hunger | FCS 93.5, HHS 6
2026-08-27 | enum_K_02 | non_idp_NG021002_C06 | non_idp_NG021002_C06_H03 | 469a3bcf-f2a3-4e2f-bb87-16416a27d5b6 | gps_far | GPS point 5.0 km from the household | 4995
2026-08-27 | enum_K_02 | non_idp_NG021002_C06 | non_idp_NG021002_C06_H06 | 7600139d-4af4-4caf-a34f-79a27911c3b7 | gps_far | GPS point 1.1 km from the household | 1058
2026-08-27 | enum_K_03 | non_idp_NG021006_C11 | non_idp_NG021006_C11_R01 | 6ce78dd1-f3cf-428d-88bc-797a0d54ec59 | fcs_hhs_contradiction | Acceptable food consumption with severe hunger | FCS 37.0, HHS 5
2026-08-27 | enum_K_04 | non_idp_NG021006_C11 | non_idp_NG021006_C11_H04 | f4183e42-8f38-4efe-8289-e9187d519f77 | fcs_hhs_contradiction | Acceptable food consumption with severe hunger | FCS 93.5, HHS 6
2026-08-27 | enum_K_07 | non_idp_NG021012_C08 | non_idp_NG021012_C08_H05 | 37a419d1-57a7-4b55-acba-5da15bff60b6 | fcs_hhs_contradiction | Acceptable food consumption with severe hunger | FCS 93.5, HHS 6
2026-08-27 | enum_K_07 | non_idp_NG021012_C08 | non_idp_NG021012_C08_R01 | 7268645e-e166-4093-847c-a353fdfb01ff | gps_far | GPS point 4.6 km from the household | 4598
2026-08-27 | enum_K_15 | non_idp_NG021025_C07 | non_idp_NG021025_C07_H01 | 16c91550-4b5b-4a43-8e08-6963722f4f6e | fcs_hhs_contradiction | Acceptable food consumption with severe hunger | FCS 40.0, HHS 4
2026-08-28 | enum_K_10 | idp_NG021017_C14 | idp_NG021017_C14_H06 | 45901c4f-40c9-454b-8a8f-5e9ce2aeea82 | gps_far | GPS point 5.0 km from the household | 4995
2026-08-28 | enum_K_12 | non_idp_NG021017_C12 | non_idp_NG021017_C12_H01 | 8bb73f9d-438a-4d2e-b92e-f7971961c898 | gps_far | GPS point 3.0 km from the household | 2989
2026-08-28 | enum_K_13 | non_idp_NG021021_C08 | non_idp_NG021021_C08_R01 | b7ae0a6a-cb11-417a-a8bb-e1269739c326 | fcs_flat | Every food group given the same number of days | 7
2026-08-28 | enum_K_18 | idp_NG021028_C09 | idp_NG021028_C09_H05 | 8aec744e-edef-407b-a7a6-91072c34a117 | gps_far | GPS point 4.3 km from the household | 4264
2026-08-29 | enum_K_01 | non_idp_NG021002_C08 | non_idp_NG021002_C08_H02 | 909ecb5b-5106-4603-a10d-3a3328d857b2 | gps_far | GPS point 0.6 km from the household | 631
2026-08-29 | enum_K_02 | non_idp_NG021002_C08 | non_idp_NG021002_C08_H01 | c363d8ef-86fd-4c3c-801b-57dfe8874a65 | fcs_flat | Every food group given the same number of days | 7
2026-08-29 | enum_K_07 | non_idp_NG021012_C10 | non_idp_NG021012_C10_R01 | 358a2a8c-0a88-4d53-b2d5-e1c08d61b1e8 | gps_far | GPS point 1.5 km from the household | 1499
2026-08-29 | enum_K_19 | non_idp_NG021029_C11 | non_idp_NG021029_C11_H03 | c46b7e92-c5cd-47cc-87ed-bbe551e1aa37 | gps_far | GPS point 4.4 km from the household | 4358
2026-08-29 | enum_K_19 | non_idp_NG021029_C11 | non_idp_NG021029_C11_H04 | c394d9c7-b656-4802-bab2-4f8048ab9164 | gps_far | GPS point 3.8 km from the household | 3828
2026-08-30 | enum_K_02 | non_idp_NG021002_C09 | non_idp_NG021002_C09_H01 | 2f66f77c-344f-4cba-9673-945d64c51097 | gps_far | GPS point 2.3 km from the household | 2289
2026-08-30 | enum_K_13 | non_idp_NG021021_C10 | non_idp_NG021021_C10_H01 | 2668d1d7-db72-4b70-8387-95f88afdb371 | gps_far | GPS point 2.6 km from the household | 2594
2026-08-31 | enum_K_02 | non_idp_NG021002_C10 | non_idp_NG021002_C10_H02 | d961d93f-2bbd-430f-933b-5f1b6c2ca9dc | fcs_flat | Every food group given the same number of days | 7
2026-08-31 | enum_K_04 | non_idp_NG021006_C12 | non_idp_NG021006_C12_R02 | 12a66347-5d94-4dc9-b003-4dcafa31bc94 | fcs_hhs_contradiction | Acceptable food consumption with severe hunger | FCS 44.5, HHS 4
2026-08-31 | enum_K_14 | non_idp_NG021021_C11 | non_idp_NG021021_C11_H02 | 85d09f4c-ecdd-4063-8552-16ef7b58ebfa | fcs_hhs_contradiction | Acceptable food consumption with severe hunger | FCS 93.5, HHS 6
2026-09-02 | enum_K_10 | non_idp_NG021017_C05 | non_idp_NG021017_C05_H04 | 16e6a5b5-578b-4a71-a314-ad9103170e36 | attending_exceed_school_age | More children attending school than of school age | 5
2026-09-02 | enum_K_11 | non_idp_NG021017_C16 | non_idp_NG021017_C16_H04 | 35d406fc-c9ac-4cd7-a478-69bcb9785c2d | gps_far | GPS point 1.3 km from the household | 1306
2026-09-02 | enum_K_11 | non_idp_NG021017_C16 | non_idp_NG021017_C16_H06 | 9d360791-abfd-47a4-9e93-b652824e9738 | gps_far | GPS point 1.9 km from the household | 1941
2026-09-02 | enum_K_16 | non_idp_NG021025_C11 | non_idp_NG021025_C11_H03 | a9a8347c-a1f5-4b90-94be-b033496ae57f | fcs_hhs_contradiction | Acceptable food consumption with severe hunger | FCS 93.5, HHS 6
2026-09-03 | enum_K_11 | non_idp_NG021017_C17 | non_idp_NG021017_C17_H01 | a6f0ca75-c3b5-4b90-8cb3-63fe842ac24d | fcs_flat | Every food group given the same number of days | 7
2026-09-03 | enum_K_13 | non_idp_NG021021_C14 | non_idp_NG021021_C14_H03 | 6de01621-8bd9-4c8c-bf53-ec733e158f2d | children_exceed_hh | More children than household members | 1 + 8 children, household of 7
2026-09-03 | enum_K_13 | non_idp_NG021021_C14 | non_idp_NG021021_C14_H04 | 785c8806-0809-4c12-8459-2e7edd50a4d8 | gps_far | GPS point 2.0 km from the household | 1960
2026-09-03 | enum_K_18 | idp_NG021028_C14 | idp_NG021028_C14_H06 | 15fa46ea-74fc-4593-9896-000d56da42b3 | attending_exceed_school_age | More children attending school than of school age | 6
2026-09-03 | enum_K_19 | non_idp_NG021029_C17 | non_idp_NG021029_C17_H04 | 09bcde43-edc9-4d7d-985a-da3614b28839 | fcs_flat | Every food group given the same number of days | 7
2026-09-03 | enum_K_20 | non_idp_NG021029_C17 | non_idp_NG021029_C17_H02 | 4c4e1d89-44c6-4b3f-ac4f-e67feb7e13e0 | fcs_hhs_contradiction | Acceptable food consumption with severe hunger | FCS 93.5, HHS 6
2026-09-04 | enum_K_03 | non_idp_NG021006_C15 | non_idp_NG021006_C15_H01 | cfb1206e-e776-4f2a-a6fd-4da2d8c350bc | fcs_flat | Every food group given the same number of days | 0
2026-09-04 | enum_K_04 | non_idp_NG021006_C15 | non_idp_NG021006_C15_H02 | 725ffb24-1553-4d44-9515-ee952de14b55 | fcs_hhs_contradiction | Acceptable food consumption with severe hunger | FCS 37.5, HHS 4
2026-09-04 | enum_K_19 | non_idp_NG021028_R1_01 | non_idp_NG021028_R1_01_H04 | 66638b4f-dd9e-4d05-a309-4ce7b7e90172 | fcs_flat | Every food group given the same number of days | 7
2026-09-04 | enum_K_19 | non_idp_NG021028_R1_01 | non_idp_NG021028_R1_01_H04 | 66638b4f-dd9e-4d05-a309-4ce7b7e90172 | fcs_hhs_contradiction | Acceptable food consumption with severe hunger | FCS 112.0, HHS 4
2026-09-05 | enum_K_08 | non_idp_NG021012_C13 | non_idp_NG021012_C13_H06 | 55c17d2c-f3c5-42a4-98c1-fee423c423e9 | fcs_flat | Every food group given the same number of days | 0
2026-09-05 | enum_K_10 | non_idp_NG021017_C08 | non_idp_NG021017_C08_H02 | 328b3fd9-f302-477b-80fb-7b2a33cba233 | gps_far | GPS point 1.8 km from the household | 1817
2026-09-05 | enum_K_14 | non_idp_NG021021_C16 | non_idp_NG021021_C16_H02 | 81ef5536-5fa5-450f-9c4a-2935e1438e12 | gps_far | GPS point 2.7 km from the household | 2732
2026-09-06 | enum_K_02 | non_idp_NG021002_C16 | non_idp_NG021002_C16_H04 | d526ff8c-cc07-480b-b33e-2be0467c49b1 | attending_exceed_school_age | More children attending school than of school age | 3
2026-09-06 | enum_K_11 | idp_NG021021_C03 | idp_NG021021_C03_H01 | d4fedca5-da56-497c-bede-9c7d90913ec3 | fcs_flat | Every food group given the same number of days | 7
2026-09-06 | enum_K_11 | idp_NG021021_C03 | idp_NG021021_C03_R01 | 5bf02754-1dc9-47d1-8928-d723004753e0 | fcs_hhs_contradiction | Acceptable food consumption with severe hunger | FCS 93.5, HHS 6
2026-09-06 | enum_K_15 | non_idp_NG021025_C16 | non_idp_NG021025_C16_H01 | 4bb917fd-5a3a-4b60-95da-503a2e4d5edb | children_exceed_hh | More children than household members | 0 + 7 children, household of 5
2026-09-06 | enum_K_15 | non_idp_NG021025_C16 | non_idp_NG021025_C16_H02 | e5a6cdd1-af4d-4720-9e82-d1960e475911 | gps_far | GPS point 2.6 km from the household | 2559
2026-09-07 | enum_K_07 | non_idp_NG021012_C16 | non_idp_NG021012_C16_H05 | 6993ed1b-102f-41dd-a1e5-cf0bd55d9f72 | gps_far | GPS point 2.1 km from the household | 2120
2026-09-07 | enum_K_13 | idp_NG021025_C01 | idp_NG021025_C01_H02 | da5dcb8c-fcee-4d76-8e1c-26b52155fcb7 | attending_exceed_school_age | More children attending school than of school age | 4
2026-09-07 | enum_K_14 | idp_NG021025_C01 | idp_NG021025_C01_H04 | e6da1cec-120d-4309-9402-12f74b75988c | fcs_hhs_contradiction | Acceptable food consumption with severe hunger | FCS 53.5, HHS 4
2026-09-07 | enum_K_15 | non_idp_NG021025_C17 | non_idp_NG021025_C17_H02 | 6bbbeee7-d2c9-4e4b-8431-fa278f19100a | gps_far | GPS point 1.1 km from the household | 1126
2026-09-07 | enum_K_15 | non_idp_NG021025_C17 | non_idp_NG021025_C17_R02 | 784c7f0f-dadb-4ea7-92d7-2609dc6038ba | fcs_flat | Every food group given the same number of days | 7
2026-09-07 | enum_K_16 | non_idp_NG021025_C17 | non_idp_NG021025_C17_H04 | c1f81768-d4a6-4212-bfe5-111d5036cded | fcs_flat | Every food group given the same number of days | 0
2026-09-08 | enum_K_15 | idp_NG021028_C01 | idp_NG021028_C01_H06 | 9f9330e6-7d44-4d33-b6aa-4389a9757cb2 | fcs_hhs_contradiction | Acceptable food consumption with severe hunger | FCS 41.5, HHS 4
2026-09-09 | enum_K_01 | non_idp_NG021006_C02 | non_idp_NG021006_C02_H02 | 3dfd8435-7ef9-4155-9325-0f52d59598d3 | fcs_hhs_contradiction | Acceptable food consumption with severe hunger | FCS 44.5, HHS 4
2026-09-09 | enum_K_01 | non_idp_NG021006_C02 | non_idp_NG021006_C02_H05 | a990e94d-369c-4943-b70e-c2470475808e | children_exceed_hh | More children than household members | 0 + 6 children, household of 5
2026-09-10 | enum_K_05 | idp_NG021012_C07 | idp_NG021012_C07_H01 | b82c4a1a-7d1e-4ec1-b93f-bdb329fdd92a | children_exceed_hh | More children than household members | 1 + 5 children, household of 5
2026-09-10 | enum_K_07 | non_idp_NG021012_C17 | non_idp_NG021012_C17_H04 | d46b7d36-1983-4fcd-ba2e-4cbc57a81cc4 | fcs_hhs_contradiction | Acceptable food consumption with severe hunger | FCS 57.0, HHS 4
2026-09-10 | enum_K_08 | non_idp_NG021012_C17 | non_idp_NG021012_C17_H06 | 90d11ab3-cb7f-4179-b306-60c1fb60a24a | gps_far | GPS point 1.5 km from the household | 1504
2026-09-11 | enum_K_06 | idp_NG021012_C08 | idp_NG021012_C08_H06 | f60f789a-7cf6-4811-84e3-ab1ac374cbbc | gps_far | GPS point 3.3 km from the household | 3311
2026-09-11 | enum_K_15 | idp_NG021028_C03 | idp_NG021028_C03_R01 | 99a962ae-7205-4556-af84-18c2629cb04c | gps_far | GPS point 3.7 km from the household | 3710
2026-09-11 | enum_K_17 | non_idp_NG021028_C05 | non_idp_NG021028_C05_H04 | 284ee8b9-6188-411c-83cb-b936d648f4cd | fcs_flat | Every food group given the same number of days | 0
2026-09-12 | enum_K_15 | idp_NG021028_C04 | idp_NG021028_C04_H02 | 2df44dbc-cc36-41e5-a368-757003abb7f3 | gps_far | GPS point 4.1 km from the household | 4072
2026-09-13 | enum_K_06 | idp_NG021012_C09 | idp_NG021012_C09_H01 | 9390c1e0-34be-40da-afc7-a9365473b8fd | fcs_hhs_contradiction | Acceptable food consumption with severe hunger | FCS 93.5, HHS 6
2026-09-14 | enum_K_04 | non_idp_NG021009_C05 | non_idp_NG021009_C05_H02 | ae90a601-b677-464b-a92e-b9f0658f70f7 | gps_far | GPS point 3.3 km from the household | 3333
2026-09-14 | enum_K_05 | idp_NG021012_C10 | idp_NG021012_C10_H02 | 8b4f76a2-c28b-4907-a28e-f82176446b7d | gps_far | GPS point 0.8 km from the household | 770
2026-09-15 | enum_K_15 | idp_NG021028_C06 | idp_NG021028_C06_R01 | 9006a184-d2a3-49e0-bd9c-b71cd0ae9d32 | fcs_hhs_contradiction | Acceptable food consumption with severe hunger | FCS 53.0, HHS 4
2026-09-15 | enum_K_16 | idp_NG021028_C06 | idp_NG021028_C06_H01 | 1b941143-5646-4ded-b4b0-3ebc0ee47306 | gps_far | GPS point 2.8 km from the household | 2814
2026-09-17 | enum_K_03 | non_idp_NG021009_C06 | non_idp_NG021009_C06_H06 | fc89b213-7b6f-42ca-a16f-14e622a4885e | children_exceed_hh | More children than household members | 0 + 8 children, household of 6
2026-09-17 | enum_K_07 | non_idp_NG021012_R1_02 | non_idp_NG021012_R1_02_R01 | ef3c8195-269b-4719-b155-b599918a3cad | gps_far | GPS point 0.8 km from the household | 826
2026-09-17 | enum_K_18 | non_idp_NG021028_C10 | non_idp_NG021028_C10_H06 | 3fb48eda-16b9-4961-af3c-c84c57032f8a | gps_far | GPS point 2.5 km from the household | 2492
2026-09-18 | enum_K_03 | non_idp_NG021009_C07 | non_idp_NG021009_C07_H03 | 475b62c2-6c0e-4088-986d-1a5e3d29d09c | gps_far | GPS point 2.0 km from the household | 1982
2026-09-18 | enum_K_04 | non_idp_NG021009_C07 | non_idp_NG021009_C07_H05 | 9b94a2f6-766a-4a75-838c-682aeda034b6 | attending_exceed_school_age | More children attending school than of school age | 4
2026-09-18 | enum_K_04 | non_idp_NG021009_C07 | non_idp_NG021009_C07_H06 | ce25ece4-187b-4cae-ae25-15d7f37a5d94 | fcs_hhs_contradiction | Acceptable food consumption with severe hunger | FCS 41.0, HHS 4
2026-09-18 | enum_K_12 | idp_NG021021_C11 | idp_NG021021_C11_H03 | 72b5c4a5-2326-46ed-8c94-f75a92eb2d0e | fcs_flat | Every food group given the same number of days | 7
2026-09-18 | enum_K_12 | idp_NG021021_C11 | idp_NG021021_C11_H03 | 72b5c4a5-2326-46ed-8c94-f75a92eb2d0e | fcs_hhs_contradiction | Acceptable food consumption with severe hunger | FCS 112.0, HHS 4
2026-09-22 | enum_K_01 | non_idp_NG021006_C04 | non_idp_NG021006_C04_R03 | 1b632529-926e-4608-848e-50982a5be587 | fcs_hhs_contradiction | Acceptable food consumption with severe hunger | FCS 37.0, HHS 5
2026-09-23 | enum_K_17 | non_idp_NG021028_C14 | non_idp_NG021028_C14_H06 | f28a8ae6-6dc1-4554-bc4c-ea319807cb2c | gps_far | GPS point 2.5 km from the household | 2472

## Removed
Interviews removed from the dataset, and why
Synthetic data – not real findings
date | enumerator_id | cluster_id | household_id | _uuid | check_id | reason
2026-08-19 | enum_K_08 | non_idp_NG021012_C01 | non_idp_NG021012_C01_H01 | 032a73d9-7fce-42f1-85de-74f7a03580ea | C04 | Interview took 9 minutes
2026-08-20 | enum_K_13 | non_idp_NG021021_C03 | non_idp_NG021021_C03_H05 | 0e02d7b6-d053-4db5-88c3-207d2d045e43 | C04 | Interview took 10 minutes
2026-08-20 | enum_K_14 | non_idp_NG021021_C03 | non_idp_NG021021_C03_H06 | 72e49162-7e53-48f0-9f04-b153c5f9e20a | C04 | Interview took 11 minutes
2026-08-22 | enum_K_09 | idp_NG021017_C08 | idp_NG021017_C08_R01 | 8ab147b9-2b57-4175-a99d-9b6926c5d519 | C02 | Same submission uploaded more than once
2026-08-23 | enum_K_14 | non_idp_NG021021_C05 | non_idp_NG021021_C05_H06 | b6f64f24-649b-4b07-a8aa-36119dce4102 | C04 | Interview took 12 minutes
2026-08-24 | enum_K_03 | non_idp_NG021006_C07 | non_idp_NG021006_C07_H01 | 88665cda-b88b-4111-8af5-a3762eafeea6 | C01 | Respondent did not consent
2026-08-24 | enum_K_05 | non_idp_NG021009_C09 | non_idp_NG021009_C09_H06 | c01c2bf8-f2a1-4504-bb5b-4b9a39963626 | C04 | Interview took 6 minutes
2026-08-24 | enum_K_06 | non_idp_NG021009_C09 | non_idp_NG021009_C09_H03 | d302fea1-28e2-49aa-b8ff-c881be8ab0de | C04 | Interview took 8 minutes
2026-08-24 | enum_K_07 | non_idp_NG021012_C04 | non_idp_NG021012_C04_H05 | aec0fef8-54fe-48b4-95af-143bf8075ad1 | C04 | Interview took 10 minutes
2026-08-24 | enum_K_12 | non_idp_NG021017_C10 | non_idp_NG021017_C10_H05 | f54a3c2f-a312-4753-a89c-48a7a802e66e | C01 | Respondent did not consent
2026-08-25 | enum_K_04 | non_idp_NG021006_C08 | non_idp_NG021006_C08_H06 | e8661294-23e0-4e0b-a9b3-b0f1dafcf79d | C04 | Interview took 6 minutes
2026-08-26 | enum_K_02 | non_idp_NG021002_C05 | non_idp_NG021002_C05_H02 | b985bd96-e367-4e6f-b776-ae9ec8d13497 | C04 | Interview took 11 minutes
2026-08-26 | enum_K_08 | non_idp_NG021012_C07 | non_idp_NG021012_C07_R01 | a81ce663-d39d-4815-bb88-229300506322 | C04 | Interview took 7 minutes
2026-08-26 | enum_K_10 | idp_NG021017_C12 | idp_NG021017_C12_H01 | 18b12687-0a7a-44cf-a591-d1b6785bbb8c | C04 | Interview took 10 minutes
2026-08-26 | enum_K_11 | non_idp_NG021017_C11 | non_idp_NG021017_C11_H02 | 97504c44-bd6a-4dae-8ab6-f32225fbe435 | C04 | Interview took 8 minutes
2026-08-26 | enum_K_12 | non_idp_NG021017_C11 | non_idp_NG021017_C11_H05 | 13e6e801-124f-46af-ab44-337cded0b46e | C04 | Interview took 6 minutes
2026-08-26 | enum_K_15 | non_idp_NG021025_C06 | non_idp_NG021025_C06_H02 | 7f1b7ada-12c7-44bf-a382-af18d403ad6e | C04 | Interview took 10 minutes
2026-08-26 | enum_K_16 | non_idp_NG021025_C06 | non_idp_NG021025_C06_H01 | d159a404-4d57-46d9-8270-9e5114fc87f6 | C03 | Household already interviewed in an earlier submission
2026-08-27 | enum_K_07 | non_idp_NG021012_C08 | non_idp_NG021012_C08_H04 | 03bede2f-a2e2-4d08-aaaa-77b1b6156d2d | C04 | Interview took 8 minutes
2026-08-27 | enum_K_10 | idp_NG021017_C13 | idp_NG021017_C13_H02 | af962005-128c-4947-8056-9aa46983c93d | C02 | Same submission uploaded more than once
2026-08-27 | enum_K_13 | non_idp_NG021021_C07 | non_idp_NG021021_C07_H03 | 7c57b995-4010-4f43-b4b5-1c132e2ddf23 | C02 | Same submission uploaded more than once
2026-08-27 | enum_K_15 | non_idp_NG021025_C07 | non_idp_NG021025_C07_H01 | 16c91550-4b5b-4a43-8e08-6963722f4f6e | C04 | Interview took 6 minutes
2026-08-27 | enum_K_15 | non_idp_NG021025_C07 | non_idp_NG021025_C07_H02 | 8864cced-8049-4fce-9dd2-5d8ae8b00739 | C04 | Interview took 9 minutes
2026-08-27 | enum_K_15 | non_idp_NG021025_C07 | non_idp_NG021025_C07_H05 | 1e8c1286-0880-4be0-93f1-562543fb0da8 | C01 | Respondent did not consent
2026-08-28 | enum_K_04 | non_idp_NG021006_C12 | non_idp_NG021006_C12_R01 | a1747dd8-e267-4115-8c98-125d96a47006 | C04 | Interview took 9 minutes
2026-08-28 | enum_K_07 | non_idp_NG021012_C09 | non_idp_NG021012_C09_H02 | 89aab4fd-9aeb-4bf3-995b-2b5a436c43e2 | C03 | Household already interviewed in an earlier submission
2026-08-28 | enum_K_12 | non_idp_NG021017_C12 | non_idp_NG021017_C12_H05 | 25699613-a877-4843-8d0f-84df8b0742b1 | C01 | Respondent did not consent
2026-08-28 | enum_K_12 | non_idp_NG021017_C12 | non_idp_NG021017_C12_H06 | b426d633-2aeb-4633-aee5-61e06a78aab4 | C03 | Household already interviewed in an earlier submission
2026-08-28 | enum_K_13 | non_idp_NG021021_C08 | non_idp_NG021021_C08_H02 | eb3b4d86-af96-45c7-a6e5-6b36144f00d5 | C01 | Respondent did not consent
2026-08-28 | enum_K_17 | idp_NG021028_C10 | idp_NG021028_C10_H03 | 149144b9-729d-473a-afa6-e716ea94cccc | C04 | Interview took 6 minutes
2026-08-28 | enum_K_18 | idp_NG021028_C09 | idp_NG021028_C09_H02 | f4156118-0007-47e9-9a0e-f20c215bd1cf | C04 | Interview took 5 minutes
2026-08-29 | enum_K_12 | non_idp_NG021017_C13 | non_idp_NG021017_C13_R01 | ecedac5f-e2d5-43bd-8e4e-4b33cc9ada0e | C04 | Interview took 6 minutes
2026-08-29 | enum_K_20 | non_idp_NG021029_C11 | non_idp_NG021029_C11_R01 | 88aaa8e3-2928-494e-9f23-d67ad3c05a7e | C01 | Respondent did not consent
2026-08-30 | enum_K_07 | non_idp_NG021012_C11 | non_idp_NG021012_C11_H06 | 0217d1bc-5939-4d47-aae7-7a44b7db9386 | C01 | Respondent did not consent
2026-08-30 | enum_K_12 | non_idp_NG021017_C14 | non_idp_NG021017_C14_H01 | 2973a7ca-edab-4b3b-a733-aa5b29721675 | C01 | Respondent did not consent
2026-08-31 | enum_K_12 | non_idp_NG021017_C15 | non_idp_NG021017_C15_H01 | a5f5eade-8fd7-44ee-a4db-2d435dcb278d | C04 | Interview took 11 minutes
2026-08-31 | enum_K_17 | idp_NG021028_C12 | idp_NG021028_C12_H03 | 77a7df8d-40e6-4d35-a9b1-2adb5acc0f9d | C01 | Respondent did not consent
2026-08-31 | enum_K_18 | idp_NG021028_C12 | idp_NG021028_C12_H05 | 1739a7aa-3497-4a6e-9c89-65d405a22a52 | C04 | Interview took 12 minutes
2026-08-31 | enum_K_18 | idp_NG021028_C12 | idp_NG021028_C12_H06 | d6d5cefc-94d4-420c-9b11-01bc9b2fabe1 | C01 | Respondent did not consent
2026-08-31 | enum_K_18 | idp_NG021028_C12 | idp_NG021028_C12_R02 | bf6035eb-db70-4e3e-a149-28e5ad7e815c | C01 | Respondent did not consent
2026-09-01 | enum_K_01 | non_idp_NG021002_C11 | non_idp_NG021002_C11_R01 | 0f9f0370-e508-4e97-85d5-154ef2aed251 | C04 | Interview took 10 minutes
2026-09-01 | enum_K_09 | non_idp_NG021017_C04 | non_idp_NG021017_C04_H04 | a7e59324-70a0-452c-a413-d6792cf29e9f | C01 | Respondent did not consent
2026-09-01 | enum_K_15 | non_idp_NG021025_C10 | non_idp_NG021025_C10_H01 | 98f0ad6b-642e-4bd2-8a86-6a5da7272987 | C03 | Household already interviewed in an earlier submission
2026-09-02 | enum_K_18 | idp_NG021028_C13 | idp_NG021028_C13_H04 | 7a949411-dfa0-4ee8-b1c3-dd64aa01ea62 | C04 | Interview took 5 minutes
2026-09-03 | enum_K_03 | non_idp_NG021006_C14 | non_idp_NG021006_C14_H01 | c0392ee6-2c61-4c5f-a9dc-bcbbd954382a | C02 | Same submission uploaded more than once
2026-09-03 | enum_K_15 | non_idp_NG021025_C12 | non_idp_NG021025_C12_H03 | 2cdb8f93-99ee-445a-b8f4-324d154b3cfa | C01 | Respondent did not consent
2026-09-03 | enum_K_15 | non_idp_NG021025_C12 | non_idp_NG021025_C12_H04 | 6d6ea813-2000-4880-8d30-170ac31536bf | C02 | Same submission uploaded more than once
2026-09-03 | enum_K_16 | non_idp_NG021025_C12 | non_idp_NG021025_C12_H02 | 691e2c43-5d45-4f6b-9e82-cf1cb3bdb192 | C04 | Interview took 5 minutes
2026-09-03 | enum_K_19 | non_idp_NG021029_C17 | non_idp_NG021029_C17_H01 | abd8e6a1-1e47-4b36-837b-8c483c40cf04 | C03 | Household already interviewed in an earlier submission
2026-09-03 | enum_K_20 | non_idp_NG021029_C17 | non_idp_NG021029_C17_H05 | 0c4d2575-6cb9-40ba-88f5-ba438e32e73c | C01 | Respondent did not consent
2026-09-04 | enum_K_11 | idp_NG021021_C01 | idp_NG021021_C01_H06 | 51c6ccb5-2045-41f7-abd2-13594e17420f | C04 | Interview took 10 minutes
2026-09-04 | enum_K_16 | non_idp_NG021025_C13 | non_idp_NG021025_C13_H02 | 8fae3e0a-2008-496e-9de4-4a2acb6cc20a | C01 | Respondent did not consent
2026-09-04 | enum_K_20 | non_idp_NG021028_R1_01 | non_idp_NG021028_R1_01_H01 | bb802f49-582b-4e04-bb70-09cbbe85bb6e | C01 | Respondent did not consent
2026-09-05 | enum_K_10 | non_idp_NG021017_C08 | non_idp_NG021017_C08_H04 | be10a4fc-66ce-4ea2-ad7e-a17565323cf2 | C04 | Interview took 9 minutes
2026-09-05 | enum_K_15 | non_idp_NG021025_C14 | non_idp_NG021025_C14_H05 | 6c6f8692-8b0b-440c-a08b-d70e0d13cccb | C04 | Interview took 7 minutes
2026-09-05 | enum_K_18 | idp_NG021028_C15 | idp_NG021028_C15_H02 | 23456b76-44ba-495c-a477-fd95dc869429 | C04 | Interview took 8 minutes
2026-09-05 | enum_K_18 | idp_NG021028_C15 | idp_NG021028_C15_H03 | c44ef10c-7d83-4520-9451-7e865d52019f | C04 | Interview took 5 minutes
2026-09-06 | enum_K_09 | non_idp_NG021017_C09 | non_idp_NG021017_C09_H06 | 390f7950-9247-48bd-a0bf-4423a8264d57 | C01 | Respondent did not consent
2026-09-06 | enum_K_13 | non_idp_NG021021_C17 | non_idp_NG021021_C17_H02 | 5bc125c0-3bda-4178-85d9-d1e43cedfc3c | C04 | Interview took 4 minutes
2026-09-06 | enum_K_14 | non_idp_NG021021_C17 | non_idp_NG021021_C17_H03 | 15f4366b-5f85-43dc-a3e4-43cda36f67d9 | C04 | Interview took 10 minutes
2026-09-07 | enum_K_06 | idp_NG021012_C05 | idp_NG021012_C05_H04 | d0536f1e-1d53-4a23-b3c2-01c4f2ab64d9 | C01 | Respondent did not consent
2026-09-07 | enum_K_15 | non_idp_NG021025_C17 | non_idp_NG021025_C17_H05 | 630985ad-93ea-4dea-8246-a29543c92d9b | C01 | Respondent did not consent
2026-09-08 | enum_K_03 | non_idp_NG021009_C01 | non_idp_NG021009_C01_H02 | 47afccc5-9fd4-497e-9175-215538291ff8 | C01 | Respondent did not consent
2026-09-08 | enum_K_11 | idp_NG021021_C05 | idp_NG021021_C05_H01 | 5bad2cd6-3482-4a92-adc4-2076e280ee68 | C01 | Respondent did not consent
2026-09-08 | enum_K_13 | non_idp_NG021025_C01 | non_idp_NG021025_C01_R01 | d932e1b8-309f-4a6e-a81b-0fce41a5b08a | C04 | Interview took 9 minutes
2026-09-08 | enum_K_19 | non_idp_NG021029_R1_02 | non_idp_NG021029_R1_02_H04 | 942246c8-0020-4804-802a-2b8ed237acc9 | C04 | Interview took 5 minutes
2026-09-09 | enum_K_02 | non_idp_NG021006_C02 | non_idp_NG021006_C02_R01 | 1fed250f-2b2b-42f4-8947-3234a2ec1282 | C04 | Interview took 11 minutes
2026-09-09 | enum_K_11 | idp_NG021021_C06 | idp_NG021021_C06_H01 | 9bb0c08c-a51f-4e7e-ba97-2b06ca16dff1 | C04 | Interview took 8 minutes
2026-09-09 | enum_K_18 | non_idp_NG021028_C97 | non_idp_NG021028_C03_H02 | 473e5880-cec4-40dc-a614-25b4b67f9481 | C05 | Cluster code not in the sample
2026-09-09 | enum_K_20 | non_idp_NG021029_R1_03 | non_idp_NG021029_R1_03_H01 | 0945f3bb-fdae-4101-aae3-96f7946a566c | C01 | Respondent did not consent
2026-09-10 | enum_K_05 | idp_NG021012_C07 | idp_NG021012_C07_H02 | e4592be6-c54c-4c07-a81e-4d9db8174bf9 | C01 | Respondent did not consent
2026-09-10 | enum_K_06 | idp_NG021012_C07 | idp_NG021012_C07_R01 | 9abad599-0f7b-432a-837e-fedfeffaee24 | C04 | Interview took 7 minutes
2026-09-10 | enum_K_12 | idp_NG021021_C07 | idp_NG021021_C07_H01 | 8f990ada-e61a-41d3-a156-8e54c33492ba | C02 | Same submission uploaded more than once
2026-09-10 | enum_K_19 | non_idp_NG021029_R1_04 | non_idp_NG021029_R1_04_H06 | 186626b8-dab6-4706-9543-26c9d9b905d6 | C04 | Interview took 6 minutes
2026-09-11 | enum_K_04 | non_idp_NG021009_C03 | non_idp_NG021009_C03_H03 | eb4513ac-b1b6-4f76-8df0-3662de8845c5 | C04 | Interview took 5 minutes
2026-09-12 | enum_K_01 | non_idp_NG021006_C04 | non_idp_NG021006_C04_H01 | 682839f5-d647-4b4b-b8ad-ecf0c3e853c1 | C01 | Respondent did not consent
2026-09-12 | enum_K_01 | non_idp_NG021006_C04 | non_idp_NG021006_C04_R02 | 0c4dd4ab-b232-4727-83ba-2738b5ccb8c4 | C04 | Interview took 5 minutes
2026-09-12 | enum_K_04 | non_idp_NG021009_C04 | non_idp_NG021009_C04_H04 | 16a57b90-5ae6-4da3-9abd-47ff9726d6c6 | C01 | Respondent did not consent
2026-09-12 | enum_K_07 | idp_NG021017_C01 | idp_NG021017_C01_H04 | 34691047-7fe6-4e39-8a7e-462ca7af3dca | C01 | Respondent did not consent
2026-09-12 | enum_K_07 | idp_NG021017_C01 | idp_NG021017_C01_H06 | e145b506-67d9-4062-a647-c9a37cd77e36 | C04 | Interview took 7 minutes
2026-09-12 | enum_K_08 | idp_NG021017_C92 | idp_NG021017_C01_H01 | 74033f5c-dbeb-4029-bb0f-8628ecf36011 | C05 | Cluster code not in the sample
2026-09-12 | enum_K_15 | idp_NG021028_C04 | idp_NG021028_C04_H03 | 38a903d4-b684-4967-b807-818deb498e75 | C02 | Same submission uploaded more than once
2026-09-12 | enum_K_16 | idp_NG021028_C04 | idp_NG021028_C04_H05 | 153849c2-01cb-4ba9-a2e7-4cdf94373964 | C03 | Household already interviewed in an earlier submission
2026-09-13 | enum_K_02 | non_idp_NG021002_R1_01 | non_idp_NG021002_R1_01_H01 | d8a4ab4c-4fc0-43dd-a10f-7b0014246654 | C01 | Respondent did not consent
2026-09-13 | enum_K_05 | idp_NG021012_C09 | idp_NG021012_C09_H05 | cc2e1852-05a9-4ada-b886-f996de3f5939 | C04 | Interview took 9 minutes
2026-09-13 | enum_K_05 | idp_NG021012_C09 | idp_NG021012_C09_H06 | e3b2d243-9176-47a8-80f3-2e9ed98bae57 | C03 | Household already interviewed in an earlier submission
2026-09-13 | enum_K_06 | idp_NG021012_C09 | idp_NG021012_C09_H02 | fc796ebe-b66b-4ea5-be87-9c27335c1681 | C01 | Respondent did not consent
2026-09-13 | enum_K_07 | idp_NG021017_C02 | idp_NG021017_C02_H04 | 52b7d8b9-0fdb-4dea-ad35-1d5ebdebef27 | C01 | Respondent did not consent
2026-09-14 | enum_K_17 | non_idp_NG021028_C06 | non_idp_NG021028_C06_H03 | c1f98bfd-f20c-4e28-ae63-4029e20942c8 | C01 | Respondent did not consent
2026-09-15 | enum_K_17 | non_idp_NG021028_C08 | non_idp_NG021028_C08_H06 | 684e096f-b6b5-4786-a47e-2fdaed9eba51 | C02 | Same submission uploaded more than once
2026-09-17 | enum_K_04 | non_idp_NG021009_C06 | non_idp_NG021009_C06_H03 | 6a20c115-cfed-49b8-a955-27a818504346 | C04 | Interview took 5 minutes
2026-09-17 | enum_K_04 | non_idp_NG021009_C06 | non_idp_NG021009_C06_H05 | db7049b1-e4de-43be-8c50-a9de1a64b880 | C04 | Interview took 10 minutes
2026-09-17 | enum_K_15 | idp_NG021028_C07 | idp_NG021028_C07_H03 | 5e2a5e2b-10df-4b53-8572-1dd58a5a03f8 | C01 | Respondent did not consent
2026-09-17 | enum_K_18 | non_idp_NG021028_C10 | non_idp_NG021028_C10_H02 | 75aa33c8-5179-42c0-b873-7eaadb9272ee | C04 | Interview took 10 minutes
2026-09-18 | enum_K_12 | idp_NG021021_C11 | idp_NG021021_C11_H02 | ab5a6d90-9f7f-4d62-aa65-860a32febb7e | C01 | Respondent did not consent
2026-09-18 | enum_K_17 | non_idp_NG021028_C11 | non_idp_NG021028_C11_H01 | 9cf3a0c0-13c0-4856-a4e7-5ef1aa3d38c0 | C02 | Same submission uploaded more than once
2026-09-19 | enum_K_04 | non_idp_NG021006_R2_01 | non_idp_NG021006_R2_01_H02 | 4d407ad3-2858-4cae-a506-99c0ce00dc98 | C04 | Interview took 7 minutes
2026-09-20 | enum_K_11 | non_idp_NG021021_C01 | non_idp_NG021021_C01_H03 | 8c570050-9074-409e-bdf0-1dbe924ef19e | C04 | Interview took 7 minutes
2026-09-20 | enum_K_17 | non_idp_NG021028_C90 | non_idp_NG021028_C12_H04 | de929a9c-c855-4520-902a-057d4d8856c4 | C05 | Cluster code not in the sample
2026-09-20 | enum_K_18 | non_idp_NG021028_C12 | non_idp_NG021028_C12_H06 | 0b3a9af1-a338-44b7-b723-044430248739 | C04 | Interview took 8 minutes
2026-09-20 | enum_K_18 | non_idp_NG021028_C12 | non_idp_NG021028_C12_R01 | 0469e7c3-4f2c-4431-8c25-20ffb0995166 | C02 | Same submission uploaded more than once

## Enumerators
Enumerators
Synthetic data – not real findings
enumerator_id | interviews | median minutes | % repeated answers | interviews removed | interviews flagged | pattern
enum_K_01 | 66 | 42.4 | 0 | 3 | 6
enum_K_02 | 64 | 42 | 0 | 3 | 7
enum_K_03 | 65 | 42 | 3.1 | 3 | 7
enum_K_04 | 68 | 40.7 | 0 | 7 | 6
enum_K_05 | 67 | 40.7 | 0 | 4 | 2
enum_K_06 | 64 | 44 | 0 | 4 | 2
enum_K_07 | 70 | 44.3 | 0 | 7 | 8
enum_K_08 | 63 | 43.5 | 0 | 3 | 4
enum_K_09 | 60 | 39.6 | 3.3 | 3 | 0
enum_K_10 | 64 | 40.1 | 3.1 | 3 | 3
enum_K_11 | 63 | 43.4 | 0 | 5 | 5
enum_K_12 | 72 | 40.1 | 2.8 | 9 | 2
enum_K_13 | 71 | 40.7 | 2.8 | 5 | 5
enum_K_14 | 63 | 41.6 | 0 | 3 | 3
enum_K_15 | 81 | 39.8 | 7.4 | 11 | 9
enum_K_16 | 55 | 45.9 | 3.6 | 4 | 3
enum_K_17 | 63 | 42.3 | 6.3 | 6 | 2
enum_K_18 | 76 | 40.9 | 2.6 | 11 | 3
enum_K_19 | 66 | 43.1 | 0 | 3 | 4
enum_K_20 | 57 | 40.5 | 0 | 4 | 1

## Progress
Progress against target by LGA
Synthetic data – not real findings
adm1_name | adm2_name | pop_type | target | achieved | percent
Katsina | Batagarawa | non_idp | 102 | 102 | 100
Katsina | Charanchi | non_idp | 102 | 102 | 100
Katsina | Danja | idp | 6 | 6 | 100
Katsina | Danja | non_idp | 102 | 102 | 100
Katsina | Dutsin-Ma | idp | 72 | 72 | 100
Katsina | Dutsin-Ma | non_idp | 102 | 102 | 100
Katsina | Kafur | idp | 84 | 84 | 100
Katsina | Kafur | non_idp | 102 | 102 | 100
Katsina | Katsina | idp | 72 | 72 | 100
Katsina | Katsina | non_idp | 102 | 102 | 100
Katsina | Malumfashi | idp | 6 | 7 | 116.7
Katsina | Malumfashi | non_idp | 102 | 102 | 100
Katsina | Matazu | idp | 90 | 90 | 100
Katsina | Matazu | non_idp | 102 | 102 | 100
Katsina | Musawa | non_idp | 102 | 102 | 100