## Summary
Data-quality digest: Partner M
Synthetic data – not real findings
Item | Value
Partner | Partner M
States | Kebbi
Data as of | 2026-09-27
Submissions received | 1030
Interviews kept | 956
Interviews removed | 74
Values corrected | 10
Interviews flagged for follow-up | 69
Households targeted | 1032
Households achieved | 956
Progress against target | 92.6%

## Follow up
Interviews flagged: please check with the enumerator
Synthetic data – not real findings
date | enumerator_id | cluster_id | household_id | _uuid | check | issue | value
2026-08-21 | enum_M_03 | non_idp_NG022005_C14 | non_idp_NG022005_C14_R01 | ac3a412c-8692-423c-aa64-c8455078463c | gps_far | GPS point 2.0 km from the household | 2024
2026-08-24 | enum_M_04 | non_idp_NG022005_C17 | non_idp_NG022005_C17_R01 | c4ab7239-5757-47b0-8e95-5f58c9b27687 | fcs_hhs_contradiction | Acceptable food consumption with severe hunger | FCS 93.5, HHS 6
2026-08-24 | enum_M_05 | non_idp_NG022006_C05 | non_idp_NG022006_C05_H05 | 49088c6f-e263-4cc4-8841-4040fa888a1e | fcs_hhs_contradiction | Acceptable food consumption with severe hunger | FCS 50.5, HHS 4
2026-08-25 | enum_M_03 | idp_NG022006_C01 | idp_NG022006_C01_H01 | 1b6b8ad5-80fb-4e86-b0e0-edb80617a717 | gps_far | GPS point 4.2 km from the household | 4247
2026-08-25 | enum_M_04 | idp_NG022006_C01 | idp_NG022006_C01_H02 | b13ce831-414c-4249-b0b6-4ac037acc49b | fcs_hhs_contradiction | Acceptable food consumption with severe hunger | FCS 36.5, HHS 4
2026-08-26 | enum_M_07 | non_idp_NG022007_C07 | non_idp_NG022007_C07_H04 | 224aedeb-6d6d-401c-b07f-a6a7efe8dd73 | gps_far | GPS point 3.7 km from the household | 3721
2026-08-26 | enum_M_14 | non_idp_NG022014_C03 | non_idp_NG022014_C03_H01 | 0bda2fb3-eeb5-403b-b607-c3d7f709669a | fcs_hhs_contradiction | Acceptable food consumption with severe hunger | FCS 58.5, HHS 4
2026-08-26 | enum_M_15 | idp_NG022018_C08 | idp_NG022018_C08_H06 | b6614ffa-7843-4634-94b8-ac82e638c4c0 | fcs_hhs_contradiction | Acceptable food consumption with severe hunger | FCS 93.5, HHS 6
2026-08-27 | enum_M_05 | non_idp_NG022006_C08 | non_idp_NG022006_C08_H03 | 7b2e4fa7-a5ea-4a5e-8abe-6ee2443c5072 | fcs_hhs_contradiction | Acceptable food consumption with severe hunger | FCS 93.5, HHS 6
2026-08-27 | enum_M_11 | non_idp_NG022013_C08 | non_idp_NG022013_C08_H01 | fb12e267-98eb-4f92-b3be-2439cb887826 | gps_far | GPS point 2.8 km from the household | 2779
2026-08-28 | enum_M_12 | non_idp_NG022013_C09 | non_idp_NG022013_C09_H04 | c9366772-f9fd-4baf-b54c-20b11c4cf53f | gps_far | GPS point 4.2 km from the household | 4230
2026-08-28 | enum_M_13 | non_idp_NG022014_C05 | non_idp_NG022014_C05_H06 | 8df2d26f-cfef-4be3-ad08-6a568911090d | gps_far | GPS point 4.4 km from the household | 4390
2026-08-29 | enum_M_10 | non_idp_NG022012_C01 | non_idp_NG022012_C01_H01 | 9d1fb301-e2df-49a9-8544-4b7f9e39b77b | fcs_hhs_contradiction | Acceptable food consumption with severe hunger | FCS 36.0, HHS 5
2026-08-29 | enum_M_13 | non_idp_NG022014_C06 | non_idp_NG022014_C06_H04 | 16eb2c87-5379-4667-a859-3f47d53fb95b | gps_far | GPS point 1.4 km from the household | 1367
2026-08-29 | enum_M_13 | non_idp_NG022014_C06 | non_idp_NG022014_C06_R01 | 23a10d09-cc78-40a6-81da-7ab9441b4ef9 | fcs_hhs_contradiction | Acceptable food consumption with severe hunger | FCS 93.5, HHS 6
2026-08-30 | enum_M_09 | non_idp_NG022012_C03 | non_idp_NG022012_C03_H05 | ba89c4db-45db-4d4d-976c-873539e2f509 | fcs_hhs_contradiction | Acceptable food consumption with severe hunger | FCS 46.0, HHS 4
2026-08-31 | enum_M_01 | idp_NG022005_C05 | idp_NG022005_C05_H05 | cac3d5a5-e267-4b20-b7eb-cdb8aaa41ab8 | fcs_hhs_contradiction | Acceptable food consumption with severe hunger | FCS 42.0, HHS 4
2026-08-31 | enum_M_03 | idp_NG022006_C07 | idp_NG022006_C07_H02 | 69684a8e-6e17-498e-869d-2a1e46c2dab6 | fcs_hhs_contradiction | Acceptable food consumption with severe hunger | FCS 43.0, HHS 4
2026-08-31 | enum_M_05 | non_idp_NG022006_C11 | non_idp_NG022006_C11_H04 | 5b35404d-541f-4cf0-acd0-decbbec518f2 | fcs_hhs_contradiction | Acceptable food consumption with severe hunger | FCS 93.5, HHS 6
2026-08-31 | enum_M_06 | non_idp_NG022006_C11 | non_idp_NG022006_C11_H02 | 6051d636-b7d7-48e6-a22c-cb77062415ab | fcs_hhs_contradiction | Acceptable food consumption with severe hunger | FCS 93.5, HHS 6
2026-09-01 | enum_M_09 | non_idp_NG022012_C07 | non_idp_NG022012_C07_H04 | 315c8f50-638e-40de-b13c-990cef50ffec | gps_far | GPS point 4.8 km from the household | 4815
2026-09-02 | enum_M_09 | non_idp_NG022012_C10 | non_idp_NG022012_C10_R01 | db0c82a6-4f88-4e18-b578-c5266e6631f8 | fcs_hhs_contradiction | Acceptable food consumption with severe hunger | FCS 36.0, HHS 4
2026-09-02 | enum_M_10 | non_idp_NG022012_C10 | non_idp_NG022012_C10_H06 | ce89e078-d40a-4cc9-8ede-6273c2063741 | gps_far | GPS point 3.2 km from the household | 3238
2026-09-02 | enum_M_12 | non_idp_NG022013_C14 | non_idp_NG022013_C14_H02 | fe035e24-db1e-45bd-b023-ac8fcdd9594d | fcs_hhs_contradiction | Acceptable food consumption with severe hunger | FCS 93.5, HHS 6
2026-09-02 | enum_M_14 | non_idp_NG022014_C10 | non_idp_NG022014_C10_H05 | ac0af21e-8cda-4914-95b9-13f378dce915 | attending_exceed_school_age | More children attending school than of school age | 3
2026-09-03 | enum_M_05 | non_idp_NG022006_C14 | non_idp_NG022006_C14_H02 | a1d3add4-c640-425b-a7f8-16cc5c1e2eae | fcs_hhs_contradiction | Acceptable food consumption with severe hunger | FCS 93.5, HHS 6
2026-09-03 | enum_M_08 | non_idp_NG022007_C13 | non_idp_NG022007_C13_H03 | 43ceea2c-455c-457e-8468-39edb2459668 | attending_exceed_school_age | More children attending school than of school age | 6
2026-09-03 | enum_M_10 | non_idp_NG022012_C12 | non_idp_NG022012_C12_R01 | 0b3b3b64-112e-4c0a-a621-c1f2582cc153 | fcs_hhs_contradiction | Acceptable food consumption with severe hunger | FCS 38.0, HHS 4
2026-09-03 | enum_M_11 | non_idp_NG022013_C15 | non_idp_NG022013_C15_H02 | 1cfae2ce-dc33-40d8-982f-e62c2d463e4f | fcs_hhs_contradiction | Acceptable food consumption with severe hunger | FCS 93.5, HHS 6
2026-09-04 | enum_M_02 | idp_NG022005_C08 | idp_NG022005_C08_R01 | 1fc413d8-6eb7-4def-b33b-0ccc390019ff | fcs_hhs_contradiction | Acceptable food consumption with severe hunger | FCS 48.5, HHS 4
2026-09-04 | enum_M_04 | non_idp_NG022006_C03 | non_idp_NG022006_C03_H04 | 2b0e4bf8-f723-4c07-b7eb-98b5eabf64ba | attending_exceed_school_age | More children attending school than of school age | 4
2026-09-04 | enum_M_04 | non_idp_NG022006_C03 | non_idp_NG022006_C03_H06 | c90b7ad6-db76-413f-b827-b9950af98692 | children_exceed_hh | More children than household members | 1 + 8 children, household of 6
2026-09-04 | enum_M_15 | non_idp_NG022018_C02 | non_idp_NG022018_C02_H06 | 2e20a86a-bac3-4101-a996-021ae7fd7cdc | gps_far | GPS point 3.4 km from the household | 3442
2026-09-05 | enum_M_13 | non_idp_NG022014_C13 | non_idp_NG022014_C13_H06 | 46a71980-8ee2-46a9-be87-85e52f6847ec | gps_far | GPS point 4.2 km from the household | 4200
2026-09-06 | enum_M_13 | non_idp_NG022014_C14 | non_idp_NG022014_C14_R01 | dd472f55-0332-44ec-bb87-f6c4140a444c | fcs_flat | Every food group given the same number of days | 7
2026-09-06 | enum_M_15 | non_idp_NG022018_C04 | non_idp_NG022018_C04_H05 | 395f6047-ac58-4032-aa9e-eb351418f197 | fcs_hhs_contradiction | Acceptable food consumption with severe hunger | FCS 40.0, HHS 4
2026-09-07 | enum_M_01 | idp_NG022005_C11 | idp_NG022005_C11_H03 | 0ed3466d-0547-44fb-a0e0-a7a02f5dab3f | fcs_flat | Every food group given the same number of days | 7
2026-09-07 | enum_M_02 | idp_NG022005_C11 | idp_NG022005_C11_H04 | a05f3a7e-59a0-4f72-a410-b792fd75dc14 | fcs_hhs_contradiction | Acceptable food consumption with severe hunger | FCS 93.5, HHS 6
2026-09-07 | enum_M_09 | non_idp_NG022012_C15 | non_idp_NG022012_C15_H06 | a9731c9d-26ee-422e-a4a8-818acca097d9 | fcs_hhs_contradiction | Acceptable food consumption with severe hunger | FCS 51.0, HHS 4
2026-09-07 | enum_M_15 | non_idp_NG022018_C05 | non_idp_NG022018_C05_H04 | 4d88e510-62da-40f8-94f9-4b9216a744f4 | gps_far | GPS point 2.3 km from the household | 2252
2026-09-07 | enum_M_16 | non_idp_NG022018_C05 | non_idp_NG022018_C05_H06 | a1b23732-8fea-45b4-b3b8-ff8871d645ae | fcs_hhs_contradiction | Acceptable food consumption with severe hunger | FCS 42.0, HHS 4
2026-09-08 | enum_M_01 | idp_NG022005_C12 | idp_NG022005_C12_H03 | 283ddbf3-52ee-4787-ac04-0711e3ff023d | fcs_hhs_contradiction | Acceptable food consumption with severe hunger | FCS 42.5, HHS 4
2026-09-08 | enum_M_02 | idp_NG022005_C12 | idp_NG022005_C12_H06 | e42d413a-1907-40f4-810a-79526fd6a6a0 | gps_far | GPS point 3.9 km from the household | 3923
2026-09-08 | enum_M_04 | non_idp_NG022005_R1_05 | non_idp_NG022005_R1_05_H02 | c443b233-5277-4173-a2e8-15d958ede721 | fcs_hhs_contradiction | Acceptable food consumption with severe hunger | FCS 93.5, HHS 6
2026-09-08 | enum_M_04 | non_idp_NG022005_R1_05 | non_idp_NG022005_R1_05_H05 | e4796f7c-0a64-4cc9-aed0-484911f534cd | attending_exceed_school_age | More children attending school than of school age | 6
2026-09-08 | enum_M_08 | non_idp_NG022007_C17 | non_idp_NG022007_C17_H04 | e50abd26-c11e-46e2-9a84-19688aae1e1d | fcs_hhs_contradiction | Acceptable food consumption with severe hunger | FCS 45.5, HHS 5
2026-09-08 | enum_M_10 | non_idp_NG022012_C16 | non_idp_NG022012_C16_H05 | 8c8ad801-86c3-4a3a-9a79-7dfa8a89a8d1 | fcs_hhs_contradiction | Acceptable food consumption with severe hunger | FCS 49.5, HHS 4
2026-09-09 | enum_M_05 | non_idp_NG022007_C04 | non_idp_NG022007_C04_H04 | 30aae3b9-382f-449b-a1c3-9038a31357f9 | fcs_hhs_contradiction | Acceptable food consumption with severe hunger | FCS 93.5, HHS 6
2026-09-10 | enum_M_06 | non_idp_NG022007_C05 | non_idp_NG022007_C05_H02 | af89ac5c-c75b-45ba-ae91-c194f032e2d4 | attending_exceed_school_age | More children attending school than of school age | 4
2026-09-10 | enum_M_09 | non_idp_NG022012_C17 | non_idp_NG022012_C17_H04 | 1bfd772d-deda-4c28-82a1-c5aee54c280b | fcs_hhs_contradiction | Acceptable food consumption with severe hunger | FCS 44.5, HHS 4
2026-09-11 | enum_M_14 | idp_NG022018_C02 | idp_NG022018_C02_H03 | 41f13b3b-336a-4e4d-987d-e31f02550ec7 | fcs_hhs_contradiction | Acceptable food consumption with severe hunger | FCS 50.5, HHS 4
2026-09-11 | enum_M_16 | non_idp_NG022018_C07 | non_idp_NG022018_C07_H04 | abed8da3-fca2-4511-8b37-3bccbf7a5257 | fcs_flat | Every food group given the same number of days | 7
2026-09-12 | enum_M_12 | non_idp_NG022012_R2_01 | non_idp_NG022012_R2_01_R01 | 3320b3c9-96a3-4757-acee-01399bec520c | fcs_hhs_contradiction | Acceptable food consumption with severe hunger | FCS 93.5, HHS 6
2026-09-13 | enum_M_03 | non_idp_NG022005_R2_02 | non_idp_NG022005_R2_02_H01 | 2f7d33a8-9239-49bd-aadd-d058730bda10 | fcs_flat | Every food group given the same number of days | 7
2026-09-13 | enum_M_07 | non_idp_NG022011_C05 | non_idp_NG022011_C05_R01 | 00f21952-50e8-4a3f-8cff-9145fc6ec995 | attending_exceed_school_age | More children attending school than of school age | 2
2026-09-13 | enum_M_12 | non_idp_NG022012_R2_02 | non_idp_NG022012_R2_02_H02 | ceeb4809-a14d-4feb-9aa2-5ba3c7d354b4 | fcs_flat | Every food group given the same number of days | 0
2026-09-14 | enum_M_01 | idp_NG022005_C15 | idp_NG022005_C15_H01 | 2eb623c4-49c2-4053-82ca-7a394aacc7ac | fcs_hhs_contradiction | Acceptable food consumption with severe hunger | FCS 93.5, HHS 6
2026-09-14 | enum_M_05 | non_idp_NG022007_C06 | non_idp_NG022007_C06_H02 | 1a2b3a8b-520c-4152-bb98-ce26d7e78f77 | fcs_hhs_contradiction | Acceptable food consumption with severe hunger | FCS 39.0, HHS 4
2026-09-14 | enum_M_06 | non_idp_NG022007_C06 | non_idp_NG022007_C06_R02 | bce9e298-cfd5-40cc-bf0a-3d5f65c69463 | fcs_hhs_contradiction | Acceptable food consumption with severe hunger | FCS 93.5, HHS 6
2026-09-15 | enum_M_01 | idp_NG022005_C16 | idp_NG022005_C16_H04 | d13cf2e8-7b07-48d0-bb84-ee0d74617609 | fcs_hhs_contradiction | Acceptable food consumption with severe hunger | FCS 93.5, HHS 6
2026-09-16 | enum_M_13 | idp_NG022018_C06 | idp_NG022018_C06_H01 | a3f473a4-f5bf-4127-b653-628c8bbc04c2 | gps_far | GPS point 2.6 km from the household | 2636
2026-09-16 | enum_M_13 | idp_NG022018_C06 | idp_NG022018_C06_H01 | a3f473a4-f5bf-4127-b653-628c8bbc04c2 | fcs_hhs_contradiction | Acceptable food consumption with severe hunger | FCS 45.0, HHS 4
2026-09-17 | enum_M_10 | non_idp_NG022011_R2_02 | non_idp_NG022011_R2_02_H05 | 190564e9-788f-4444-9351-4d9c39300a42 | gps_far | GPS point 1.8 km from the household | 1762
2026-09-18 | enum_M_01 | non_idp_NG022005_C04 | non_idp_NG022005_C04_H06 | 28aeb060-e4b7-4618-a085-8fb4f29f3c09 | fcs_hhs_contradiction | Acceptable food consumption with severe hunger | FCS 93.5, HHS 6
2026-09-18 | enum_M_14 | non_idp_NG022014_R1_03 | non_idp_NG022014_R1_03_H05 | 87c7a538-f550-418c-9c69-0f5323b18ef4 | fcs_hhs_contradiction | Acceptable food consumption with severe hunger | FCS 42.0, HHS 5
2026-09-19 | enum_M_08 | non_idp_NG022011_C14 | non_idp_NG022011_C14_H01 | 22b24c30-b28f-46c2-acfe-b35deb2c7d99 | children_exceed_hh | More children than household members | 0 + 9 children, household of 6
2026-09-20 | enum_M_02 | non_idp_NG022005_C05 | non_idp_NG022005_C05_H02 | d1e3abfd-509e-4b04-8a5e-2c06149981ef | attending_exceed_school_age | More children attending school than of school age | 8
2026-09-20 | enum_M_16 | non_idp_NG022018_C12 | non_idp_NG022018_C12_H03 | 359dd229-72e3-4b9a-b5c7-bf4b128fddc8 | fcs_flat | Every food group given the same number of days | 7
2026-09-21 | enum_M_07 | non_idp_NG022011_R1_01 | non_idp_NG022011_R1_01_H02 | abf84241-4672-4aec-af00-d452d8020589 | fcs_hhs_contradiction | Acceptable food consumption with severe hunger | FCS 93.5, HHS 6
2026-09-24 | enum_M_07 | non_idp_NG022011_R1_02 | non_idp_NG022011_R1_02_R02 | 731f10f5-c46c-40dd-b0a9-24d49ea505a0 | fcs_flat | Every food group given the same number of days | 7

## Removed
Interviews removed from the dataset, and why
Synthetic data – not real findings
date | enumerator_id | cluster_id | household_id | _uuid | check_id | reason
2026-08-20 | enum_M_03 | non_idp_NG022005_C99 | non_idp_NG022005_C11_H03 | 8d1e2fc0-40e2-49e8-9606-06988b22ea79 | C05 | Cluster code not in the sample
2026-08-21 | enum_M_03 | non_idp_NG022005_C14 | non_idp_NG022005_C14_H05 | e5648a5d-0658-4ba6-9c90-0f64f9a16689 | C01 | Respondent did not consent
2026-08-24 | enum_M_05 | non_idp_NG022006_C05 | non_idp_NG022006_C05_H05 | 49088c6f-e263-4cc4-8841-4040fa888a1e | C04 | Interview took 10 minutes
2026-08-24 | enum_M_06 | non_idp_NG022006_C05 | non_idp_NG022006_C05_H04 | 11919eb1-776f-4c20-8f90-5dd15e9ec12e | C04 | Interview took 11 minutes
2026-08-25 | enum_M_03 | idp_NG022006_C01 | idp_NG022006_C01_H05 | 4868ac8a-1120-4701-9e79-94ae9cc27e2c | C04 | Interview took 6 minutes
2026-08-25 | enum_M_04 | idp_NG022006_C99 | idp_NG022006_C01_H03 | feee824b-8475-4db6-98c7-1d9521dcb795 | C05 | Cluster code not in the sample
2026-08-25 | enum_M_12 | non_idp_NG022013_C06 | non_idp_NG022013_C06_H05 | 5c5c275a-c162-4339-8e2c-d2a8a7753488 | C04 | Interview took 9 minutes
2026-08-25 | enum_M_16 | idp_NG022018_C07 | idp_NG022018_C07_H05 | 239860e0-9e9c-4e69-aeac-c2058083437e | C04 | Interview took 11 minutes
2026-08-26 | enum_M_07 | non_idp_NG022007_C07 | non_idp_NG022007_C07_H01 | 767b47cc-e678-401d-a035-8cc7b85b9dfa | C04 | Interview took 9 minutes
2026-08-26 | enum_M_16 | idp_NG022018_C08 | idp_NG022018_C08_H02 | dc301c07-adce-405c-9db3-8c21e01dafdb | C04 | Interview took 8 minutes
2026-08-27 | enum_M_01 | idp_NG022005_C01 | idp_NG022005_C01_H04 | 269c0231-de71-4548-9fe2-7f01979a3d2b | C04 | Interview took 10 minutes
2026-08-27 | enum_M_11 | non_idp_NG022013_C08 | non_idp_NG022013_C08_H02 | f2509abe-7736-4cae-a370-ea7a4d3f2880 | C04 | Interview took 4 minutes
2026-08-27 | enum_M_11 | non_idp_NG022013_C08 | non_idp_NG022013_C08_R01 | 66577dfc-632c-4296-acc6-e9a1d6574760 | C01 | Respondent did not consent
2026-08-28 | enum_M_11 | non_idp_NG022013_C09 | non_idp_NG022013_C09_R02 | 20cc0283-929d-47b6-a4f6-f05062d4c474 | C01 | Respondent did not consent
2026-08-28 | enum_M_13 | non_idp_NG022014_C05 | non_idp_NG022014_C05_H01 | 0307b19b-4324-480f-b54a-4116a22bf50d | C01 | Respondent did not consent
2026-08-30 | enum_M_08 | non_idp_NG022007_C10 | non_idp_NG022007_C10_H04 | 77a5bcd0-28a0-40bd-ba0c-c73b7ee5b1e7 | C04 | Interview took 7 minutes
2026-08-30 | enum_M_10 | non_idp_NG022012_C04 | non_idp_NG022012_C04_H05 | b69c8253-9c8a-43ca-98f7-78ad6b6b2f8e | C04 | Interview took 6 minutes
2026-08-30 | enum_M_14 | non_idp_NG022014_C07 | non_idp_NG022014_C07_R02 | 273b29da-6698-4b68-841f-61991cc5c5bb | C02 | Same submission uploaded more than once
2026-08-31 | enum_M_02 | idp_NG022005_C96 | idp_NG022005_C05_H01 | b561af8d-97ec-4f11-a7e0-bdeaec2e5ae0 | C05 | Cluster code not in the sample
2026-08-31 | enum_M_02 | idp_NG022005_C05 | idp_NG022005_C05_H03 | 239e4e62-cadd-4761-9f45-11ab67e06a98 | C04 | Interview took 11 minutes
2026-08-31 | enum_M_07 | non_idp_NG022007_C11 | non_idp_NG022007_C11_H04 | a16d31da-5100-4f12-a53f-035f8f5ab81d | C01 | Respondent did not consent
2026-09-02 | enum_M_02 | idp_NG022005_C06 | idp_NG022005_C06_H02 | 01b33114-2282-435f-8453-17bdb9c7820f | C01 | Respondent did not consent
2026-09-03 | enum_M_01 | idp_NG022005_C07 | idp_NG022005_C07_H03 | 369ec6c5-b3b4-46dd-9ffa-84d4056b3979 | C02 | Same submission uploaded more than once
2026-09-03 | enum_M_12 | non_idp_NG022013_C15 | non_idp_NG022013_C15_H06 | 794744e6-6804-4786-8502-e8e156783703 | C04 | Interview took 5 minutes
2026-09-04 | enum_M_05 | non_idp_NG022006_C16 | non_idp_NG022006_C16_R01 | 41e328da-8b76-445b-9822-a8a7575d6d26 | C01 | Respondent did not consent
2026-09-04 | enum_M_06 | non_idp_NG022006_C16 | non_idp_NG022006_C16_H02 | 8aa1eb9a-d620-41f7-8522-19f48792c37a | C01 | Respondent did not consent
2026-09-04 | enum_M_08 | non_idp_NG022007_C14 | non_idp_NG022007_C14_H02 | fa0fd51d-3e23-4827-84f5-3eb27bcf77fc | C03 | Household already interviewed in an earlier submission
2026-09-04 | enum_M_08 | non_idp_NG022007_C14 | non_idp_NG022007_C14_H05 | 06a813bd-61cd-4af3-b8f0-faedd0e94d05 | C04 | Interview took 7 minutes
2026-09-04 | enum_M_12 | non_idp_NG022013_C16 | non_idp_NG022013_C16_H03 | 93532f82-d0ba-49b2-b662-e95b3e87fb3e | C03 | Household already interviewed in an earlier submission
2026-09-04 | enum_M_13 | non_idp_NG022014_C12 | non_idp_NG022014_C12_H01 | 32b76c70-9a36-453c-bf54-dfe39301b4ba | C04 | Interview took 7 minutes
2026-09-04 | enum_M_14 | non_idp_NG022014_C12 | non_idp_NG022014_C12_R02 | 72bec835-df41-4984-9d5c-659cf2389994 | C04 | Interview took 9 minutes
2026-09-05 | enum_M_01 | idp_NG022005_C09 | idp_NG022005_C09_H04 | 2dd0657d-7430-4a30-8a8e-2f0c5cdd501d | C01 | Respondent did not consent
2026-09-05 | enum_M_11 | non_idp_NG022013_C17 | non_idp_NG022013_C17_H01 | c90d1827-2e64-47c7-9ae0-34d89aa26ca3 | C04 | Interview took 11 minutes
2026-09-05 | enum_M_13 | non_idp_NG022014_C13 | non_idp_NG022014_C13_H03 | cd38317d-28d8-4ca2-9d98-8cecdb237009 | C04 | Interview took 12 minutes
2026-09-05 | enum_M_14 | non_idp_NG022014_C13 | non_idp_NG022014_C13_H04 | 9f37c802-fd10-402f-93d6-7d9dabcaa9aa | C04 | Interview took 11 minutes
2026-09-06 | enum_M_10 | non_idp_NG022012_C14 | non_idp_NG022012_C14_R01 | 27bb71ec-b11e-4874-807a-084efed8e440 | C01 | Respondent did not consent
2026-09-07 | enum_M_03 | non_idp_NG022005_R1_04 | non_idp_NG022005_R1_04_H03 | 46eee384-c560-4658-b464-1608b34cd8f4 | C04 | Interview took 7 minutes
2026-09-07 | enum_M_04 | non_idp_NG022005_R1_04 | non_idp_NG022005_R1_04_H01 | de70df9d-c100-4475-bd41-e87010add07e | C04 | Interview took 5 minutes
2026-09-07 | enum_M_07 | non_idp_NG022007_C16 | non_idp_NG022007_C16_H03 | b1adf574-901e-4047-919a-719d89494099 | C03 | Household already interviewed in an earlier submission
2026-09-07 | enum_M_09 | non_idp_NG022012_C15 | non_idp_NG022012_C15_H06 | a9731c9d-26ee-422e-a4a8-818acca097d9 | C04 | Interview took 4 minutes
2026-09-07 | enum_M_12 | non_idp_NG022013_R1_01 | non_idp_NG022013_R1_01_H02 | ef2c78f6-f672-44f8-a444-0e5d1e99f4a9 | C04 | Interview took 7 minutes
2026-09-08 | enum_M_08 | non_idp_NG022007_C17 | non_idp_NG022007_C17_H02 | 2e6a49a4-6719-420c-b89f-455a5b5b81d8 | C01 | Respondent did not consent
2026-09-08 | enum_M_09 | non_idp_NG022012_C16 | non_idp_NG022012_C16_H03 | 5204f978-6d6f-4953-b7aa-55a1c4f8818e | C04 | Interview took 8 minutes
2026-09-08 | enum_M_14 | non_idp_NG022014_C16 | non_idp_NG022014_C16_H05 | 153ebe92-4df9-48ff-bd78-b0b3c6e66624 | C01 | Respondent did not consent
2026-09-08 | enum_M_14 | non_idp_NG022014_C16 | non_idp_NG022014_C16_H06 | 879267cd-f21f-4df5-b17e-3fa7bcfef5c2 | C01 | Respondent did not consent
2026-09-08 | enum_M_16 | non_idp_NG022018_C06 | non_idp_NG022018_C06_H01 | 26922825-1c7f-4965-9495-05f779541a97 | C01 | Respondent did not consent
2026-09-09 | enum_M_06 | non_idp_NG022007_C04 | non_idp_NG022007_C04_H06 | e19a74c0-7523-49f3-947e-b0d6726aeb7f | C04 | Interview took 12 minutes
2026-09-09 | enum_M_07 | non_idp_NG022011_C02 | non_idp_NG022011_C02_R01 | 46ab59dc-ccd0-4bbe-9214-a65dd5eb9702 | C01 | Respondent did not consent
2026-09-09 | enum_M_08 | non_idp_NG022011_C02 | non_idp_NG022011_C02_H05 | b74e525d-9f04-4772-b87a-b24b210b775f | C01 | Respondent did not consent
2026-09-10 | enum_M_03 | non_idp_NG022005_R1_06 | non_idp_NG022005_R1_06_H02 | a6e58c1d-85ca-4085-94b2-53282dd8f785 | C04 | Interview took 8 minutes
2026-09-10 | enum_M_06 | non_idp_NG022007_C05 | non_idp_NG022007_C05_H05 | 24709d98-e027-47ab-adca-121f2c6f8a3d | C01 | Respondent did not consent
2026-09-10 | enum_M_08 | non_idp_NG022011_C03 | non_idp_NG022011_C03_H01 | a8be8658-392f-4f53-8c97-917fc592a465 | C04 | Interview took 9 minutes
2026-09-10 | enum_M_08 | non_idp_NG022011_C03 | non_idp_NG022011_C03_H02 | fddc324a-2793-4670-8e72-85b3cd91bf99 | C01 | Respondent did not consent
2026-09-11 | enum_M_13 | idp_NG022018_C02 | idp_NG022018_C02_H06 | 4b227a1a-b0ba-4737-afbc-baa384168d07 | C04 | Interview took 10 minutes
2026-09-11 | enum_M_15 | non_idp_NG022018_C07 | non_idp_NG022018_C07_H03 | 153ae386-43b0-43b6-a8e7-8e29a26c9438 | C04 | Interview took 8 minutes
2026-09-13 | enum_M_04 | non_idp_NG022005_R2_02 | non_idp_NG022005_R2_02_H03 | 119d6464-2dbe-48ce-ad12-c2de93425319 | C04 | Interview took 4 minutes
2026-09-13 | enum_M_07 | non_idp_NG022011_C05 | non_idp_NG022011_C05_H03 | fc03daee-1e98-46cf-97e9-788de8c76960 | C01 | Respondent did not consent
2026-09-13 | enum_M_12 | non_idp_NG022012_R2_02 | non_idp_NG022012_R2_02_H04 | 37c3ef3e-b9e3-4ec8-b488-c098c11b24cd | C04 | Interview took 11 minutes
2026-09-13 | enum_M_15 | non_idp_NG022018_C08 | non_idp_NG022018_C08_H06 | f0d624aa-f866-46cb-9d97-c172f7adcc60 | C01 | Respondent did not consent
2026-09-14 | enum_M_07 | non_idp_NG022011_C12 | non_idp_NG022011_C12_H02 | 627735d9-e2db-40a9-80d0-a209037238dd | C04 | Interview took 8 minutes
2026-09-14 | enum_M_10 | non_idp_NG022011_R2_01 | non_idp_NG022011_R2_01_H05 | 3f808435-88ed-4004-9e40-ec9f178dcf17 | C01 | Respondent did not consent
2026-09-15 | enum_M_02 | idp_NG022005_C16 | idp_NG022005_C16_H06 | c44d02b7-9794-4466-ac40-8c185d93b42a | C01 | Respondent did not consent
2026-09-15 | enum_M_13 | idp_NG022018_C05 | idp_NG022018_C05_H06 | 9ef33658-c114-4abb-8615-5c1ec69d92d5 | C04 | Interview took 9 minutes
2026-09-16 | enum_M_06 | non_idp_NG022006_R1_01 | non_idp_NG022006_R1_01_H04 | ab62d5df-a911-401c-83d0-a379bc033744 | C04 | Interview took 4 minutes
2026-09-17 | enum_M_05 | non_idp_NG022006_R1_02 | non_idp_NG022006_R1_02_H01 | baf915e1-fd6d-42a1-829a-95ba4538e6e9 | C02 | Same submission uploaded more than once
2026-09-17 | enum_M_05 | non_idp_NG022006_R1_02 | non_idp_NG022006_R1_02_H05 | 8d02093f-898d-4966-a9a5-2d81bbc0f49a | C03 | Household already interviewed in an earlier submission
2026-09-17 | enum_M_14 | non_idp_NG022014_R1_C95 | non_idp_NG022014_R1_01_H04 | 0c45b5cf-e884-48cb-b663-6a0c3865e36d | C05 | Cluster code not in the sample
2026-09-18 | enum_M_07 | non_idp_NG022011_C91 | non_idp_NG022011_C13_H01 | 9cfde32c-755a-420b-96ae-1316ad7f3dff | C05 | Cluster code not in the sample
2026-09-18 | enum_M_13 | non_idp_NG022014_R1_03 | non_idp_NG022014_R1_03_H02 | d0a025cd-7f14-4db9-b4a3-607138f881bc | C04 | Interview took 11 minutes
2026-09-21 | enum_M_16 | non_idp_NG022018_C14 | non_idp_NG022018_C14_H02 | 2d089354-9050-4c49-80d7-608b546a3ef9 | C04 | Interview took 5 minutes
2026-09-23 | enum_M_02 | non_idp_NG022005_C09 | non_idp_NG022005_C09_H06 | 592d88b2-924b-4927-a38b-d255f358552e | C04 | Interview took 6 minutes
2026-09-24 | enum_M_09 | non_idp_NG022011_R2_05 | non_idp_NG022011_R2_05_H02 | 548e9ffd-ef06-4a93-86ef-fd74b31ac060 | C01 | Respondent did not consent
2026-09-24 | enum_M_10 | non_idp_NG022011_R2_05 | non_idp_NG022011_R2_05_H06 | 1f954ea2-5d4a-4528-8c39-5885e97e2ec1 | C01 | Respondent did not consent
2026-09-26 | enum_M_10 | non_idp_NG022011_R2_07 | non_idp_NG022011_R2_07_H05 | add23455-5c57-40e2-b34e-e7e3ae110eb0 | C04 | Interview took 10 minutes

## Enumerators
Enumerators
Synthetic data – not real findings
enumerator_id | interviews | median minutes | % repeated answers | interviews removed | interviews flagged | pattern
enum_M_01 | 59 | 41.1 | 3.4 | 3 | 6
enum_M_02 | 68 | 45 | 0 | 5 | 4
enum_M_03 | 62 | 41.7 | 0 | 5 | 4
enum_M_04 | 64 | 43.7 | 0 | 3 | 6
enum_M_05 | 64 | 42 | 3.1 | 4 | 6
enum_M_06 | 63 | 39.8 | 0 | 5 | 3
enum_M_07 | 60 | 42 | 0 | 7 | 4
enum_M_08 | 68 | 41.9 | 0 | 7 | 3
enum_M_09 | 57 | 39.7 | 0 | 3 | 5
enum_M_10 | 68 | 41.7 | 0 | 5 | 5
enum_M_11 | 57 | 45.4 | 0 | 4 | 2
enum_M_12 | 70 | 40.8 | 0 | 5 | 4
enum_M_13 | 69 | 39.6 | 0 | 6 | 6
enum_M_14 | 57 | 44 | 3.5 | 6 | 4
enum_M_15 | 63 | 43.8 | 0 | 2 | 4
enum_M_16 | 57 | 42.3 | 0 | 4 | 3

## Progress
Progress against target by LGA
Synthetic data – not real findings
adm1_name | adm2_name | pop_type | target | achieved | percent
Kebbi | Bagudo | idp | 96 | 93 | 96.9
Kebbi | Bagudo | non_idp | 102 | 84 | 82.4
Kebbi | Birnin Kebbi | idp | 54 | 52 | 96.3
Kebbi | Birnin Kebbi | non_idp | 102 | 98 | 96.1
Kebbi | Bunza | non_idp | 102 | 98 | 96.1
Kebbi | Jega | non_idp | 102 | 97 | 95.1
Kebbi | Kalgo | non_idp | 102 | 98 | 96.1
Kebbi | Koko/Besse | non_idp | 102 | 97 | 95.1
Kebbi | Maiyama | non_idp | 102 | 89 | 87.3
Kebbi | Suru | idp | 66 | 62 | 93.9
Kebbi | Suru | non_idp | 102 | 88 | 86.3