## Summary
Data-quality digest: Partner Q
Synthetic data – not real findings
Item | Value
Partner | Partner Q
States | Sokoto
Data as of | 2026-09-27
Submissions received | 1504
Interviews kept | 1409
Interviews removed | 95
Values corrected | 23
Interviews flagged for follow-up | 97
Households targeted | 1500
Households achieved | 1409
Progress against target | 93.9%

## Follow up
Interviews flagged: please check with the enumerator
Synthetic data – not real findings
date | enumerator_id | cluster_id | household_id | _uuid | check | issue | value
2026-08-17 | enum_Q_02 | idp_NG034001_C01 | idp_NG034001_C01_H06 | 65f160be-7560-4741-a2b1-cdc59573f4f9 | fcs_flat | Every food group given the same number of days | 0
2026-08-19 | enum_Q_06 | non_idp_NG034007_C01 | non_idp_NG034007_C01_H01 | add17625-aa51-410d-8253-1c7227cbdbdf | fcs_hhs_contradiction | Acceptable food consumption with severe hunger | FCS 45.5, HHS 4
2026-08-19 | enum_Q_06 | non_idp_NG034007_C01 | non_idp_NG034007_C01_H05 | 99f9fbc9-14b2-44a3-937f-a37b5843c4ac | fcs_hhs_contradiction | Acceptable food consumption with severe hunger | FCS 93.5, HHS 6
2026-08-19 | enum_Q_13 | non_idp_NG034011_C02 | non_idp_NG034011_C02_H01 | 85f4415a-e168-4717-87c3-8610fcb26687 | gps_far | GPS point 1.1 km from the household | 1111
2026-08-20 | enum_Q_23 | idp_NG034022_C05 | idp_NG034022_C05_H01 | 4b39c0a1-7653-4381-97e1-6f4daa7915d1 | gps_far | GPS point 2.1 km from the household | 2100
2026-08-21 | enum_Q_01 | idp_NG034001_C05 | idp_NG034001_C05_H06 | fd3260c3-fae6-4c75-9ebe-f21bfa08f49b | fcs_hhs_contradiction | Acceptable food consumption with severe hunger | FCS 36.0, HHS 4
2026-08-21 | enum_Q_02 | idp_NG034001_C05 | idp_NG034001_C05_H05 | 50358d70-0939-4229-9b44-c27f53779a3b | children_exceed_hh | More children than household members | 2 + 9 children, household of 8
2026-08-22 | enum_Q_06 | non_idp_NG034007_C08 | non_idp_NG034007_C08_H06 | 155f707c-1b15-4fde-94f2-08d4c701f9c3 | fcs_hhs_contradiction | Acceptable food consumption with severe hunger | FCS 93.5, HHS 6
2026-08-22 | enum_Q_09 | idp_NG034010_C07 | idp_NG034010_C07_H04 | 9f2dfd66-e38a-4867-972b-b8bc493d0c15 | fcs_flat | Every food group given the same number of days | 7
2026-08-22 | enum_Q_10 | idp_NG034010_C07 | idp_NG034010_C07_R01 | b78e6e18-52fe-4516-9998-f84714b08139 | children_exceed_hh | More children than household members | 0 + 6 children, household of 4
2026-08-23 | enum_Q_03 | non_idp_NG034001_C17 | non_idp_NG034001_C17_H04 | 6368b9e7-baf4-49b0-964a-70e6294999f9 | attending_exceed_school_age | More children attending school than of school age | 3
2026-08-23 | enum_Q_19 | non_idp_NG034019_C06 | non_idp_NG034019_C06_H05 | 898cf3cd-3fd2-453f-ad3a-64713e8b8a3b | fcs_hhs_contradiction | Acceptable food consumption with severe hunger | FCS 40.5, HHS 4
2026-08-23 | enum_Q_24 | idp_NG034022_C08 | idp_NG034022_C08_H02 | df57e142-4195-434a-a1bc-96bc02a3b601 | fcs_hhs_contradiction | Acceptable food consumption with severe hunger | FCS 46.5, HHS 4
2026-08-24 | enum_Q_01 | idp_NG034001_C08 | idp_NG034001_C08_H05 | 7a4973db-d2ed-4f7e-8166-ce4d9a4b37f9 | fcs_hhs_contradiction | Acceptable food consumption with severe hunger | FCS 93.5, HHS 6
2026-08-24 | enum_Q_06 | non_idp_NG034007_C10 | non_idp_NG034007_C10_H05 | 678d04a8-a8c0-4122-b8a8-766b2aac8970 | fcs_flat | Every food group given the same number of days | 7
2026-08-24 | enum_Q_17 | non_idp_NG034015_C15 | non_idp_NG034015_C15_H04 | 1d7d5605-9194-473f-8ee8-adcf59464757 | gps_far | GPS point 3.8 km from the household | 3847
2026-08-26 | enum_Q_03 | non_idp_NG034006_C03 | non_idp_NG034006_C03_H06 | d6a343e4-ae8a-488f-b3b4-da0415f5f483 | children_exceed_hh | More children than household members | 0 + 8 children, household of 7
2026-08-26 | enum_Q_06 | non_idp_NG034007_C12 | non_idp_NG034007_C12_H06 | 418b9203-59bc-410d-9c8e-6281e6a53f07 | fcs_hhs_contradiction | Acceptable food consumption with severe hunger | FCS 44.0, HHS 5
2026-08-26 | enum_Q_15 | non_idp_NG034012_C06 | non_idp_NG034012_C06_H06 | 688ac7ea-71aa-4471-af30-5529ade0c29a | fcs_hhs_contradiction | Acceptable food consumption with severe hunger | FCS 39.0, HHS 5
2026-08-26 | enum_Q_19 | non_idp_NG034019_C09 | non_idp_NG034019_C09_H05 | ce7e7b8c-ae24-431e-8caa-8612e4b0ea3e | fcs_flat | Every food group given the same number of days | 7
2026-08-27 | enum_Q_09 | idp_NG034010_C10 | idp_NG034010_C10_R02 | b2a684de-1704-4d99-907c-70b37e8a87ab | fcs_flat | Every food group given the same number of days | 7
2026-08-27 | enum_Q_16 | non_idp_NG034012_C07 | non_idp_NG034012_C07_H06 | a245a5cd-c647-4795-a5f2-d03dbb276012 | gps_far | GPS point 4.2 km from the household | 4165
2026-08-28 | enum_Q_07 | non_idp_NG034009_C06 | non_idp_NG034009_C06_R01 | c1f05525-b8b5-4697-be99-d4b22060317e | fcs_hhs_contradiction | Acceptable food consumption with severe hunger | FCS 93.5, HHS 6
2026-08-29 | enum_Q_06 | non_idp_NG034007_C16 | non_idp_NG034007_C16_H05 | 093ccf5b-e253-4c0c-8a16-930694e67196 | fcs_flat | Every food group given the same number of days | 7
2026-08-29 | enum_Q_10 | idp_NG034010_C11 | idp_NG034010_C11_H02 | c87b490d-73d0-4963-b132-fe7774ca8a26 | attending_exceed_school_age | More children attending school than of school age | 5
2026-08-29 | enum_Q_10 | idp_NG034010_C11 | idp_NG034010_C11_H04 | 895b3016-c933-42e4-a8c1-c46e90d8b06d | gps_far | GPS point 2.5 km from the household | 2490
2026-08-29 | enum_Q_20 | non_idp_NG034019_C11 | non_idp_NG034019_C11_H01 | 7be9d543-ab10-4d4b-8019-1346cc11084d | children_exceed_hh | More children than household members | 0 + 5 children, household of 4
2026-08-29 | enum_Q_23 | non_idp_NG034022_C08 | non_idp_NG034022_C08_H02 | 62da46bd-5551-4a9b-9ce6-5ee90d1e323b | fcs_hhs_contradiction | Acceptable food consumption with severe hunger | FCS 48.0, HHS 4
2026-08-30 | enum_Q_04 | non_idp_NG034006_C07 | non_idp_NG034006_C07_H03 | 8c3b623b-140d-4d0e-ae85-b53627d448d4 | children_exceed_hh | More children than household members | 0 + 6 children, household of 5
2026-08-30 | enum_Q_04 | non_idp_NG034006_C07 | non_idp_NG034006_C07_H04 | ffb81e57-9b91-40e5-8246-03fc41c3c594 | fcs_hhs_contradiction | Acceptable food consumption with severe hunger | FCS 93.5, HHS 6
2026-08-30 | enum_Q_15 | non_idp_NG034012_C12 | non_idp_NG034012_C12_H01 | b9eefa53-008f-4df6-b41f-000f5a724da5 | gps_far | GPS point 3.0 km from the household | 3021
2026-08-31 | enum_Q_03 | non_idp_NG034006_C12 | non_idp_NG034006_C12_H03 | d56d5862-2829-4f95-b2aa-72fb605facdf | gps_far | GPS point 3.9 km from the household | 3884
2026-08-31 | enum_Q_04 | non_idp_NG034006_C12 | non_idp_NG034006_C12_H02 | c288dbe0-8bd1-4ca4-8857-863fb95c7719 | fcs_flat | Every food group given the same number of days | 0
2026-08-31 | enum_Q_07 | non_idp_NG034009_C09 | non_idp_NG034009_C09_H06 | f072b3a6-5e74-4275-885f-4fa947da5de1 | gps_far | GPS point 2.3 km from the household | 2331
2026-08-31 | enum_Q_11 | idp_NG034011_C01 | idp_NG034011_C01_H02 | 0bd70094-0c89-47d1-8470-c6ae4e32b21b | fcs_hhs_contradiction | Acceptable food consumption with severe hunger | FCS 36.0, HHS 4
2026-08-31 | enum_Q_13 | non_idp_NG034011_C09 | non_idp_NG034011_C09_H04 | 00a158c5-da08-4150-a71c-c84ce00e0f6f | gps_far | GPS point 4.3 km from the household | 4286
2026-08-31 | enum_Q_15 | non_idp_NG034012_C13 | non_idp_NG034012_C13_H03 | dac6756d-3340-4cd4-847a-d3999d23c743 | fcs_flat | Every food group given the same number of days | 0
2026-08-31 | enum_Q_23 | non_idp_NG034022_C10 | non_idp_NG034022_C10_R01 | 534770f1-8ac0-4cfe-b79b-97b7f9ffd5b8 | fcs_hhs_contradiction | Acceptable food consumption with severe hunger | FCS 93.5, HHS 6
2026-09-01 | enum_Q_01 | non_idp_NG034001_C05 | non_idp_NG034001_C05_H03 | bf97ee11-5626-4d42-94b7-50429ad43b97 | fcs_hhs_contradiction | Acceptable food consumption with severe hunger | FCS 39.5, HHS 4
2026-09-01 | enum_Q_06 | non_idp_NG034006_R1_04 | non_idp_NG034006_R1_04_H03 | 1b7a9043-68e4-4b3f-91c2-dbdf96340a6d | fcs_flat | Every food group given the same number of days | 7
2026-09-01 | enum_Q_12 | idp_NG034011_C02 | idp_NG034011_C02_H06 | 51b363b1-b27a-49df-a1ec-16d7755d41dd | fcs_hhs_contradiction | Acceptable food consumption with severe hunger | FCS 45.5, HHS 4
2026-09-01 | enum_Q_17 | non_idp_NG034018_C04 | non_idp_NG034018_C04_H05 | 0d92d05c-7ce5-418a-9434-4a3462fd9a07 | attending_exceed_school_age | More children attending school than of school age | 2
2026-09-01 | enum_Q_19 | non_idp_NG034019_C14 | non_idp_NG034019_C14_H05 | e418fe4d-9ebc-4118-b3af-66d093b7fac2 | gps_far | GPS point 3.1 km from the household | 3076
2026-09-02 | enum_Q_06 | non_idp_NG034006_R1_05 | non_idp_NG034006_R1_05_H05 | 27dfe55e-bae6-4747-a58e-3ff19cfbd61a | gps_far | GPS point 1.2 km from the household | 1210
2026-09-02 | enum_Q_13 | non_idp_NG034011_C10 | non_idp_NG034011_C10_H04 | 4766c579-db29-49f6-b337-b3f55d3df98c | fcs_flat | Every food group given the same number of days | 7
2026-09-02 | enum_Q_22 | non_idp_NG034020_C08 | non_idp_NG034020_C08_H04 | 193bf7c5-6050-437e-826e-1bfc0bfe0ea1 | fcs_flat | Every food group given the same number of days | 7
2026-09-02 | enum_Q_23 | non_idp_NG034022_C13 | non_idp_NG034022_C13_H03 | 1f9ef1fb-35bd-479b-9630-187a2f82521c | gps_far | GPS point 1.5 km from the household | 1479
2026-09-03 | enum_Q_11 | idp_NG034011_C03 | idp_NG034011_C03_H05 | 9b658a92-2779-4f9b-bb34-ab49496261a9 | fcs_flat | Every food group given the same number of days | 7
2026-09-03 | enum_Q_18 | non_idp_NG034018_C08 | non_idp_NG034018_C08_H04 | 12aea59e-82fc-466a-a3c0-b899dc23d593 | fcs_hhs_contradiction | Acceptable food consumption with severe hunger | FCS 93.5, HHS 6
2026-09-03 | enum_Q_18 | non_idp_NG034018_C08 | non_idp_NG034018_C08_H06 | ea0a736e-ac64-4781-9a15-795e4d700c39 | children_exceed_hh | More children than household members | 1 + 5 children, household of 5
2026-09-03 | enum_Q_21 | non_idp_NG034020_C09 | non_idp_NG034020_C09_H03 | 0b8bfb6b-727c-4404-8670-1db2f4c30d60 | gps_far | GPS point 1.5 km from the household | 1461
2026-09-04 | enum_Q_01 | non_idp_NG034001_C10 | non_idp_NG034001_C10_H06 | b4d734e3-20d3-4ca6-8630-61b20fb951bf | attending_exceed_school_age | More children attending school than of school age | 5
2026-09-04 | enum_Q_05 | non_idp_NG034007_R1_02 | non_idp_NG034007_R1_02_H04 | 53470a9f-09a9-4596-a06c-7fe2842bb9e3 | fcs_hhs_contradiction | Acceptable food consumption with severe hunger | FCS 93.5, HHS 6
2026-09-04 | enum_Q_23 | non_idp_NG034022_C17 | non_idp_NG034022_C17_H05 | f1d3ad0a-eb73-4861-beb6-f42e2ba88cfe | children_exceed_hh | More children than household members | 3 + 9 children, household of 10
2026-09-04 | enum_Q_23 | non_idp_NG034022_C17 | non_idp_NG034022_C17_R01 | 0e7d5e35-5912-414d-88d0-de26d3aa4fd1 | gps_far | GPS point 2.5 km from the household | 2479
2026-09-05 | enum_Q_02 | non_idp_NG034001_C12 | non_idp_NG034001_C12_H04 | 01013dba-a029-4e6a-a071-16a2e1c9544d | fcs_hhs_contradiction | Acceptable food consumption with severe hunger | FCS 93.5, HHS 6
2026-09-05 | enum_Q_16 | non_idp_NG034012_C17 | non_idp_NG034012_C17_H01 | dd1b1a68-048e-44b6-913f-7bea5629a8f5 | gps_far | GPS point 0.7 km from the household | 663
2026-09-06 | enum_Q_07 | non_idp_NG034009_C11 | non_idp_NG034009_C11_H06 | 8ada1d70-8e61-4a4f-b589-01c3b6ad5066 | fcs_hhs_contradiction | Acceptable food consumption with severe hunger | FCS 93.5, HHS 6
2026-09-07 | enum_Q_08 | non_idp_NG034009_C12 | non_idp_NG034009_C12_H01 | 0e432b7d-8b0a-46ac-875d-486e9ec2d5a6 | fcs_hhs_contradiction | Acceptable food consumption with severe hunger | FCS 36.0, HHS 4
2026-09-07 | enum_Q_08 | non_idp_NG034009_C12 | non_idp_NG034009_C12_H05 | 1a2ce5f7-5b36-4b9d-893e-432cb83a83c5 | children_exceed_hh | More children than household members | 1 + 7 children, household of 5
2026-09-07 | enum_Q_09 | non_idp_NG034010_C04 | non_idp_NG034010_C04_H01 | 43f24a53-2693-47dd-a9f7-0aebbeb0f800 | fcs_hhs_contradiction | Acceptable food consumption with severe hunger | FCS 38.0, HHS 4
2026-09-07 | enum_Q_09 | non_idp_NG034010_C04 | non_idp_NG034010_C04_H04 | 91ba3ac0-94f8-4d01-b728-0dec725e3525 | gps_far | GPS point 4.6 km from the household | 4609
2026-09-07 | enum_Q_10 | non_idp_NG034010_C04 | non_idp_NG034010_C04_H03 | 321acfec-5854-4a89-b553-fa9dfe2c55aa | attending_exceed_school_age | More children attending school than of school age | 3
2026-09-08 | enum_Q_12 | idp_NG034011_C07 | idp_NG034011_C07_H03 | 6d8c2faf-83b9-4e02-aab0-f1df49322b5e | fcs_hhs_contradiction | Acceptable food consumption with severe hunger | FCS 63.0, HHS 4
2026-09-08 | enum_Q_21 | non_idp_NG034020_C12 | non_idp_NG034020_C12_R01 | 1c14b823-3ac7-4b1d-92be-bac5b4460ba8 | gps_far | GPS point 3.6 km from the household | 3622
2026-09-08 | enum_Q_22 | non_idp_NG034020_C12 | non_idp_NG034020_C12_R02 | b0b0848e-48ab-4986-b981-43d7fb581e23 | gps_far | GPS point 2.9 km from the household | 2910
2026-09-09 | enum_Q_07 | non_idp_NG034009_C15 | non_idp_NG034009_C15_H03 | 8bbc434b-a233-40fa-a822-cfd74ac2594f | fcs_hhs_contradiction | Acceptable food consumption with severe hunger | FCS 55.5, HHS 4
2026-09-09 | enum_Q_16 | non_idp_NG034015_C06 | non_idp_NG034015_C06_H01 | 5a376428-bf89-4f7f-961b-356e8867fe95 | gps_far | GPS point 0.9 km from the household | 944
2026-09-10 | enum_Q_08 | non_idp_NG034009_C16 | non_idp_NG034009_C16_H01 | 1464a077-62a1-469e-a16e-5a0e370f10a4 | fcs_hhs_contradiction | Acceptable food consumption with severe hunger | FCS 93.5, HHS 6
2026-09-10 | enum_Q_14 | non_idp_NG034011_C16 | non_idp_NG034011_C16_H06 | 7709f739-0579-424a-a6f6-2980f5f6256c | children_exceed_hh | More children than household members | 0 + 9 children, household of 7
2026-09-10 | enum_Q_16 | non_idp_NG034015_C07 | non_idp_NG034015_C07_R01 | 9dca6474-0a93-4ad0-8600-658f5b6ac5ac | gps_far | GPS point 4.6 km from the household | 4602
2026-09-10 | enum_Q_17 | non_idp_NG034018_R1_04 | non_idp_NG034018_R1_04_H06 | 1e578d60-add0-412e-93c1-6be9e05d0e8a | fcs_hhs_contradiction | Acceptable food consumption with severe hunger | FCS 93.5, HHS 6
2026-09-11 | enum_Q_08 | idp_NG034010_C01 | idp_NG034010_C01_H01 | 0c7941ee-de07-4a5c-8202-aa75ec689f33 | gps_far | GPS point 0.7 km from the household | 673
2026-09-11 | enum_Q_08 | idp_NG034010_C01 | idp_NG034010_C01_H04 | a5846a99-4fa3-4bc7-978e-6d9a57ec2799 | attending_exceed_school_age | More children attending school than of school age | 3
2026-09-11 | enum_Q_09 | non_idp_NG034010_C07 | non_idp_NG034010_C07_H01 | 14056cc0-793c-4a3e-b699-fdb5506b2f3d | children_exceed_hh | More children than household members | 1 + 7 children, household of 7
2026-09-12 | enum_Q_05 | non_idp_NG034007_R2_01 | non_idp_NG034007_R2_01_R01 | fd560ee1-1cc1-4e4a-b09f-30205b7b0a4b | fcs_hhs_contradiction | Acceptable food consumption with severe hunger | FCS 37.0, HHS 4
2026-09-12 | enum_Q_09 | non_idp_NG034010_C08 | non_idp_NG034010_C08_H03 | aa06924e-e796-417f-89f4-136bdafb236f | gps_far | GPS point 3.7 km from the household | 3664
2026-09-12 | enum_Q_09 | non_idp_NG034010_C08 | non_idp_NG034010_C08_H04 | 671a0f01-58e2-4637-85fb-c5c1c84167ad | gps_far | GPS point 3.0 km from the household | 3019
2026-09-12 | enum_Q_20 | non_idp_NG034018_R2_01 | non_idp_NG034018_R2_01_R02 | 9f118845-a225-44be-81f4-74f16c637867 | fcs_hhs_contradiction | Acceptable food consumption with severe hunger | FCS 37.5, HHS 4
2026-09-12 | enum_Q_21 | non_idp_NG034020_C15 | non_idp_NG034020_C15_H03 | 53a3b485-50a6-4507-b9b7-e984dba83341 | fcs_hhs_contradiction | Acceptable food consumption with severe hunger | FCS 93.5, HHS 6
2026-09-12 | enum_Q_24 | non_idp_NG034022_R2_01 | non_idp_NG034022_R2_01_H06 | fd607099-5f91-489d-9d24-4a70e47f8cef | gps_far | GPS point 4.4 km from the household | 4381
2026-09-13 | enum_Q_04 | non_idp_NG034006_R1_02 | non_idp_NG034006_R1_02_H06 | af722c24-8951-4948-9b10-518fa6567a1e | attending_exceed_school_age | More children attending school than of school age | 4
2026-09-13 | enum_Q_07 | idp_NG034010_C02 | idp_NG034010_C02_H01 | e8850464-44ec-4d38-8af1-992e485b0443 | attending_exceed_school_age | More children attending school than of school age | 2
2026-09-13 | enum_Q_07 | idp_NG034010_C02 | idp_NG034010_C02_H03 | 50d80f56-0e12-4f41-9b09-7eb7802eea83 | fcs_hhs_contradiction | Acceptable food consumption with severe hunger | FCS 93.5, HHS 6
2026-09-13 | enum_Q_20 | non_idp_NG034018_R2_02 | non_idp_NG034018_R2_02_H01 | d423a652-b941-4d3d-aeee-7da26694cdbc | fcs_hhs_contradiction | Acceptable food consumption with severe hunger | FCS 40.5, HHS 4
2026-09-15 | enum_Q_07 | idp_NG034010_C04 | idp_NG034010_C04_H06 | c69448d5-6780-4ff6-b7e3-e4df1913c7a6 | gps_far | GPS point 3.5 km from the household | 3539
2026-09-16 | enum_Q_07 | idp_NG034010_C05 | idp_NG034010_C05_R01 | d12bda20-03dc-45af-88ea-2f1a9eb7530f | fcs_hhs_contradiction | Acceptable food consumption with severe hunger | FCS 39.0, HHS 4
2026-09-16 | enum_Q_16 | non_idp_NG034012_R1_01 | non_idp_NG034012_R1_01_H06 | 6dbd068f-a6ab-4c04-8d97-025813a20e98 | fcs_hhs_contradiction | Acceptable food consumption with severe hunger | FCS 93.5, HHS 6
2026-09-17 | enum_Q_08 | idp_NG034010_C06 | idp_NG034010_C06_H04 | fd11f890-9f32-419e-b148-189d6444edd6 | fcs_hhs_contradiction | Acceptable food consumption with severe hunger | FCS 93.5, HHS 6
2026-09-17 | enum_Q_09 | non_idp_NG034010_C11 | non_idp_NG034010_C11_R03 | 9d96bb43-4309-479e-abd8-f8216d5f3d64 | gps_far | GPS point 3.2 km from the household | 3155
2026-09-19 | enum_Q_08 | non_idp_NG034009_R2_01 | non_idp_NG034009_R2_01_H05 | 78129efa-c2f9-4e63-8057-4fd351a022a0 | attending_exceed_school_age | More children attending school than of school age | 6
2026-09-19 | enum_Q_10 | non_idp_NG034010_C12 | non_idp_NG034010_C12_H03 | 3841fb6e-ea29-4605-b492-91e456685b92 | gps_far | GPS point 2.0 km from the household | 1954
2026-09-19 | enum_Q_17 | non_idp_NG034015_R2_01 | non_idp_NG034015_R2_01_H05 | c30419c6-c393-4e3b-a7a3-436979cdb471 | gps_far | GPS point 1.8 km from the household | 1805
2026-09-20 | enum_Q_11 | idp_NG034011_C16 | idp_NG034011_C16_H04 | 8082d09d-2a0f-4b56-b7be-fc88501816ce | children_exceed_hh | More children than household members | 4 + 7 children, household of 10
2026-09-22 | enum_Q_17 | non_idp_NG034015_R2_03 | non_idp_NG034015_R2_03_H03 | 7e148460-1684-46a9-9adf-0ac83529b0b8 | gps_far | GPS point 4.3 km from the household | 4329
2026-09-22 | enum_Q_17 | non_idp_NG034015_R2_03 | non_idp_NG034015_R2_03_R01 | 8cdc5437-40ba-40b2-82bd-320d68584530 | fcs_hhs_contradiction | Acceptable food consumption with severe hunger | FCS 53.0, HHS 4
2026-09-24 | enum_Q_12 | non_idp_NG034010_R1_02 | non_idp_NG034010_R1_02_R02 | 7f43e211-056f-4531-8247-73afa43af313 | fcs_hhs_contradiction | Acceptable food consumption with severe hunger | FCS 42.0, HHS 4

## Removed
Interviews removed from the dataset, and why
Synthetic data – not real findings
date | enumerator_id | cluster_id | household_id | _uuid | check_id | reason
2026-08-18 | enum_Q_01 | idp_NG034001_C02 | idp_NG034001_C02_H02 | 566b7134-71fd-4925-a668-6c5313bb89a2 | C02 | Same submission uploaded more than once
2026-08-20 | enum_Q_06 | non_idp_NG034007_C02 | non_idp_NG034007_C02_H06 | d683e0b3-55e7-41c6-ad08-0f0d53dbd28c | C04 | Interview took 5 minutes
2026-08-21 | enum_Q_01 | idp_NG034001_C05 | idp_NG034001_C05_H04 | 3e235357-7c28-4279-b92e-805ffa85f925 | C01 | Respondent did not consent
2026-08-21 | enum_Q_13 | non_idp_NG034011_C03 | non_idp_NG034011_C03_H02 | cf4a5a1b-d920-4c98-b8ae-65750ddac0ed | C04 | Interview took 6 minutes
2026-08-21 | enum_Q_20 | non_idp_NG034019_C04 | non_idp_NG034019_C04_H01 | 4fc72141-8e01-49d8-a4fb-5a3b61fd7b41 | C01 | Respondent did not consent
2026-08-22 | enum_Q_10 | idp_NG034010_C07 | idp_NG034010_C07_H05 | 9e633714-c602-4336-8163-7b41b2079836 | C04 | Interview took 12 minutes
2026-08-22 | enum_Q_10 | idp_NG034010_C07 | idp_NG034010_C07_H06 | d77085ab-f12c-4e86-baae-86fca6896d68 | C01 | Respondent did not consent
2026-08-22 | enum_Q_20 | non_idp_NG034019_C05 | non_idp_NG034019_C05_H05 | cf636711-89b4-4e47-85db-9af5403c6424 | C04 | Interview took 10 minutes
2026-08-23 | enum_Q_04 | non_idp_NG034001_C17 | non_idp_NG034001_C17_H05 | 47b68be7-2d35-4f77-9095-084f977298d5 | C04 | Interview took 11 minutes
2026-08-23 | enum_Q_14 | non_idp_NG034011_C04 | non_idp_NG034011_C04_H06 | dd1cc39f-1181-4dc7-a587-c2a56aefa9b2 | C01 | Respondent did not consent
2026-08-24 | enum_Q_19 | non_idp_NG034019_C07 | non_idp_NG034019_C07_H06 | d62887bc-8a2f-497a-af54-b776edc003a4 | C01 | Respondent did not consent
2026-08-24 | enum_Q_20 | non_idp_NG034019_C07 | non_idp_NG034019_C07_H03 | 3d3532cf-52bc-4e35-b381-a1113ff4adbc | C01 | Respondent did not consent
2026-08-25 | enum_Q_20 | non_idp_NG034019_C08 | non_idp_NG034019_C08_H04 | 7b4147e3-c7ea-4718-a98f-98c0f796bff8 | C01 | Respondent did not consent
2026-08-25 | enum_Q_20 | non_idp_NG034019_C08 | non_idp_NG034019_C08_H06 | 04fcfa30-d9ea-413b-aada-52b486c48415 | C04 | Interview took 12 minutes
2026-08-26 | enum_Q_02 | idp_NG034001_C10 | idp_NG034001_C10_H03 | 79e24928-e340-497b-a954-2711aed44aeb | C04 | Interview took 5 minutes
2026-08-26 | enum_Q_08 | non_idp_NG034009_C04 | non_idp_NG034009_C04_H04 | 2524fd85-6c00-48a2-b9df-11d9c4efa9af | C04 | Interview took 6 minutes
2026-08-26 | enum_Q_09 | idp_NG034010_C09 | idp_NG034010_C09_R02 | 2f385dd0-ddc2-42ad-a55f-535f61992723 | C04 | Interview took 4 minutes
2026-08-26 | enum_Q_10 | idp_NG034010_C09 | idp_NG034010_C09_R01 | a4312822-46c1-4627-99fd-0f55fa12d573 | C01 | Respondent did not consent
2026-08-26 | enum_Q_19 | non_idp_NG034019_C09 | non_idp_NG034019_C09_H06 | ea27f8fd-57b2-4f3f-ae9d-c5cce7bf69c4 | C03 | Household already interviewed in an earlier submission
2026-08-26 | enum_Q_23 | non_idp_NG034022_C04 | non_idp_NG034022_C04_H03 | e7828a98-ff0e-4a05-9b55-0adcecd0f6d4 | C01 | Respondent did not consent
2026-08-27 | enum_Q_02 | idp_NG034001_C11 | idp_NG034001_C11_H05 | 5147ed72-23cd-4d71-a2e1-31f5410e1eb8 | C04 | Interview took 5 minutes
2026-08-27 | enum_Q_07 | non_idp_NG034009_C05 | non_idp_NG034009_C05_H01 | 14e64a0a-3a3a-465f-8112-3da06a1a348e | C02 | Same submission uploaded more than once
2026-08-27 | enum_Q_07 | non_idp_NG034009_C05 | non_idp_NG034009_C05_H06 | 0256e61d-708a-4fd2-adeb-c7a4f2378466 | C04 | Interview took 12 minutes
2026-08-27 | enum_Q_09 | idp_NG034010_C10 | idp_NG034010_C10_R03 | 019ade44-d976-4349-ba51-8b7f0eae4908 | C03 | Household already interviewed in an earlier submission
2026-08-27 | enum_Q_17 | non_idp_NG034018_C01 | non_idp_NG034018_C01_H02 | 08ede736-ad82-4c78-a822-998ffd681521 | C02 | Same submission uploaded more than once
2026-08-27 | enum_Q_20 | non_idp_NG034019_C10 | non_idp_NG034019_C10_H04 | 88e6da2b-d053-4bcd-b423-24e680788fdc | C04 | Interview took 5 minutes
2026-08-27 | enum_Q_23 | non_idp_NG034022_C05 | non_idp_NG034022_C05_H05 | 85f04f3b-4d1c-4f77-b3d4-5e1b23e63551 | C02 | Same submission uploaded more than once
2026-08-28 | enum_Q_06 | non_idp_NG034007_C96 | non_idp_NG034007_C14_H01 | 05ce5bec-e5f2-4234-888b-b4625601b9b3 | C05 | Cluster code not in the sample
2026-08-28 | enum_Q_15 | non_idp_NG034012_C08 | non_idp_NG034012_C08_H02 | d9209f16-7596-4d7c-9b0b-ce00f6ac4977 | C04 | Interview took 7 minutes
2026-08-28 | enum_Q_24 | non_idp_NG034022_C07 | non_idp_NG034022_C07_H02 | e074ae17-c7b7-47f1-a18c-20a8de4ea958 | C03 | Household already interviewed in an earlier submission
2026-08-29 | enum_Q_08 | non_idp_NG034009_C07 | non_idp_NG034009_C07_H01 | dc700251-becf-4191-8c50-2407f841a884 | C04 | Interview took 8 minutes
2026-08-29 | enum_Q_12 | non_idp_NG034010_C14 | non_idp_NG034010_C14_H05 | 101382e1-f859-4a80-87ce-c93aef9c1400 | C04 | Interview took 10 minutes
2026-08-30 | enum_Q_08 | non_idp_NG034009_C08 | non_idp_NG034009_C08_H01 | 7b405f89-21ed-4a43-928e-eb2322b796cc | C04 | Interview took 10 minutes
2026-08-30 | enum_Q_08 | non_idp_NG034009_C08 | non_idp_NG034009_C08_H04 | 459a6010-8792-41ca-b698-b857946fc46c | C03 | Household already interviewed in an earlier submission
2026-08-30 | enum_Q_18 | non_idp_NG034018_C02 | non_idp_NG034018_C02_H01 | f2b60547-5272-4e5a-bd89-654c0b93ddf2 | C01 | Respondent did not consent
2026-08-31 | enum_Q_01 | non_idp_NG034001_C91 | non_idp_NG034001_C02_H01 | 9eec0924-86aa-4e39-ac8e-ced8a0184d14 | C05 | Cluster code not in the sample
2026-08-31 | enum_Q_08 | non_idp_NG034009_C09 | non_idp_NG034009_C09_H03 | c9799df9-2053-4640-9fd9-58e33ff9fcb1 | C02 | Same submission uploaded more than once
2026-08-31 | enum_Q_08 | non_idp_NG034009_C09 | non_idp_NG034009_C09_R02 | c55c0008-97b4-4433-bed1-6b3bae3d0463 | C04 | Interview took 9 minutes
2026-08-31 | enum_Q_13 | non_idp_NG034011_C09 | non_idp_NG034011_C09_H01 | 18787aa5-afb7-4d9a-9e3e-3bdce7a2e8bf | C04 | Interview took 9 minutes
2026-08-31 | enum_Q_22 | non_idp_NG034020_C05 | non_idp_NG034020_C05_H03 | 40f3db25-436c-4534-96ad-7fea8433acfa | C01 | Respondent did not consent
2026-09-01 | enum_Q_02 | non_idp_NG034001_C05 | non_idp_NG034001_C05_H02 | bc428d2f-ad10-421a-9ea2-bac9a2ca169b | C04 | Interview took 5 minutes
2026-09-01 | enum_Q_02 | non_idp_NG034001_C94 | non_idp_NG034001_C05_H06 | 2ed455e1-f937-4809-902b-b3823642134b | C05 | Cluster code not in the sample
2026-09-01 | enum_Q_19 | non_idp_NG034019_C14 | non_idp_NG034019_C14_H06 | 19c91baa-3831-472f-a551-5909dc97cebc | C01 | Respondent did not consent
2026-09-01 | enum_Q_21 | non_idp_NG034020_C06 | non_idp_NG034020_C06_H03 | f6db5cca-a954-4bd6-894f-69f36f266b75 | C01 | Respondent did not consent
2026-09-01 | enum_Q_23 | non_idp_NG034022_C12 | non_idp_NG034022_C12_H06 | e851732b-b109-43d2-96ac-d761b17ee3ca | C03 | Household already interviewed in an earlier submission
2026-09-02 | enum_Q_03 | non_idp_NG034006_C14 | non_idp_NG034006_C14_H06 | 2dc5cc81-5072-476a-825a-679f41c7f24a | C04 | Interview took 12 minutes
2026-09-02 | enum_Q_03 | non_idp_NG034006_C14 | non_idp_NG034006_C14_R02 | 46c9b044-62f7-43ae-86c6-5892563d4b69 | C02 | Same submission uploaded more than once
2026-09-02 | enum_Q_08 | non_idp_NG034009_C10 | non_idp_NG034009_C10_H02 | 2ac12273-71d2-441d-8c84-1ae0237d7440 | C04 | Interview took 6 minutes
2026-09-02 | enum_Q_09 | idp_NG034010_C94 | idp_NG034010_C14_H01 | 763c6037-41e5-47e7-88fa-f4771237b415 | C05 | Cluster code not in the sample
2026-09-02 | enum_Q_21 | non_idp_NG034020_C08 | non_idp_NG034020_C08_H03 | 5fd9d2d8-8a96-4329-9706-5ba26126cffb | C01 | Respondent did not consent
2026-09-02 | enum_Q_23 | non_idp_NG034022_C13 | non_idp_NG034022_C13_H02 | b44fcc3e-a0cf-4b62-b9ce-1931ec61e7ae | C01 | Respondent did not consent
2026-09-03 | enum_Q_09 | non_idp_NG034010_C01 | non_idp_NG034010_C01_H05 | 32e92dec-7a3e-417b-83b5-a61accbf096e | C04 | Interview took 12 minutes
2026-09-04 | enum_Q_01 | non_idp_NG034001_C10 | non_idp_NG034001_C10_H01 | 63dcfc82-4735-42f3-a174-83badb723a6a | C01 | Respondent did not consent
2026-09-04 | enum_Q_02 | non_idp_NG034001_C10 | non_idp_NG034001_C10_H03 | 95152001-ec72-468c-bf55-d01cf501ba13 | C01 | Respondent did not consent
2026-09-04 | enum_Q_02 | non_idp_NG034001_C97 | non_idp_NG034001_C10_R01 | 33085ca2-98ea-4437-9661-edf47d1b91ac | C05 | Cluster code not in the sample
2026-09-04 | enum_Q_03 | non_idp_NG034006_C15 | non_idp_NG034006_C15_H04 | d2168cf8-06fc-45c4-bbc1-ca3002e97510 | C04 | Interview took 9 minutes
2026-09-04 | enum_Q_05 | non_idp_NG034007_R1_02 | non_idp_NG034007_R1_02_H02 | 38bdaddb-5147-4d88-bfe0-f9daad81517c | C04 | Interview took 10 minutes
2026-09-04 | enum_Q_23 | non_idp_NG034022_C17 | non_idp_NG034022_C17_H03 | 5bd38002-b4a3-4082-92e4-740d334f0708 | C04 | Interview took 7 minutes
2026-09-05 | enum_Q_05 | non_idp_NG034007_R1_03 | non_idp_NG034007_R1_03_H02 | 27c65313-8602-4da3-a27e-22c330a8724a | C01 | Respondent did not consent
2026-09-05 | enum_Q_09 | non_idp_NG034010_C03 | non_idp_NG034010_C03_H02 | 4eb00668-c253-4b07-9c0f-8aa0cd0426cc | C01 | Respondent did not consent
2026-09-05 | enum_Q_12 | idp_NG034011_C04 | idp_NG034011_C04_H03 | c1884e31-9c02-41dd-b3d3-2f116472f856 | C01 | Respondent did not consent
2026-09-05 | enum_Q_17 | non_idp_NG034015_R1_02 | non_idp_NG034015_R1_02_H05 | 6494158a-1e84-4ea1-b1f1-c7202f56723a | C04 | Interview took 4 minutes
2026-09-05 | enum_Q_23 | non_idp_NG034022_R1_01 | non_idp_NG034022_R1_01_H02 | 2fa687b8-9383-4739-9ffe-517d0a84170b | C04 | Interview took 6 minutes
2026-09-06 | enum_Q_03 | non_idp_NG034006_C17 | non_idp_NG034006_C17_H05 | b36d9fcb-504a-4da4-b03c-a2d912a7e4e5 | C03 | Household already interviewed in an earlier submission
2026-09-06 | enum_Q_16 | non_idp_NG034015_C01 | non_idp_NG034015_C01_H03 | 3bfb6647-d323-4afe-83ab-f61297b4ee7b | C04 | Interview took 4 minutes
2026-09-06 | enum_Q_22 | non_idp_NG034020_C10 | non_idp_NG034020_C10_H06 | d6a85c2a-105c-42d7-aa5a-96444b79c7b6 | C03 | Household already interviewed in an earlier submission
2026-09-06 | enum_Q_24 | non_idp_NG034022_R1_02 | non_idp_NG034022_R1_02_H03 | 4bd7ee54-7df5-4ff4-bae8-9ab6f7582c9c | C01 | Respondent did not consent
2026-09-07 | enum_Q_03 | non_idp_NG034001_R1_01 | non_idp_NG034001_R1_01_H06 | 780df966-6448-4b36-aee5-deb04226d7e4 | C04 | Interview took 12 minutes
2026-09-07 | enum_Q_04 | non_idp_NG034001_R1_01 | non_idp_NG034001_R1_01_H02 | d39c7655-0c3b-44b6-a874-e776ea19441f | C04 | Interview took 11 minutes
2026-09-07 | enum_Q_08 | non_idp_NG034009_C12 | non_idp_NG034009_C12_H02 | 4016735b-3dd3-4d26-b1ef-af18c4deea6d | C04 | Interview took 10 minutes
2026-09-07 | enum_Q_13 | non_idp_NG034011_C13 | non_idp_NG034011_C13_H02 | c92926a3-eed0-496a-a0c7-45b9e892ba1f | C01 | Respondent did not consent
2026-09-08 | enum_Q_03 | non_idp_NG034001_R1_C98 | non_idp_NG034001_R1_02_H01 | ec28c623-3693-48c8-82f6-1786f8a324bf | C05 | Cluster code not in the sample
2026-09-08 | enum_Q_07 | non_idp_NG034009_C13 | non_idp_NG034009_C13_H01 | 86f0f8b4-55f3-4543-bed6-df45da225385 | C04 | Interview took 10 minutes
2026-09-08 | enum_Q_17 | non_idp_NG034018_R1_01 | non_idp_NG034018_R1_01_H06 | 0d653f46-f3f6-49b4-9506-381bb0db3b0c | C01 | Respondent did not consent
2026-09-08 | enum_Q_21 | non_idp_NG034020_C12 | non_idp_NG034020_C12_H03 | df48ddbe-073a-4a68-b9b8-6298f483cf45 | C04 | Interview took 6 minutes
2026-09-09 | enum_Q_12 | idp_NG034011_C08 | idp_NG034011_C08_H03 | 5afaa8a6-329e-40da-ba6b-3c5802f91837 | C04 | Interview took 5 minutes
2026-09-10 | enum_Q_07 | non_idp_NG034009_C16 | non_idp_NG034009_C16_H03 | 4c2b081a-bdc8-40e3-ac61-d83385240120 | C04 | Interview took 6 minutes
2026-09-10 | enum_Q_17 | non_idp_NG034018_R1_04 | non_idp_NG034018_R1_04_H05 | a0417f89-f27a-4007-9276-ba30de291b51 | C01 | Respondent did not consent
2026-09-11 | enum_Q_22 | non_idp_NG034020_C14 | non_idp_NG034020_C14_H05 | 3af542ec-41ff-4215-835c-e8162526b619 | C01 | Respondent did not consent
2026-09-12 | enum_Q_21 | non_idp_NG034020_C15 | non_idp_NG034020_C15_H02 | 685e1649-73b5-4898-a18b-a316b199178c | C04 | Interview took 12 minutes
2026-09-13 | enum_Q_14 | non_idp_NG034012_C03 | non_idp_NG034012_C03_H02 | 47fb4f78-d56f-48ad-b17a-96dfb8555363 | C03 | Household already interviewed in an earlier submission
2026-09-13 | enum_Q_19 | non_idp_NG034018_R2_02 | non_idp_NG034018_R2_02_R01 | 24d2c5b3-3c3f-4340-b656-49a084e21c67 | C04 | Interview took 8 minutes
2026-09-13 | enum_Q_20 | non_idp_NG034018_R2_02 | non_idp_NG034018_R2_02_H01 | d423a652-b941-4d3d-aeee-7da26694cdbc | C04 | Interview took 5 minutes
2026-09-14 | enum_Q_14 | non_idp_NG034012_C04 | non_idp_NG034012_C04_H04 | 94311830-daa9-46f5-9574-0557596b0c6f | C04 | Interview took 8 minutes
2026-09-14 | enum_Q_15 | non_idp_NG034015_C13 | non_idp_NG034015_C13_R01 | ffecb1c1-bb09-4c48-9424-28120626fb68 | C02 | Same submission uploaded more than once
2026-09-16 | enum_Q_21 | non_idp_NG034020_R1_01 | non_idp_NG034020_R1_01_H04 | fecbfc0f-6407-4111-9674-fe95c5be6f6e | C04 | Interview took 5 minutes
2026-09-17 | enum_Q_14 | non_idp_NG034012_C05 | non_idp_NG034012_C05_R02 | 4df169f0-1018-4426-8dd2-c09ea5dd6960 | C04 | Interview took 7 minutes
2026-09-17 | enum_Q_21 | non_idp_NG034020_R1_02 | non_idp_NG034020_R1_02_H03 | 8254accc-63f6-4f6f-807d-814d79ca9e54 | C04 | Interview took 11 minutes
2026-09-18 | enum_Q_08 | non_idp_NG034009_R1_01 | non_idp_NG034009_R1_01_H01 | 222eb40a-e778-40b8-bef0-9dba744529ca | C01 | Respondent did not consent
2026-09-19 | enum_Q_07 | non_idp_NG034009_R2_01 | non_idp_NG034009_R2_01_H01 | eeb01e17-f786-4364-a8b1-fc371e03cbf0 | C01 | Respondent did not consent
2026-09-19 | enum_Q_08 | non_idp_NG034009_R2_01 | non_idp_NG034009_R2_01_R01 | 4f2d7086-32c2-485a-8b12-d068cbc06cd1 | C01 | Respondent did not consent
2026-09-19 | enum_Q_17 | non_idp_NG034015_R2_01 | non_idp_NG034015_R2_01_R02 | 54b108df-3414-4caf-a3bd-6eb80086c4d4 | C04 | Interview took 5 minutes
2026-09-22 | enum_Q_18 | non_idp_NG034015_R2_03 | non_idp_NG034015_R2_03_H06 | 40beb3b2-c7e5-4c74-a56a-4785aa1d4896 | C01 | Respondent did not consent
2026-09-24 | enum_Q_11 | non_idp_NG034010_R1_02 | non_idp_NG034010_R1_02_H02 | 3cb3fcee-c489-4774-8825-d00dd9d98721 | C01 | Respondent did not consent
2026-09-24 | enum_Q_12 | non_idp_NG034010_R1_02 | non_idp_NG034010_R1_02_H03 | bce2a2be-76a5-4be4-b870-5b8112fbf0b9 | C04 | Interview took 11 minutes

## Enumerators
Enumerators
Synthetic data – not real findings
enumerator_id | interviews | median minutes | % repeated answers | interviews removed | interviews flagged | pattern
enum_Q_01 | 61 | 43.2 | 3.3 | 4 | 4
enum_Q_02 | 65 | 42.1 | 0 | 6 | 3
enum_Q_03 | 67 | 44.4 | 3 | 6 | 3
enum_Q_04 | 55 | 38.4 | 0 | 2 | 4
enum_Q_05 | 54 | 43 | 0 | 2 | 2
enum_Q_06 | 66 | 42.5 | 0 | 2 | 8
enum_Q_07 | 61 | 42.4 | 3.3 | 5 | 8
enum_Q_08 | 68 | 41.8 | 2.9 | 10 | 7
enum_Q_09 | 60 | 41.3 | 3.3 | 5 | 8
enum_Q_10 | 61 | 39.2 | 0 | 3 | 5
enum_Q_11 | 57 | 41 | 0 | 1 | 3
enum_Q_12 | 62 | 43.7 | 0 | 4 | 3
enum_Q_13 | 61 | 42.4 | 0 | 3 | 3
enum_Q_14 | 65 | 41.1 | 0 | 4 | 1
enum_Q_15 | 70 | 41.4 | 2.9 | 2 | 3
enum_Q_16 | 51 | 40.1 | 0 | 1 | 5
enum_Q_17 | 61 | 42.2 | 3.3 | 5 | 6
enum_Q_18 | 60 | 40 | 0 | 2 | 2
enum_Q_19 | 62 | 41.2 | 0 | 4 | 3
enum_Q_20 | 64 | 43.2 | 0 | 7 | 3
enum_Q_21 | 63 | 43.5 | 0 | 6 | 3
enum_Q_22 | 57 | 42.9 | 0 | 3 | 2
enum_Q_23 | 69 | 43.5 | 5.8 | 6 | 6
enum_Q_24 | 54 | 43.3 | 0 | 2 | 2

## Progress
Progress against target by LGA
Synthetic data – not real findings
adm1_name | adm2_name | pop_type | target | achieved | percent
Sokoto | Binji | idp | 66 | 64 | 97
Sokoto | Binji | non_idp | 102 | 87 | 85.3
Sokoto | Goronyo | non_idp | 102 | 94 | 92.2
Sokoto | Gudu | non_idp | 96 | 93 | 96.9
Sokoto | Isa | non_idp | 102 | 93 | 91.2
Sokoto | Kebbe | idp | 84 | 81 | 96.4
Sokoto | Kebbe | non_idp | 96 | 93 | 96.9
Sokoto | Kware | idp | 96 | 94 | 97.9
Sokoto | Kware | non_idp | 102 | 99 | 97.1
Sokoto | Rabah | non_idp | 102 | 99 | 97.1
Sokoto | Silame | non_idp | 96 | 93 | 96.9
Sokoto | Tambuwal | non_idp | 102 | 100 | 98
Sokoto | Tangaza | non_idp | 102 | 92 | 90.2
Sokoto | Tureta | non_idp | 102 | 97 | 95.1
Sokoto | Wurno | idp | 48 | 36 | 75
Sokoto | Wurno | non_idp | 102 | 94 | 92.2