## Summary
Data-quality digest: Partner S
Synthetic data – not real findings
Item | Value
Partner | Partner S
States | Yobe
Data as of | 2026-09-27
Submissions received | 1195
Interviews kept | 1117
Interviews removed | 78
Values corrected | 18
Interviews flagged for follow-up | 72
Households targeted | 1224
Households achieved | 1117
Progress against target | 91.3%

## Follow up
Interviews flagged: please check with the enumerator
Synthetic data – not real findings
date | enumerator_id | cluster_id | household_id | _uuid | check | issue | value
2026-08-18 | enum_S_03 | idp_NG036003_C15 | idp_NG036003_C15_R02 | 21afe17d-0d07-4f8b-a558-e97ff367f5ef | gps_far | GPS point 2.4 km from the household | 2381
2026-08-19 | enum_S_04 | non_idp_NG036003_C03 | non_idp_NG036003_C03_H03 | c312380f-1d18-420c-94cb-ab58d2ef4fcd | gps_far | GPS point 3.9 km from the household | 3879
2026-08-19 | enum_S_17 | idp_NG036016_C11 | idp_NG036016_C11_R01 | 5e66e1c8-4b10-48cc-866c-36c5bb85403f | fcs_hhs_contradiction | Acceptable food consumption with severe hunger | FCS 93.5, HHS 6
2026-08-21 | enum_S_03 | non_idp_NG036003_C05 | non_idp_NG036003_C05_H06 | d1b8bc98-42a2-472a-9dfb-40434f370932 | fcs_flat | Every food group given the same number of days | 7
2026-08-21 | enum_S_04 | non_idp_NG036003_C05 | non_idp_NG036003_C05_H04 | fa2557a4-f731-4c05-9e93-ba1eaf7fbad0 | attending_exceed_school_age | More children attending school than of school age | 3
2026-08-23 | enum_S_04 | non_idp_NG036003_C06 | non_idp_NG036003_C06_H03 | 1d07b494-316a-478f-90c7-465cc7b9feed | fcs_hhs_contradiction | Acceptable food consumption with severe hunger | FCS 47.0, HHS 4
2026-08-23 | enum_S_05 | non_idp_NG036003_C09 | non_idp_NG036003_C09_H02 | f69e4aba-2c79-4d67-9b00-401685c4393d | attending_exceed_school_age | More children attending school than of school age | 3
2026-08-24 | enum_S_07 | non_idp_NG036005_C10 | non_idp_NG036005_C10_H04 | 5e0410cd-2373-4235-a146-4c49f656b55e | gps_far | GPS point 5.0 km from the household | 4972
2026-08-25 | enum_S_08 | non_idp_NG036005_C11 | non_idp_NG036005_C11_H04 | d8d5c2f1-b038-48de-901d-258f8dbebffe | gps_far | GPS point 1.3 km from the household | 1279
2026-08-25 | enum_S_17 | idp_NG036016_C14 | idp_NG036016_C14_H05 | 9b0b7871-f60c-48f3-9861-3aadbdc3ef10 | fcs_hhs_contradiction | Acceptable food consumption with severe hunger | FCS 38.0, HHS 5
2026-08-25 | enum_S_18 | idp_NG036016_C14 | idp_NG036016_C14_H02 | 5e4a2058-8e2c-47bb-b0cb-b6c4e9feac84 | fcs_flat | Every food group given the same number of days | 7
2026-08-26 | enum_S_01 | idp_NG036002_C01 | idp_NG036002_C01_H01 | 2ef1a851-3f3a-44c5-ae5d-b0a253cbd09b | fcs_hhs_contradiction | Acceptable food consumption with severe hunger | FCS 42.0, HHS 4
2026-08-26 | enum_S_08 | non_idp_NG036005_C14 | non_idp_NG036005_C14_H01 | 58b301ac-310c-4394-bd9c-f49aa70995d0 | fcs_hhs_contradiction | Acceptable food consumption with severe hunger | FCS 93.5, HHS 6
2026-08-26 | enum_S_09 | idp_NG036006_C13 | idp_NG036006_C13_H01 | 0d216f48-9bbf-4b11-b2b3-ba7f735bee04 | gps_far | GPS point 2.0 km from the household | 1996
2026-08-27 | enum_S_05 | non_idp_NG036003_C12 | non_idp_NG036003_C12_R01 | bff05692-56d2-403e-8d6f-e91d2fa99bce | fcs_hhs_contradiction | Acceptable food consumption with severe hunger | FCS 93.5, HHS 6
2026-08-27 | enum_S_18 | non_idp_NG036016_C01 | non_idp_NG036016_C01_R01 | 42e51c4a-a3ca-4831-b589-607b225b9a12 | fcs_flat | Every food group given the same number of days | 7
2026-08-28 | enum_S_05 | non_idp_NG036003_C13 | non_idp_NG036003_C13_H01 | 75c8b393-a621-4177-977c-fd1adaee5ce5 | fcs_flat | Every food group given the same number of days | 7
2026-08-28 | enum_S_15 | non_idp_NG036015_C13 | non_idp_NG036015_C13_H03 | 904fd701-139c-433a-908d-008e76783906 | attending_exceed_school_age | More children attending school than of school age | 3
2026-08-29 | enum_S_12 | idp_NG036007_C04 | idp_NG036007_C04_H02 | 0c1d8688-ffb1-4f75-9129-bc7ca8146dc4 | fcs_hhs_contradiction | Acceptable food consumption with severe hunger | FCS 37.5, HHS 5
2026-08-29 | enum_S_14 | non_idp_NG036008_C07 | non_idp_NG036008_C07_H06 | dfbb36fc-e038-47e8-a1da-d35f7439c0a3 | gps_far | GPS point 2.8 km from the household | 2849
2026-08-29 | enum_S_18 | non_idp_NG036016_C03 | non_idp_NG036016_C03_H05 | 02e363d5-12ee-4d45-a998-561027528dbc | gps_far | GPS point 2.4 km from the household | 2358
2026-08-30 | enum_S_07 | idp_NG036006_C01 | idp_NG036006_C01_H02 | 5d9a0852-2525-4db3-9c77-f132a293de34 | gps_far | GPS point 1.1 km from the household | 1084
2026-08-30 | enum_S_08 | idp_NG036006_C01 | idp_NG036006_C01_H06 | 7931ffc5-109f-4791-a6c1-e71d69f53c65 | gps_far | GPS point 3.4 km from the household | 3449
2026-08-30 | enum_S_10 | idp_NG036006_C14 | idp_NG036006_C14_H06 | 14e6a800-940f-403f-a15e-750b25079c6b | gps_far | GPS point 1.6 km from the household | 1634
2026-08-30 | enum_S_12 | idp_NG036007_C05 | idp_NG036007_C05_H01 | a6ba2afc-702e-489e-bac6-8fc4b4a48c9b | attending_exceed_school_age | More children attending school than of school age | 3
2026-08-31 | enum_S_02 | idp_NG036002_C06 | idp_NG036002_C06_H02 | 2d708da7-5007-43b0-b8f6-c2554b48ac0b | gps_far | GPS point 1.0 km from the household | 990
2026-08-31 | enum_S_13 | non_idp_NG036008_C09 | non_idp_NG036008_C09_R02 | b58ff778-b44b-4f4e-b667-441471daf494 | fcs_flat | Every food group given the same number of days | 7
2026-09-01 | enum_S_04 | non_idp_NG036002_R1_02 | non_idp_NG036002_R1_02_H05 | f38d1566-f87d-4d7e-9fb0-f759ce922c87 | fcs_flat | Every food group given the same number of days | 7
2026-09-02 | enum_S_13 | non_idp_NG036008_C12 | non_idp_NG036008_C12_R01 | 7d2b73bd-e7c6-4e76-b231-6cc69434911f | fcs_hhs_contradiction | Acceptable food consumption with severe hunger | FCS 41.5, HHS 4
2026-09-03 | enum_S_12 | non_idp_NG036007_C02 | non_idp_NG036007_C02_H03 | b2ed248c-6fc9-4adf-9893-afe5c06d97b6 | fcs_hhs_contradiction | Acceptable food consumption with severe hunger | FCS 45.0, HHS 4
2026-09-03 | enum_S_15 | idp_NG036016_C02 | idp_NG036016_C02_H06 | 42e5841f-2be3-444b-a6e4-7d2bba8404e5 | fcs_flat | Every food group given the same number of days | 7
2026-09-04 | enum_S_09 | non_idp_NG036006_C01 | non_idp_NG036006_C01_H05 | 51e335ad-b231-4f00-8dc6-33e4258a88ae | gps_far | GPS point 3.1 km from the household | 3125
2026-09-04 | enum_S_13 | non_idp_NG036015_C02 | non_idp_NG036015_C02_H02 | 9f9cfc5a-ee99-428c-999d-07d73fb74a11 | fcs_hhs_contradiction | Acceptable food consumption with severe hunger | FCS 41.0, HHS 4
2026-09-04 | enum_S_16 | idp_NG036016_C03 | idp_NG036016_C03_R02 | 9559ce3e-feb8-43a0-83fe-773c22914f79 | fcs_hhs_contradiction | Acceptable food consumption with severe hunger | FCS 60.0, HHS 4
2026-09-05 | enum_S_08 | idp_NG036006_C05 | idp_NG036006_C05_H04 | 151e51f1-1fa7-42cb-a29b-1bc288f7d0b8 | fcs_hhs_contradiction | Acceptable food consumption with severe hunger | FCS 93.5, HHS 6
2026-09-05 | enum_S_09 | non_idp_NG036006_C04 | non_idp_NG036006_C04_H04 | 6831c579-54bd-4f85-a78f-e9f0d0168aef | gps_far | GPS point 0.9 km from the household | 927
2026-09-05 | enum_S_11 | non_idp_NG036007_C04 | non_idp_NG036007_C04_H06 | 474ee08f-3a53-4b3c-af33-fd37b04b8bae | gps_far | GPS point 2.8 km from the household | 2840
2026-09-05 | enum_S_16 | idp_NG036016_C04 | idp_NG036016_C04_H01 | 14cdef96-ea84-4044-8286-bac04121fba4 | gps_far | GPS point 2.3 km from the household | 2285
2026-09-06 | enum_S_10 | non_idp_NG036006_C05 | non_idp_NG036006_C05_R01 | 6d92b513-e68e-426e-ae0d-5123c86c9365 | gps_far | GPS point 1.5 km from the household | 1451
2026-09-07 | enum_S_08 | idp_NG036006_C06 | idp_NG036006_C06_H06 | d70c5524-bd14-478a-9709-2501be675e56 | fcs_flat | Every food group given the same number of days | 0
2026-09-08 | enum_S_02 | idp_NG036002_C13 | idp_NG036002_C13_R01 | 795b40ca-0081-4adf-a24c-3a1d1bf97712 | gps_far | GPS point 0.7 km from the household | 721
2026-09-08 | enum_S_15 | idp_NG036016_C07 | idp_NG036016_C07_H02 | fa31ec27-5be0-4f6c-9f85-fde25c0528e1 | fcs_hhs_contradiction | Acceptable food consumption with severe hunger | FCS 93.5, HHS 6
2026-09-09 | enum_S_09 | non_idp_NG036006_C07 | non_idp_NG036006_C07_H04 | da93101d-264b-470c-b148-3581620db9a1 | children_exceed_hh | More children than household members | 0 + 4 children, household of 3
2026-09-09 | enum_S_10 | non_idp_NG036006_C07 | non_idp_NG036006_C07_H02 | f2007068-ba99-4d8c-9893-ecc82054d95c | attending_exceed_school_age | More children attending school than of school age | 3
2026-09-10 | enum_S_01 | non_idp_NG036002_C04 | non_idp_NG036002_C04_H02 | da7affa6-41ce-4a4d-909c-658acd80cc7a | fcs_flat | Every food group given the same number of days | 0
2026-09-10 | enum_S_05 | idp_NG036005_C04 | idp_NG036005_C04_H01 | 644a65dc-8280-4437-9828-4a2591bb5058 | fcs_hhs_contradiction | Acceptable food consumption with severe hunger | FCS 37.5, HHS 4
2026-09-10 | enum_S_05 | idp_NG036005_C04 | idp_NG036005_C04_H05 | 2d498371-4a23-450b-a1c7-627da024dee6 | gps_far | GPS point 3.1 km from the household | 3148
2026-09-11 | enum_S_13 | non_idp_NG036008_R1_04 | non_idp_NG036008_R1_04_H05 | 948624b3-dd5e-42c9-965c-6265da6a6e96 | children_exceed_hh | More children than household members | 2 + 9 children, household of 8
2026-09-11 | enum_S_15 | idp_NG036016_C10 | idp_NG036016_C10_H05 | 012e46aa-72c7-4558-ab55-f8cc76cf77e1 | attending_exceed_school_age | More children attending school than of school age | 3
2026-09-12 | enum_S_03 | non_idp_NG036002_R1_06 | non_idp_NG036002_R1_06_R01 | d8f2cbf9-46c4-434e-bdf2-ca6d340257c5 | gps_far | GPS point 4.8 km from the household | 4763
2026-09-12 | enum_S_13 | non_idp_NG036008_R2_01 | non_idp_NG036008_R2_01_H04 | 5e8c5402-bdf5-4bc9-b496-4d9bdb3e2aef | gps_far | GPS point 2.4 km from the household | 2367
2026-09-12 | enum_S_13 | non_idp_NG036008_R2_01 | non_idp_NG036008_R2_01_R02 | 86860259-4cae-4bf9-aabe-50fb3196bb87 | gps_far | GPS point 2.5 km from the household | 2511
2026-09-13 | enum_S_06 | idp_NG036005_C07 | idp_NG036005_C07_H05 | fa27c866-cc49-45cf-97cc-5e9f9f4d0e16 | fcs_hhs_contradiction | Acceptable food consumption with severe hunger | FCS 39.0, HHS 4
2026-09-13 | enum_S_18 | non_idp_NG036016_C14 | non_idp_NG036016_C14_H01 | b2ba3267-9e00-4d77-a435-c042c52218b9 | attending_exceed_school_age | More children attending school than of school age | 4
2026-09-14 | enum_S_06 | idp_NG036005_C08 | idp_NG036005_C08_H06 | 83439184-85c0-4568-b4d4-b4aad7f98912 | fcs_hhs_contradiction | Acceptable food consumption with severe hunger | FCS 44.5, HHS 4
2026-09-14 | enum_S_11 | non_idp_NG036007_C16 | non_idp_NG036007_C16_H02 | 9943fa1b-ef9d-4467-a762-6812866d65b6 | gps_far | GPS point 4.6 km from the household | 4630
2026-09-14 | enum_S_17 | non_idp_NG036016_C15 | non_idp_NG036016_C15_H02 | b725bcb8-a251-4355-9b35-8b218e497cb5 | gps_far | GPS point 3.7 km from the household | 3660
2026-09-14 | enum_S_17 | non_idp_NG036016_C15 | non_idp_NG036016_C15_H05 | 5299376c-21a0-4b4e-8575-3ff81354ec3b | fcs_hhs_contradiction | Acceptable food consumption with severe hunger | FCS 93.5, HHS 6
2026-09-14 | enum_S_17 | non_idp_NG036016_C15 | non_idp_NG036016_C15_H06 | 9ab58ce9-8043-4d1b-b318-941e00331e25 | gps_far | GPS point 4.9 km from the household | 4942
2026-09-15 | enum_S_05 | idp_NG036005_C09 | idp_NG036005_C09_H02 | 0da5d4f6-2001-4931-8bfc-c9613204e35f | fcs_hhs_contradiction | Acceptable food consumption with severe hunger | FCS 36.0, HHS 4
2026-09-15 | enum_S_06 | idp_NG036005_C09 | idp_NG036005_C09_H05 | ac895d75-54da-44ef-a273-9659ad8c93eb | attending_exceed_school_age | More children attending school than of school age | 2
2026-09-15 | enum_S_15 | non_idp_NG036015_R1_03 | non_idp_NG036015_R1_03_H05 | 6c570aa8-a737-411e-9941-eeb861b2f4b1 | attending_exceed_school_age | More children attending school than of school age | 5
2026-09-16 | enum_S_09 | non_idp_NG036006_C13 | non_idp_NG036006_C13_H03 | 58aa27e3-edd0-4079-8e9c-abd6dadd0c44 | fcs_flat | Every food group given the same number of days | 0
2026-09-16 | enum_S_16 | non_idp_NG036015_R2_01 | non_idp_NG036015_R2_01_H03 | e8a6979f-7009-45b0-b4ce-4d8a974047f6 | fcs_hhs_contradiction | Acceptable food consumption with severe hunger | FCS 39.0, HHS 4
2026-09-16 | enum_S_17 | non_idp_NG036016_R1_01 | non_idp_NG036016_R1_01_H04 | 626a7db8-f6b9-4666-b661-36d7bed05ef4 | fcs_hhs_contradiction | Acceptable food consumption with severe hunger | FCS 93.5, HHS 6
2026-09-17 | enum_S_04 | idp_NG036003_R1_01 | idp_NG036003_R1_01_H04 | c15d87bc-a626-404a-ad8b-299fd324ff45 | fcs_flat | Every food group given the same number of days | 7
2026-09-17 | enum_S_11 | non_idp_NG036007_R1_03 | non_idp_NG036007_R1_03_H05 | 160c98c8-be26-411a-8386-c26e6b260d17 | attending_exceed_school_age | More children attending school than of school age | 3
2026-09-19 | enum_S_09 | non_idp_NG036006_C16 | non_idp_NG036006_C16_H04 | 5b06b443-09d4-4a98-be84-c848dfa29a91 | children_exceed_hh | More children than household members | 1 + 6 children, household of 5
2026-09-21 | enum_S_10 | non_idp_NG036006_C17 | non_idp_NG036006_C17_H03 | 0b332c23-f514-4554-a2dd-5338dfc4e2db | gps_far | GPS point 1.4 km from the household | 1362
2026-09-22 | enum_S_10 | non_idp_NG036006_R1_01 | non_idp_NG036006_R1_01_H06 | 8211f6f2-5ce3-4ec0-9165-e296fb634b9e | fcs_hhs_contradiction | Acceptable food consumption with severe hunger | FCS 93.5, HHS 6
2026-09-26 | enum_S_04 | idp_NG036003_R1_07 | idp_NG036003_R1_07_H04 | 98f8a11b-eda3-4aa6-9b1a-2b15bea50d95 | fcs_flat | Every food group given the same number of days | 7
2026-09-27 | enum_S_04 | non_idp_NG036002_R2_01 | non_idp_NG036002_R2_01_H01 | 28daef41-340c-4adb-b1a7-1dc3cb03b9b7 | fcs_flat | Every food group given the same number of days | 0

## Removed
Interviews removed from the dataset, and why
Synthetic data – not real findings
date | enumerator_id | cluster_id | household_id | _uuid | check_id | reason
2026-08-18 | enum_S_04 | idp_NG036003_C15 | idp_NG036003_C15_H06 | 4c3f45c2-6be4-4a90-956a-2a5cabf56a40 | C04 | Interview took 4 minutes
2026-08-19 | enum_S_03 | non_idp_NG036003_C02 | non_idp_NG036003_C02_H04 | e1c1d368-2630-433e-b504-19809b9a90a4 | C01 | Respondent did not consent
2026-08-19 | enum_S_04 | non_idp_NG036003_C03 | non_idp_NG036003_C03_H04 | 2ed8b528-c66d-4e05-b8a1-2aa39d9fe30e | C01 | Respondent did not consent
2026-08-19 | enum_S_08 | non_idp_NG036005_C02 | non_idp_NG036005_C02_H02 | 4983850f-ab78-4b74-97cc-2d0038873142 | C04 | Interview took 8 minutes
2026-08-19 | enum_S_17 | idp_NG036016_C11 | idp_NG036016_C11_H01 | e2952087-af40-48a4-a117-c50ee2cf01ab | C04 | Interview took 4 minutes
2026-08-21 | enum_S_07 | non_idp_NG036005_C07 | non_idp_NG036005_C07_H02 | f0cd9f13-23f1-4a98-bd68-2feb99bf30cf | C04 | Interview took 6 minutes
2026-08-22 | enum_S_08 | non_idp_NG036005_C08 | non_idp_NG036005_C08_H05 | fe6f5fea-a011-4e7b-aa98-df4d51f0aa9b | C02 | Same submission uploaded more than once
2026-08-23 | enum_S_04 | non_idp_NG036003_C06 | non_idp_NG036003_C06_H01 | f58b8f6e-6819-42b0-a7c9-c284354c72b9 | C01 | Respondent did not consent
2026-08-28 | enum_S_05 | non_idp_NG036003_C13 | non_idp_NG036003_C13_H04 | a8ee269e-424d-4938-98ca-55bcc3728580 | C01 | Respondent did not consent
2026-08-28 | enum_S_14 | non_idp_NG036008_C05 | non_idp_NG036008_C05_H03 | eac38f6d-4e1e-40e6-b647-fe580134dbf9 | C04 | Interview took 6 minutes
2026-08-28 | enum_S_18 | non_idp_NG036016_C02 | non_idp_NG036016_C02_H05 | fb27e08f-0354-4470-8bad-1491b2b57768 | C03 | Household already interviewed in an earlier submission
2026-08-29 | enum_S_11 | idp_NG036007_C04 | idp_NG036007_C04_H01 | 68e3b06e-0a14-45ed-a587-2b7c9509dfb4 | C01 | Respondent did not consent
2026-08-29 | enum_S_13 | non_idp_NG036008_C07 | non_idp_NG036008_C07_H01 | 0b2b3c7a-aeb0-458e-a1a3-7c07b21defb4 | C04 | Interview took 7 minutes
2026-08-30 | enum_S_03 | non_idp_NG036003_C07 | non_idp_NG036003_C07_H02 | 8b916c17-35fe-429a-9d7a-9d9f40318927 | C02 | Same submission uploaded more than once
2026-08-30 | enum_S_08 | idp_NG036006_C01 | idp_NG036006_C01_H04 | 480a70b2-18af-4f67-a466-c2fd65c7274a | C01 | Respondent did not consent
2026-08-30 | enum_S_08 | idp_NG036006_C01 | idp_NG036006_C01_R01 | 8e9f6def-1956-4913-bbb1-7c393fae1b11 | C04 | Interview took 12 minutes
2026-08-30 | enum_S_16 | non_idp_NG036015_C15 | non_idp_NG036015_C15_H05 | b19814ce-f8a6-480f-be77-a4c2800df2e3 | C04 | Interview took 9 minutes
2026-08-31 | enum_S_01 | idp_NG036002_C06 | idp_NG036002_C06_H05 | 71393a1e-1a1c-44dc-8345-984164269d89 | C04 | Interview took 10 minutes
2026-08-31 | enum_S_02 | idp_NG036002_C06 | idp_NG036002_C06_H01 | 7098b5de-85fa-4f0e-a045-9db3d9a6e291 | C02 | Same submission uploaded more than once
2026-08-31 | enum_S_04 | non_idp_NG036002_R1_01 | non_idp_NG036002_R1_01_H02 | bdee5029-1ca2-46fe-83a7-a7105f72915f | C04 | Interview took 9 minutes
2026-08-31 | enum_S_04 | non_idp_NG036002_R1_01 | non_idp_NG036002_R1_01_H05 | 2c485e29-370d-40b7-a758-8d55baac33cd | C01 | Respondent did not consent
2026-08-31 | enum_S_06 | non_idp_NG036003_C15 | non_idp_NG036003_C15_H02 | 30209fc8-ecb3-4b0d-b6c1-2f9fafcf965e | C04 | Interview took 11 minutes
2026-08-31 | enum_S_09 | idp_NG036006_C15 | idp_NG036006_C15_R01 | 98231408-712a-4e1c-9300-491a6bcecbb3 | C01 | Respondent did not consent
2026-08-31 | enum_S_10 | idp_NG036006_C15 | idp_NG036006_C15_H05 | 9f78072e-564c-4b01-9e76-f253bfe6cb8f | C04 | Interview took 7 minutes
2026-09-01 | enum_S_01 | idp_NG036002_C07 | idp_NG036002_C07_H03 | 5bcb2f99-3bce-4940-984f-8b4cf3082869 | C04 | Interview took 6 minutes
2026-09-01 | enum_S_03 | non_idp_NG036002_R1_02 | non_idp_NG036002_R1_02_H04 | 3d269707-c44c-44be-9566-06e4ccb393eb | C01 | Respondent did not consent
2026-09-01 | enum_S_05 | non_idp_NG036003_C16 | non_idp_NG036003_C16_H04 | 1f736818-4251-4680-8fab-1af79c46e6de | C04 | Interview took 5 minutes
2026-09-01 | enum_S_11 | idp_NG036007_C07 | idp_NG036007_C07_H04 | 190c4785-25f9-4ab7-b69c-6637dfd820f9 | C01 | Respondent did not consent
2026-09-01 | enum_S_12 | idp_NG036007_C07 | idp_NG036007_C07_H06 | a29224dc-0ea0-47b9-b60a-5ffc8a6cfd31 | C04 | Interview took 11 minutes
2026-09-01 | enum_S_14 | non_idp_NG036008_C10 | non_idp_NG036008_C10_H01 | 6b43a151-ee63-4250-8c72-a435e94cfd78 | C01 | Respondent did not consent
2026-09-01 | enum_S_16 | non_idp_NG036015_C94 | non_idp_NG036015_C17_H01 | 0c338df4-fc5d-4b7d-8530-fc43894e51ce | C05 | Cluster code not in the sample
2026-09-02 | enum_S_11 | non_idp_NG036007_C01 | non_idp_NG036007_C01_H05 | 4c1102ab-d00c-45a9-b36a-5f5c05aa9a10 | C04 | Interview took 10 minutes
2026-09-02 | enum_S_12 | non_idp_NG036007_C01 | non_idp_NG036007_C01_R01 | 6360e12c-ce08-4526-b870-6d71271cad38 | C04 | Interview took 9 minutes
2026-09-02 | enum_S_14 | non_idp_NG036008_C12 | non_idp_NG036008_C12_H02 | f3917c95-1596-4940-9cb3-a4aca6803cbf | C04 | Interview took 8 minutes
2026-09-02 | enum_S_15 | idp_NG036016_C01 | idp_NG036016_C01_R01 | edb00d99-a675-464b-8e10-5be28af84889 | C01 | Respondent did not consent
2026-09-03 | enum_S_15 | idp_NG036016_C02 | idp_NG036016_C02_H02 | c2c504c1-11f9-4b8e-831e-c4578b7615d6 | C04 | Interview took 9 minutes
2026-09-03 | enum_S_18 | non_idp_NG036016_C07 | non_idp_NG036016_C07_H04 | afb15a48-36bb-4e4f-98ec-648005912dec | C04 | Interview took 10 minutes
2026-09-04 | enum_S_05 | idp_NG036005_C01 | idp_NG036005_C01_R01 | 526a226c-7a2f-4d6b-b45f-73aba29fd1f2 | C04 | Interview took 12 minutes
2026-09-04 | enum_S_08 | idp_NG036006_C04 | idp_NG036006_C04_H06 | efdc6950-9ff6-441e-8b57-4970a48baaeb | C03 | Household already interviewed in an earlier submission
2026-09-04 | enum_S_11 | non_idp_NG036007_C03 | non_idp_NG036007_C03_H04 | ab3c60d7-a8bd-4cba-9779-a618e7d88de8 | C01 | Respondent did not consent
2026-09-05 | enum_S_10 | non_idp_NG036006_C04 | non_idp_NG036006_C04_H05 | 61bfa975-465e-4d4e-8b50-d0886e43487a | C04 | Interview took 11 minutes
2026-09-05 | enum_S_14 | non_idp_NG036015_C03 | non_idp_NG036015_C03_H04 | 9b8aa718-b6a4-4b18-b412-07adc145fc04 | C01 | Respondent did not consent
2026-09-06 | enum_S_01 | idp_NG036002_C11 | idp_NG036002_C11_H05 | 25495cf7-8cb3-42e1-b09f-edda22b86c2a | C01 | Respondent did not consent
2026-09-06 | enum_S_03 | non_idp_NG036002_R1_05 | non_idp_NG036002_R1_05_H06 | 0dfbd5bf-d69c-4034-8688-2106110d50b7 | C04 | Interview took 11 minutes
2026-09-06 | enum_S_04 | non_idp_NG036002_R1_05 | non_idp_NG036002_R1_05_H01 | cbf49167-ccfb-4101-b6df-3c823c46bbfe | C04 | Interview took 5 minutes
2026-09-07 | enum_S_01 | idp_NG036002_C12 | idp_NG036002_C12_H03 | f752e271-3548-4e97-9dc4-e34c12aef245 | C03 | Household already interviewed in an earlier submission
2026-09-08 | enum_S_05 | idp_NG036005_C02 | idp_NG036005_C02_H01 | 2c7232e1-f2a9-461b-b3d0-88ca27b46d41 | C01 | Respondent did not consent
2026-09-09 | enum_S_09 | non_idp_NG036006_C07 | non_idp_NG036006_C07_H01 | 31183f5d-ae87-45d4-9544-dddfaeb0ae00 | C04 | Interview took 7 minutes
2026-09-09 | enum_S_16 | idp_NG036016_C08 | idp_NG036016_C08_H05 | 43977bc4-434a-4368-badf-35168fb12814 | C04 | Interview took 9 minutes
2026-09-09 | enum_S_18 | non_idp_NG036016_C12 | non_idp_NG036016_C12_H04 | 78965987-9b92-4f7f-a6e4-8c1600d37e05 | C01 | Respondent did not consent
2026-09-10 | enum_S_18 | non_idp_NG036016_C13 | non_idp_NG036016_C13_H02 | 856f70a5-1876-4dec-8774-7aa5bd9cfb34 | C01 | Respondent did not consent
2026-09-11 | enum_S_06 | idp_NG036005_C05 | idp_NG036005_C05_H05 | 192f837c-993b-4b84-8830-efbd9f6cd697 | C01 | Respondent did not consent
2026-09-11 | enum_S_10 | non_idp_NG036006_C08 | non_idp_NG036006_C08_H06 | a46e08b5-42e5-4cfd-a65d-2d2def78f6b2 | C03 | Household already interviewed in an earlier submission
2026-09-11 | enum_S_14 | non_idp_NG036008_R1_04 | non_idp_NG036008_R1_04_H01 | ef42ffd7-23b1-4d17-86df-a7e9a4385715 | C04 | Interview took 11 minutes
2026-09-12 | enum_S_14 | non_idp_NG036008_R2_01 | non_idp_NG036008_R2_01_R01 | 76d84aa6-8f50-4c5a-8095-f7b2c358dc8d | C04 | Interview took 11 minutes
2026-09-13 | enum_S_12 | non_idp_NG036007_C14 | non_idp_NG036007_C14_H06 | ca97b50a-b61b-4802-9a91-2cd915ea4d8b | C01 | Respondent did not consent
2026-09-13 | enum_S_18 | non_idp_NG036016_C14 | non_idp_NG036016_C14_H03 | 9f41a522-d121-44cf-a8da-93e1d43bab35 | C04 | Interview took 9 minutes
2026-09-14 | enum_S_06 | idp_NG036005_C08 | idp_NG036005_C08_R01 | dca7fcdf-350b-4183-997d-950651da3d61 | C01 | Respondent did not consent
2026-09-14 | enum_S_10 | non_idp_NG036006_C10 | non_idp_NG036006_C10_H03 | 30c9ffe9-7d4a-47e0-a563-fb1e7981c9e1 | C01 | Respondent did not consent
2026-09-14 | enum_S_16 | non_idp_NG036015_R1_02 | non_idp_NG036015_R1_02_H06 | 76bfcde5-85fb-46ed-9422-c49a79eaff15 | C04 | Interview took 8 minutes
2026-09-14 | enum_S_17 | non_idp_NG036016_C15 | non_idp_NG036016_C15_H01 | f402bc4e-9194-40a2-905c-0bc750b3327f | C04 | Interview took 10 minutes
2026-09-15 | enum_S_03 | non_idp_NG036002_R1_07 | non_idp_NG036002_R1_07_H03 | d06e3e4b-e7aa-4166-b950-b29f2fdbdf4e | C04 | Interview took 6 minutes
2026-09-15 | enum_S_03 | non_idp_NG036002_R1_07 | non_idp_NG036002_R1_07_H05 | 1573ee50-0574-4b49-ac05-6011d15cfd5c | C01 | Respondent did not consent
2026-09-15 | enum_S_04 | non_idp_NG036002_R1_C93 | non_idp_NG036002_R1_07_H06 | 0eb76645-e346-4a5e-9dfe-deeb2d80d0b1 | C05 | Cluster code not in the sample
2026-09-15 | enum_S_14 | non_idp_NG036008_R2_04 | non_idp_NG036008_R2_04_H03 | 53e64bf6-cbc0-43f5-b030-febc199e60c0 | C04 | Interview took 9 minutes
2026-09-15 | enum_S_15 | non_idp_NG036015_R1_03 | non_idp_NG036015_R1_03_H02 | 3f62aee8-4095-49fe-8038-0f2c0271ad71 | C04 | Interview took 8 minutes
2026-09-15 | enum_S_17 | non_idp_NG036016_C16 | non_idp_NG036016_C16_H06 | ab973afe-c48c-4ad3-98ae-65b65238fc03 | C03 | Household already interviewed in an earlier submission
2026-09-16 | enum_S_12 | non_idp_NG036007_R1_02 | non_idp_NG036007_R1_02_H02 | 8f7a6fee-a5e1-4897-9bb2-5bb82675af87 | C01 | Respondent did not consent
2026-09-16 | enum_S_16 | non_idp_NG036015_R2_01 | non_idp_NG036015_R2_01_H02 | 78769ebc-d96d-4452-b000-0847fcc1e8ae | C01 | Respondent did not consent
2026-09-16 | enum_S_18 | non_idp_NG036016_R1_01 | non_idp_NG036016_R1_01_H02 | 13f5f2a0-ed4a-401b-953e-ffbb7d7b8681 | C01 | Respondent did not consent
2026-09-17 | enum_S_16 | non_idp_NG036015_R2_02 | non_idp_NG036015_R2_02_H05 | ec0e9694-fe0f-4190-ac05-5e44d9aaa015 | C01 | Respondent did not consent
2026-09-18 | enum_S_04 | idp_NG036003_R1_02 | idp_NG036003_R1_02_R01 | ca4859be-a96a-42be-8748-b2c3e6ac99d9 | C04 | Interview took 6 minutes
2026-09-19 | enum_S_09 | non_idp_NG036006_C16 | non_idp_NG036006_C16_R02 | 4cdfb3ee-3695-4428-943e-bd78a399d187 | C01 | Respondent did not consent
2026-09-20 | enum_S_04 | idp_NG036003_R1_03 | idp_NG036003_R1_03_H04 | c7fef9c1-4bdd-4d49-80c4-54f1f03f2016 | C01 | Respondent did not consent
2026-09-21 | enum_S_09 | non_idp_NG036006_C17 | non_idp_NG036006_C17_H02 | 737121f1-31d6-4a3e-9b7b-4f5a84b1a7cb | C03 | Household already interviewed in an earlier submission
2026-09-22 | enum_S_09 | non_idp_NG036006_R1_01 | non_idp_NG036006_R1_01_H02 | bf7c77cf-b7fa-4454-a9b1-e1c5d8eb1320 | C04 | Interview took 10 minutes
2026-09-23 | enum_S_04 | idp_NG036003_R1_06 | idp_NG036003_R1_06_H03 | 75728770-c30f-45d0-9516-10668a5e25af | C01 | Respondent did not consent
2026-09-24 | enum_S_10 | non_idp_NG036006_R2_02 | non_idp_NG036006_R2_02_H01 | 4b26b27e-b819-442d-bf23-9d40b08a440d | C02 | Same submission uploaded more than once

## Enumerators
Enumerators
Synthetic data – not real findings
enumerator_id | interviews | median minutes | % repeated answers | interviews removed | interviews flagged | pattern
enum_S_01 | 65 | 41.3 | 0 | 4 | 2
enum_S_02 | 69 | 41.9 | 2.9 | 1 | 2
enum_S_03 | 49 | 42.4 | 4.1 | 6 | 3
enum_S_04 | 82 | 42.1 | 0 | 10 | 7
enum_S_05 | 63 | 42 | 0 | 4 | 6
enum_S_06 | 62 | 40.4 | 0 | 3 | 3
enum_S_07 | 55 | 42.8 | 0 | 1 | 2
enum_S_08 | 79 | 40.9 | 2.5 | 5 | 5
enum_S_09 | 61 | 43.1 | 0 | 5 | 6
enum_S_10 | 68 | 42.9 | 2.9 | 5 | 5
enum_S_11 | 54 | 42 | 0 | 4 | 3
enum_S_12 | 77 | 44.5 | 0 | 4 | 3
enum_S_13 | 74 | 43 | 0 | 1 | 6
enum_S_14 | 51 | 41 | 0 | 7 | 1
enum_S_15 | 62 | 40.7 | 0 | 3 | 5
enum_S_16 | 68 | 42.9 | 0 | 6 | 3
enum_S_17 | 68 | 37 | 0 | 3 | 6
enum_S_18 | 58 | 43.9 | 3.4 | 6 | 4

## Progress
Progress against target by LGA
Synthetic data – not real findings
adm1_name | adm2_name | pop_type | target | achieved | percent
Yobe | Bursari | idp | 84 | 82 | 97.6
Yobe | Bursari | non_idp | 102 | 91 | 89.2
Yobe | Damaturu | idp | 48 | 39 | 81.2
Yobe | Damaturu | non_idp | 102 | 99 | 97.1
Yobe | Fune | idp | 60 | 58 | 96.7
Yobe | Fune | non_idp | 102 | 82 | 80.4
Yobe | Geidam | idp | 90 | 82 | 91.1
Yobe | Geidam | non_idp | 102 | 93 | 91.2
Yobe | Gujba | idp | 42 | 35 | 83.3
Yobe | Gujba | non_idp | 102 | 99 | 97.1
Yobe | Gulani | non_idp | 96 | 89 | 92.7
Yobe | Tarmua | non_idp | 102 | 96 | 94.1
Yobe | Yunusari | idp | 90 | 81 | 90
Yobe | Yunusari | non_idp | 102 | 91 | 89.2